## Sheet1
[6 empty] | Total Stories | [7 empty] | Test Case Execution Summary |  |  |  | Defect Summary
Feature ID | Initiative | Sub Initiative | Module/ Textverification | Parent Title | RAG | Total Stories | Stories Delivered | Stories Not Delivered | Total Test Cases | Completed Test Cases | Pass | Fail | Not Tested | Pass % | Fail % | Not Tested % | Execution % | Total | Critical | High | Medium | Low
4365879 | Platform Consolidation | Analytics | Analytics | March Release Analytics Enhancements | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4366466 |  |  |  | Advisory SA Role Sync in DFD, PLD, Define Team | Completed | 1 | 1 | 0 | 6 | 6 | 6 | 0 | 0 | 100% | 0% | 0% | 100%
4317244 |  | Calculator | DFD-myISP | Song Deals Compliant Logic Update | Completed | 24 | 24 | 0 | 120 | 120 | 120 | 0 | 0 | 100% | 0% | 0% | 100%
4371748 |  | DFD | DFD | Advisory SA - PLD cancellation and Status sync across DFD, PLD and Define Team | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4384974 |  |  |  | ESA role rename to Market Maker ESA | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4384974 |  |  | Market Maker ESA - status sync | ESA role rename to Market Maker ESA_M | Completed | 1 | 1 | 0 | 7 | 7 | 7 | 0 | 0 | 100% | 0% | 0% | 100%
4371748 |  |  | PLD | Advisory SA - PLD cancellation and Status sync across DFD, PLD and Define Team_PLD | Completed | 1 | 1 | 0 | 9 | 9 | 9 | 0 | 0 | 100% | 0% | 0% | 100%
4384974 |  |  |  | ESA role rename to Market Maker ESA_PLD | Awaiting bug fix | 1 | 1 | 0 | 21 | 21 | 19 | 2 | 0 | 90.48% | 9.524% | 0% | 100% | 1 |  |  | 1
4371748 |  |  | PLD - cancellation | Advisory SA - PLD cancellation and Status sync across DFD, PLD and Define Team_PLDCan | Completed | 1 | 1 | 0 | 18 | 18 | 18 | 0 | 0 | 100% | 0% | 0% | 100%
4373652 |  | DSP | DLC | DSP Core Solution Plan Enhancements | Awaiting bug fix | 1 | 1 | 0 | 2 | 2 | 0 | 2 | 0 | 0% | 100% | 0% | 100%
4364390 |  |  | DSP | DSP MDA Enhancements for PPT/PDF | In Progress | 2 | 2 | 0 | 6 | 4 | 2 | 2 | 2 | 50% | 50% | 33.33% | 66.67% | 1 |  |  | 1
4373652 |  |  |  | DSP Core Solution Plan Enhancements_DSP | In Progress | 16 | 16 | 0 | 43 | 34 | 31 | 3 | 9 | 91.18% | 8.824% | 20.93% | 79.07%
4395058 |  |  |  | PPT/PDF Updated for all SGs | In Progress | 4 | 4 | 0 | 12 | 9 | 7 | 2 | 3 | 77.78% | 22.22% | 25% | 75%
4390197 |  |  |  | DSP March 14th CRs | In Progress | 1 | 1 | 0 | 3 | 2 | 0 | 2 | 1 | 0% | 100% | 33.33% | 66.67% | 1 |  |  | 1
4368954 |  | GenAI | CDAT | CDAT Gen AI additional Nudges addition. | Awaiting bug fix | 7 | 7 | 0 | 32 | 32 | 30 | 2 | 0 | 93.75% | 6.25% | 0% | 100%
4223629 |  |  | GEN AI | Retrospective Learnings - Opportunity Benchmarks | In Progress | 43 | 43 | 0 | 106 | 100 | 87 | 13 | 6 | 87% | 13% | 5.66% | 94.34% | 7 |  | 1 | 6
4260380 |  |  |  | March Release DLC Revamp - Gen AI | In Progress | 12 | 12 | 0 | 26 | 22 | 20 | 2 | 4 | 90.91% | 9.091% | 15.38% | 84.62% | 5 |  | 1 | 2 | 2
4317766 |  |  |  | S2C_UI and Role Access changes | In Progress | 4 | 4 | 0 | 10 | 6 | 6 | 0 | 4 | 100% | 0% | 40% | 60%
4319556 |  |  |  | One-Click Review File – Excel Download with Nudge Details and DSP File Links | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4319932 |  |  |  | GEN AI March Enhancements | Awaiting bug fix | 5 | 5 | 0 | 15 | 15 | 11 | 4 | 0 | 73.33% | 26.67% | 0% | 100% | 1 |  |  | 1
4319934 |  |  |  | GEN AI Feb Enhancements | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4369453 |  |  |  | [Gen AI - SSA] - S2C Use Cases | Awaiting bug fix | 4 | 4 | 0 | 12 | 12 | 8 | 4 | 0 | 66.67% | 33.33% | 0% | 100% | 1 |  |  | 1
4373561 |  |  |  | S2C Salesforce Enablement Across Configuration Flows | Awaiting bug fix | 9 | 9 | 0 | 107 | 107 | 105 | 2 | 0 | 98.13% | 1.869% | 0% | 100%
4373741 |  |  |  | Solution Version Comparator Feature in SSA | In Progress | 5 | 5 | 0 | 12 | 11 | 11 | 0 | 1 | 100% | 0% | 8.333% | 91.67% | 2 |  | 1 | 1
4387681 |  |  |  | HSP March Release Enhancements | Completed | 4 | 4 | 0 | 7 | 7 | 7 | 0 | 0 | 100% | 0% | 0% | 100%
4390945 |  |  |  | GEN AI QDI March Enhancements | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4393292 |  |  |  | [Gen AI - SSA] - Enhancements of SSA Chat | In Progress | 5 | 5 | 0 | 19 | 15 | 10 | 5 | 4 | 66.67% | 33.33% | 21.05% | 78.95% | 2 |  | 1 | 1
4372101 |  |  |  | [Gen AI - SSA] - Enhancement of SSA Agent info. pane. | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4369470 |  |  | Solution Review Agent | [Gen AI - SRA] - Review Agent L2 summarization | In Progress | 3 | 3 | 0 | 6 | 5 | 5 | 0 | 1 | 100% | 0% | 16.67% | 83.33%
4392680 |  |  |  | [Gen AI - SRA] - UI changes in Review Agent | Awaiting bug fix | 3 | 3 | 0 | 6 | 6 | 5 | 1 | 0 | 83.33% | 16.67% | 0% | 100% | 1 |  |  | 1
4393835 |  |  |  | [Gen AI - SRA] - SRA Landing Page with DSP, RFP Synthesis Version, Deal Level Canvas, Review Outcomes | Awaiting bug fix | 3 | 3 | 0 | 10 | 10 | 8 | 2 | 0 | 80% | 20% | 0% | 100% | 2 |  |  | 2
4393838 |  |  |  | [Gen AI - SRA] Introducing Opportunity Context screen in Solution Review Agent | Awaiting bug fix | 2 | 2 | 0 | 4 | 4 | 2 | 2 | 0 | 50% | 50% | 0% | 100%
4330816 |  |  | Solution Super Agent | CR: [Gen AI - SSA] - Featuring SSA chat as part of the screen | In Progress | 4 | 4 | 0 | 7 | 6 | 5 | 1 | 1 | 83.33% | 16.67% | 14.29% | 85.71%
4357664 |  |  |  | [Gen AI - SSA] - Span of Search | Awaiting bug fix | 3 | 3 | 0 | 7 | 7 | 6 | 1 | 0 | 85.71% | 14.29% | 0% | 100%
4361786 |  |  |  | [SSA - SCA] - Prompt Library UI changes | Completed | 1 | 1 | 0 | 10 | 10 | 10 | 0 | 0 | 100% | 0% | 0% | 100%
4368560 |  |  |  | [Gen AI - SSA] - PII Reporting form changes. | Awaiting bug fix | 3 | 3 | 0 | 10 | 10 | 7 | 3 | 0 | 70% | 30% | 0% | 100%
4369453 |  |  |  | [Gen AI - SSA] - S2C Use Cases_SuperAgent | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4372101 |  |  |  | [Gen AI - SSA] - Enhancement of SSA Agent info. pane._SuperAgent | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4392680 |  |  |  | [Gen AI - SRA] - UI changes in Review Agent_SuperAgent | Awaiting bug fix | 1 | 1 | 0 | 3 | 3 | 2 | 1 | 0 | 66.67% | 33.33% | 0% | 100%
4278081 |  | KDA | DCSO | myISP - Digital DCSO | Completed | 2 | 2 | 0 | 10 | 10 | 10 | 0 | 0 | 100% | 0% | 0% | 100%
4356899 |  | MSDA | MDA | MDA IMS Personalization - March Release | Awaiting bug fix | 6 | 6 | 0 | 30 | 30 | 15 | 15 | 0 | 50% | 50% | 0% | 100%
4368157 |  |  |  | [MDA-AMS]: View Group-wise Data Across Headcount & Pyramid Reports for Both OCP & MMP routes for Both OCP & MMP Route | Awaiting bug fix | 4 | 4 | 0 | 12 | 12 | 10 | 2 | 0 | 83.33% | 16.67% | 0% | 100%
4368212 |  |  |  | Change Request for MDA PBI reports- March Release | Awaiting bug fix | 3 | 3 | 0 | 10 | 10 | 9 | 1 | 0 | 90% | 10% | 0% | 100%
4390100 |  |  |  | MDA‑Common: Enable Lead Solution Architects to Create MSDA Deal Versions | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4316934 |  | myISP_BPMS | BPMS Onboarding | BPMS Reporting & Compliance UI Suggestions post demo call | Completed | 3 | 3 | 0 | 11 | 11 | 11 | 0 | 0 | 100% | 0% | 0% | 100%
4316945 |  |  |  | Solution Simplification mandatory field updates | Completed | 2 | 2 | 0 | 8 | 8 | 8 | 0 | 0 | 100% | 0% | 0% | 100%
4317373 |  |  |  | Capco Template - Enhancement | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4368357 |  |  |  | TfO Internal Approvals: Enable auto‑approval when lead does not approve the approval request | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4368359 |  |  |  | Custom meeting slots for BPMS meeting scheduler | Completed | 1 | 1 | 0 | 5 | 5 | 5 | 0 | 0 | 100% | 0% | 0% | 100%
4368361 |  |  |  | VMM out of scope status and risk and compliance auto insert block for Foxtrot Q1 = No | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4371834 |  |  |  | Benchmark Report - Add a column for Lead SA - Operations | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4371836 |  |  |  | Reporting Layer: CXTA Fields to be added | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4371914 |  |  |  | Client name should be mapped to MasterCustomerNM in Mob architect , CXTA email & Reporting Layer | Completed | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4378908 |  |  |  | Diel hierarchy - rolled up revenue | Completed | 9 | 9 | 0 | 33 | 33 | 33 | 0 | 0 | 100% | 0% | 0% | 100%
4385939 |  |  |  | Addition of information in mobilization SA and CXTA User request email | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4385941 |  |  |  | Generative AI productivity calculation by Year on Year productivity % in separate columns | Completed | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 100% | 0% | 0% | 100%
4387610 |  |  |  | Enterprise SA should have Read–Write access to the Reporting & Compliance module | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4387613 |  |  |  | Operations toggle enable only for BPMS SG | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4387615 |  |  |  | Solution status based on Transition status stream | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4386527 |  | NextGen | Advisory SA - SONG | PLD - Advisory SA Role | Completed | 6 | 6 | 0 | 35 | 35 | 35 | 0 | 0 | 100% | 0% | 0% | 100%
4386527 |  |  | Advisory SA - Song | PLD - Advisory SA Role_Song | Awaiting bug fix | 14 | 14 | 0 | 66 | 66 | 65 | 1 | 0 | 98.48% | 1.515% | 0% | 100%
4366466 |  |  | Advisory SA - SONG role enablement | Advisory SA Role Sync in DFD, PLD, Define Team_ASA | Completed | 1 | 1 | 0 | 7 | 7 | 7 | 0 | 0 | 100% | 0% | 0% | 100%
4365879 |  |  | Analytics | March Release Analytics Enhancements_Analytics | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4275996 |  |  | BPMS Onboarding | RA BPMS Feedback | Completed | 2 | 2 | 0 | 8 | 8 | 8 | 0 | 0 | 100% | 0% | 0% | 100%
4387609 |  |  | Common | Comma formatting in all raise request emails | Completed | 1 | 1 | 0 | 7 | 7 | 7 | 0 | 0 | 100% | 0% | 0% | 100%
4344500 |  |  | Cross Service PLD | Feb21¦¦UAT1¦¦PLD¦¦In Cluster management under Generate Pricing->One Click Pricing, Add Group is enabled in Actions column for cross service lead role. | Completed | 1 | 1 | 0 | 7 | 7 | 7 | 0 | 0 | 100% | 0% | 0% | 100%
4278081 |  |  | DCSO | myISP - Digital DCSO_DCSO | Awaiting bug fix | 21 | 21 | 0 | 86 | 86 | 65 | 21 | 0 | 75.58% | 24.42% | 0% | 100%
4365826 |  |  | Document Type Rename | March Release NextGen Enhancements_DTR | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4365826 |  |  | ESA to Market Maker ESA | March Release NextGen Enhancements_ESA | Completed | 2 | 2 | 0 | 13 | 13 | 13 | 0 | 0 | 100% | 0% | 0% | 100%
4365879 |  |  |  | March Release Analytics Enhancements_ESA | Completed | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 100% | 0% | 0% | 100%
4365826 |  |  | myISP Enhancements | March Release NextGen Enhancements_MYISP Enhancements | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4365826 |  |  | Role Rename | March Release NextGen Enhancements_Rolerename | Completed | 7 | 7 | 0 | 18 | 18 | 18 | 0 | 0 | 100% | 0% | 0% | 100%
4365826 |  |  | Self Assign | March Release NextGen Enhancements_SelfAssign | Completed | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 100% | 0% | 0% | 100%
4278081 |  |  | SI - pcw | myISP - Digital DCSO_SIPCW | In Progress | 1 | 1 | 0 | 9 | 8 | 6 | 2 | 1 | 75% | 25% | 11.11% | 88.89%
4366466 |  |  | Small Deal - COE | Advisory SA Role Sync in DFD, PLD, Define Team_COE | Completed | 1 | 1 | 0 | 7 | 7 | 7 | 0 | 0 | 100% | 0% | 0% | 100%
4139936 |  | NextGen SI | AEP-myISP | Enhance AEP refresh feature to handle use cases where SA updates DNP, Pricing, other screens on myISP end | Completed | 1 | 1 | 0 | 5 | 5 | 5 | 0 | 0 | 100% | 0% | 0% | 100%
4318937 |  | PCW | PCW | Billable Expenses Method as % of Price inclusion in JSON in Lower environment | Awaiting bug fix | 1 | 1 | 0 | 9 | 9 | 7 | 2 | 0 | 77.78% | 22.22% | 0% | 100%
4389866 |  |  |  | PCW Enhancements and User Feedback - March Release | In Progress | 1 | 1 | 0 | 6 | 3 | 1 | 2 | 3 | 33.33% | 66.67% | 50% | 50% | 1 | 1
4359602 | Rapid Soln | Analytics | DATA Refresh | Omdia Mapping data FY2025 - for the platform | Completed | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 100% | 0% | 0% | 100%
4373529 |  | DCTA | AMS | Updating the logic for calculating productivity assessment values | Awaiting bug fix | 1 | 1 | 0 | 6 | 6 | 3 | 3 | 0 | 50% | 50% | 0% | 100%
4351343 |  |  | IMS MMP | Price to Client after Negotiation Contingency calculation | Awaiting bug fix | 1 | 1 | 0 | 4 | 4 | 3 | 1 | 0 | 75% | 25% | 0% | 100%
4351343 |  |  | Pricing | Price to Client after Negotiation Contingency calculation_Pricing | Completed | 2 | 2 | 0 | 8 | 8 | 8 | 0 | 0 | 100% | 0% | 0% | 100%
4371605 |  |  | SI DCTA | Billable Expenses as % of Price UI | Awaiting bug fix | 1 | 1 | 0 | 3 | 3 | 2 | 1 | 0 | 66.67% | 33.33% | 0% | 100%
4371607 |  |  |  | MMP release: Billable Expense as % of Price | Completed | 2 | 2 | 0 | 5 | 5 | 5 | 0 | 0 | 100% | 0% | 0% | 100%
4371610 |  |  | SI OCP | Billable Expense as % of Price | Awaiting bug fix | 1 | 1 | 0 | 6 | 6 | 5 | 1 | 0 | 83.33% | 16.67% | 0% | 100%
4390112 |  | GenAI | AMS Refactoring Scope | AMS MVP1 – Refactoring Scope for Mar 28 (Profiles, Groups, Group‑wide Pricing, Other Cost, Planner Agent) | Awaiting bug fix | 5 | 5 | 0 | 75 | 75 | 70 | 5 | 0 | 93.33% | 6.667% | 0% | 100% | 4 |  | 3 | 1
4318876 |  |  | AMS Solution Configuration Agent | AMS SCA MVP2 March 28th Release Scope | Awaiting bug fix | 14 | 14 | 0 | 178 | 178 | 141 | 37 | 0 | 79.21% | 20.79% | 0% | 100% | 11 |  | 7 | 4
4269015 |  | NextGen | AMS | AMS - Staffing OU Across versions for AMS & edit in File name | Awaiting bug fix | 1 | 1 | 0 | 6 | 6 | 4 | 2 | 0 | 66.67% | 33.33% | 0% | 100%
4317843 |  |  |  | Enhancement for Generative AI tab for AMS | Awaiting bug fix | 1 | 1 | 0 | 4 | 4 | 2 | 2 | 0 | 50% | 50% | 0% | 100%
4278081 |  |  | DCSO | myISP - Digital DCSO_NGR | Awaiting bug fix | 6 | 6 | 0 | 20 | 20 | 11 | 9 | 0 | 55% | 45% | 0% | 100% | 4 |  | 2 | 1 | 1
4275381 |  | NextGen SI | DCSO | myISP - Online SI API's for DSCO | Completed | 1 | 1 | 0 | 6 | 6 | 6 | 0 | 0 | 100% | 0% | 0% | 100%
4371812 |  | OCP | AMS | Updating the Staffing OU Import Export Validation logic based on Modified On column | Awaiting bug fix | 1 | 1 | 0 | 3 | 3 | 2 | 1 | 0 | 66.67% | 33.33% | 0% | 100%
4316161 |  |  | AMS, SI, DCTA | Updating the logic for populating the Deal Rag Status in KDA Variance Analysis Report | Awaiting bug fix | 1 | 1 | 0 | 10 | 10 | 9 | 1 | 0 | 90% | 10% | 0% | 100%
4316161 |  |  | AMS, SI, OCP | Updating the logic for populating the Deal Rag Status in KDA Variance Analysis Report_OCP | Completed | 1 | 1 | 0 | 11 | 11 | 11 | 0 | 0 | 100% | 0% | 0% | 100%
4272104 |  |  | BPMS | BPMS OCP: Cost/FTE/Year report | Awaiting bug fix | 1 | 1 | 0 | 5 | 5 | 4 | 1 | 0 | 80% | 20% | 0% | 100%
4351343 |  |  | IMS OCP | Price to Client after Negotiation Contingency calculation_IMSOCP | Completed | 1 | 1 | 0 | 4 | 4 | 4 | 0 | 0 | 100% | 0% | 0% | 100%
4371602 |  |  |  | Sending Roles and Open for SA notes to MSDA along with Cost Description and Category | Awaiting bug fix | 1 | 1 | 0 | 4 | 4 | 3 | 1 | 0 | 75% | 25% | 0% | 100%
4364026 |  |  | OCP/DCTA | OCP/DCTA - Updating the logic for Calculating productivity assessment values in Recommended Productivity section | Completed | 1 | 1 | 0 | 3 | 3 | 3 | 0 | 0 | 100% | 0% | 0% | 100%
4352766 |  |  | Pricing | Corrections in OCP/DCTA Resource Level Excel Export Reports | Awaiting bug fix | 4 | 4 | 0 | 15 | 15 | 13 | 2 | 0 | 86.67% | 13.33% | 0% | 100%
4364026 |  |  |  | OCP/DCTA - Updating the logic for Calculating productivity assessment values in Recommended Productivity section_Pricing | Awaiting bug fix | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 0 | 33.33% | 66.67% | 0% | 100%
4378855 |  |  |  | Including Client Volume Discount for BPMS OCP | Completed | 1 | 1 | 0 | 5 | 5 | 5 | 0 | 0 | 100% | 0% | 0% | 100%
4358815 | V2V | Calculator | Mobilization Calculator | Mobilization - CXTA Calculator : CXTA enhancements | Completed | 2 | 2 | 0 | 8 | 8 | 8 | 0 | 0 | 100% | 0% | 0% | 100%
4330994 |  | V2V | Value Shaping | Value Shaping –Enhancements | Awaiting bug fix | 26 | 26 | 0 | 70 | 70 | 55 | 15 | 0 | 78.57% | 21.43% | 0% | 100% | 1 |  |  | 1
[18 empty] | 24 |  | 10 | 10 | 4
[6 empty] | 369 | 369 | 0 | 1592 | 1552 | 1366 | 186 | 40 | 88.02% | 11.98% | 2.513% | 97.49% | 69 | 1 | 26 | 35 | 7