## Bug Summary
ID | Title | Severity | Node Name | AD POC | SM POC | M POC | Defect Record | TextVerification | State | StageFound
4372095 | Pilot User Error: Staffing import operation failed: Import was not successful: Excel import failed due to system error. _Trigger Date - 2/15/2026 | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Prod | Agent-SCA | Ready to Deploy | Production
4372099 | Pilot User Error: Staffing file import operation failed: Import was not successful: Excel import failed due to system error _Trigger Date - 2/15/2026 | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Prod | Agent-SCA | Ready to Deploy | Production
4383717 | Pilot user bug_Feb 21st¦ UAT1¦ Mobilization Calculator¦ Bottom Up¦ For Subcontractor Profiles, FTES are not displaying in wave mapping | 2 - High | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | Prod user bug | Mobilization Calculator | Active | User Acceptance Test
4420975 | UAT____AI Foundry_The message is incorrect when the deal is not eligible for Gen AI Embedded | 3 - Medium | CodeCrafters | madhuri.chintala | c.dhiman | sona.job | 4318876 | AMS Solution Configuration Agent | Blocked in UAT | User Acceptance Test
4422932 | 28th March ¦ PT ¦ Login as SA > Multitower Deal (AMS, SI) Digital DCSO not generated for AMS still Green Tick Displayed under opportunity workflow | 3 - Medium | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj |  | DCSO | Deferred | Product Test
4428315 | 28th March ¦ PT/UAT ¦ Available Hours ¦ Getting system error when updated excel file is imported. | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4367340 | AMS | Resolved | Product Test
4434967 | UAT__AI--Foundry___Gen AI: Differentiation is marked apart from GenWizard still getting incorrect message in Agent and also unable to see update on UI under Generative AI screen. | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Ready to Deploy | User Acceptance Test
4436636 | 28th March ¦ UAT ¦ Available Hrs ¦ Annual hrs in excel is not displayed in yellow for subk profiles. | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4367340 | AMS | Active | Product Test
4436840 | 28th March ¦ UAT ¦ Available hrs ¦ Monthly values are not displayed in yellow even after changing the Default value to 'No' for PMO section in the export excel. | 4 - Low | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4367340 | AMS | Active | Product Test
4436981 | Regression : UAT___AI--Foundry____Agent shows MMP generated successfully but it is still at Sent to MMP state | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Solution Configuration Agent | Blocked | User Acceptance Test
4437674 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hours ¦ Annual Hours values are editable in Available Hrs export in case of default value is Yes but still columns are highlighting in grey. | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4367340 | AMS | Re-open | User Acceptance Test
4437685 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hours ¦ Annual hours are still editable even though Default value is marked as "No" in export for Subk Profiles. | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4367340 | AMS | Re-open | User Acceptance Test
4438166 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hours ¦ Avl hours export shows completed state only after navigating to other tab and navigating back to Export/Import tab | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4367340 | AMS | Resolved | User Acceptance Test
4439180 | UAT__AI--Foundry___Gen AI: Differentiation is marked apart from GenWizard, GenAI tracking section marked as Non embedded but reason not selected still showing as GenAI config save successfully. | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Active | User Acceptance Test
4439703 | UAT___AI__Foundry___Agent is running through ramp up and staffing steps even though prompt is related to update of Pricing input screen in existing version | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4390112 | AMS Refactoring Scope | Ready to Deploy | User Acceptance Test
4439739 | 28th March_UAT2_OBM_Demographics section data is not displaying properly for SI and IMS | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4223629 | GEN AI | Re-open | Product Test
4444390 | 28th March ¦ UAT2 ¦ SI AEP ¦ Profiles are not flowing for AEP Versions | 3 - Medium | DevStormers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Regression | AEP | Active | User Acceptance Test
4444409 | Mar 28 ¦ Prod Env ¦ Agent AI Foundry ¦ US_ 4351206 ¦ Profile NRR ¦ Total NRR count is not getting Added in Active tab. | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Re-open | Product Test
4445143 | Regression ¦ UAT___AI__Foundry____Pricing input : Agent not able to configure Group wide Hourly rate. | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Refactoring Scope | Active | User Acceptance Test
4445260 | April 03_UAT_Gen AI_OBM values are not matching with solution version Data for SI | 2 - High | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | Re-open | Product Test
4446839 | [Automated Tracking bug]: Prod ¦ OCP ¦ Simulation Failed with Exception Message | 3 - Medium | Simulators | srinivasan.ks | vishnupriya.aluru | K.devaraj |  |  | Active | Production
4446855 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ OCP and MMP are getting skipped with "Capability, Specialty, Skill does NOT EXISTS in some of the profiles" error even though valid skills are already available. | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Sanity | AMS Solution Configuration Agent | Ready to Deploy | Product Test
4446945 | Mar 28¦¦ Prod Sanity ¦¦ AI--Foundry ¦¦ Agent is not displaying info message if staffing is imported with rate card applied to records even though Pricing input is not hourly rate | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Re-open | User Acceptance Test
4446956 | Mar 28¦¦ Prod Sanity ¦¦ AI--Foundry ¦¦ Agent is calling "Save Pricing Configuration" step twice | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4390112 | AMS Refactoring Scope | Ready to Deploy | User Acceptance Test
4446959 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ Multiple functional issues in Rate card import functionality | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Sanity | AMS Solution Configuration Agent | Ready to Deploy | Product Test
4446972 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ Import PMO is displaying System error message. | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Sanity | AMS Solution Configuration Agent | Ready to Deploy | Product Test
4447047 | March 28th ¦¦ Prod Sanity ¦¦ DSP ¦ Scope ¦ Detailed scope ¦ "Hyper care" field is not highlighting even It was selected in WRWS service offerings | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4373652 | DSP | Active | User Acceptance Test
4451687 | April 18 ¦¦ PROD ¦¦ DSP ¦¦ List of version is not present in existing old dsp versions in Appendix | 3 - Medium | NinjaWarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Sanity | DSP | New | Product Test
4452033 | April 18 ¦¦ Prod ¦¦ Estimator/Calculator ¦¦ IMS Mobilization is displaying in gallery tab | 3 - Medium | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri |  | gallery | New | Sanity Testing
4458816 | UAT2 env ¦¦OBM ¦¦ SVC _ KDA Table Value mismatch issue ¦¦ SI SG | 2 - High | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | Active | Product Test
4460514 | April 18 ¦ PT ¦ SI ¦ DSCO¦ Blank page displayed on clicking Digital DCSO in Digital Documentation | 2 - High | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj |  | PCW | New | User Acceptance Test
4460790 | April18th¦Sanity¦PT¦BPMS¦Review approval tile is not loading for both screen Reporting & compliance, Solution review & approval | 2 - High | mySPIntegratedSolutionPlatform |  |  |  | Sanity | Opportunity workflow | New | Product Test
4461424 | 18th April¦ UAT ¦ SI DCTA ¦ Custom rate card data is not flowing in MMP griddy | 3 - Medium | TechSprinters | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Regression | SI | BA clarification | User Acceptance Test
4461622 | UAT2_OBM_Opp metrics table_ columns showing expand icon but not having sub-columns | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | BA clarification | Product Test
4461710 | Apr 18 ¦ UAT ¦ OBM ¦ SVC ¦ IMS Security Data Mismatch | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | OBM | Active | Product Test
4461770 | 18th Apr¦ UAT ¦ SI ¦When the Technology role is selected, the corresponding Standard Role is highlighted in red in staffing OU | 3 - Medium | TechWizards | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD | Ready to Deploy | Product Test
4462015 | UAT2_OBM_ Benchmark / In-progress deal validation _ Cost & KDA Mismatch _ AMS SG | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | Active | Product Test
4462287 | 18 Apr ¦ myISP ¦ UAT¦ SI Staffing Baseline ¦¦ Technology Role and Standard Role values are cleared instantly. | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | Staffing Baseline | Active | Product Test
4462325 | April 18th ¦¦ Prod ¦¦ DSP Summary _ Review & Approvals Screen _ Signoff Status & Stage 2B/3B is not present in PPT/PDF | 3 - Medium | Pirates | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Prod Bug | DSP | New | Product Test
4462431 | 18th April ¦ UAT ¦ Super User ¦ Dashboard breadcrumb redirecting to PMO Manage | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | Regression | myISP | Ready to Deploy | User Acceptance Test
4462433 | APRIL UAT ¦ SI KDA REPORTS ISSUE 1 | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4386341 | SI KDA REPORTS ISSUE | Active | User Acceptance Test
4462436 | Gen AI ¦¦ OBM ¦¦ Align UX with Figma Prototype | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | Gen AI | Active | User Acceptance Test
4462476 | 18th April ¦ UAT ¦ SI ¦ When SG/SSG is Updated in profile screen the Role type is not getting mapped according to updated SG in staffing baseline | 3 - Medium | TechWizards | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD Role | Ready to Deploy | Product Test
4462512 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role should initially have dropdown values before Technology Role is selected (SAP,Salesforce and Custom Development Solutions under SI) | 3 - Medium | Tech Ensemble | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | SI-PCW | Active | Product Test
4462520 | 18 Apr_UAT_PCW_ For a Checked in version , Standard role is not populating in Staffing UI | 3 - Medium | TechAvatar | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | NextGen SI | Active | Product Test
4462540 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role is not coming back after refresh for SI SG | 2 - High | TechAvatar | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | SI-PCW | Active | Product Test
4462585 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Forecast data is not coming back | 3 - Medium | Tech Ensemble | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Sanity | SI - PCW | Active | Product Test
4462634 | UAT2_OBM_ Activae tab is not clearly visible issues | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | Resolved | Product Test
4462642 | Apr 18 ¦ UAT ¦ OBM ¦ IMS - CORE ¦ Missing Values in OBM | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | OBM | Re-open | Product Test
4462668 | 18th Apr ¦ UAT ¦ SI ¦ Few Accenture Role/Type is getting highlighted in Red in MMP FFP Template | 3 - Medium | BA Support | arul.vasu | arul.vasu | varsha.b.rani | 4389877 | MMP FFP | Active | Product Test
4462685 | UAT2_OBM_ Recommendations for your solution issue | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | New | Product Test
4462715 | APRIL UAT ¦ MMP Resource Template issue 2 | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4386341 | SI KDA REPORTS ISSUE | Active | User Acceptance Test
4463613 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role is not retained when Technology is changed from SAP to non-SAP (SI SG) | 4 - Low | Tech Ensemble | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | SI-PCW | New | Product Test
4463621 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role is not retained when SG is changed from SI to non-SI (SAP tech) | 4 - Low | Tech Ensemble | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | SI-PCW | New | Product Test
4463627 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Wrong validation message when Technology Role is not selected for applicable SI profiles | 3 - Medium | Tech Ensemble | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | SI-PCW | Active | Product Test
4464301 | 18th Apr ¦ PT/UAT¦ SI ¦when triggers are in progress all buttons in the Generate Pricing screen are enabled | 2 - High | TechSprinters | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Sanity | SI | Ready to Deploy | Product Test
4464439 | 18th April¦ UAT ¦ SI ¦ For "CON-CAS" Client Ratecard is not flowing in myISP Ratecard UI | 3 - Medium | TechSprinters | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Regression | SI | Active | User Acceptance Test
4464475 | Apr 18 ¦ UAT ¦ OBM ¦ SVC ¦ Cost and Metrics at Glance - Response Issue | 1 - Critical | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | OBM | New | Product Test
4464985 | OBM ¦PROD validation ¦ PBI column width is not uniform | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | BA clarification | Product Test
4465797 | 18th April ¦ UAT ¦ SI ¦ Getting duplicate profiles in target version while doing carting | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Regression | SI | Active | User Acceptance Test
4465936 | 18th Apr ¦UAT ¦ SI ¦ The Role type is populating for other SSG which is not mentioned in the Role type sheet | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD Role | Active | Product Test
4465961 | 18 Apr ¦ myISP ¦ UAT¦ SI Staffing Baseline ¦¦ From OU Validations & Error messages is not showing in UI | 2 - High | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | myISP | Ready to Deploy | Product Test
4466177 | APRIL UAT ¦ SI KDA REPORTS ISSUE 2 | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4386341 | SI KDA REPORTS ISSUE | New | User Acceptance Test
4466178 | 18 Apr_UAT_SI_Staffing Baseline_Staffing OU _Facing performance issue in Staffing Import | 3 - Medium | TechWizards | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | NextGen SI | Active | Product Test
4466202 | APRIL UAT ¦ LCM INFRA & COTS REPLATFROM UI | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4386341 | LCM COTS REPLATFROM UI | New | User Acceptance Test
4466282 | 18th April¦ UAT ¦ SI ¦ In Technology Role dropdown few roles are missing for SAP, Salesforce, Custom Development solutions Technology | 3 - Medium | TechSprinters | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD Role | BA clarification | User Acceptance Test
4466857 | 18th April¦ UAT ¦ SI ¦ For applicable SG and Technology "Technology Role" is not highlighting in Amber and without configuring "Technology Role" Screen is getting saved in Staffing Baseline | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD Role | Active | User Acceptance Test
4467462 | APRIL UAT ¦ SI KDA REPORTS Variance Logic | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4386341 | SI KDA REPORTS ISSUE | New | User Acceptance Test
4467554 | 18th Apr ¦UAT ¦ SI ¦Role type values are not populating as per staffing baseline Screen in MMP FFP Template | 2 - High | BA Support | arul.vasu | arul.vasu | varsha.b.rani | 4389877 | MMP FFP | BA clarification | Product Test
4467583 | Apr 18 ¦ UAT 2¦ OBM ¦ IMS _Opportunity is getting blank in OBM metrices table | 1 - Critical | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | OBM | New | Product Test
4467585 | Apr 18 ¦¦ PLD ¦¦ PT Sanity ¦¦ Save button is not working in Edit SA Assignment Popup | 3 - Medium | Pacemakers | madhuri.chintala | c.dhiman | sona.job | Sanity | PLD | Active | Product Test
4467592 | Apr 18 ¦ UAT 2¦ OBM ¦ 0’ value is impacting the average Onshore LCR | 1 - Critical | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | OBM | New | Product Test
4467787 | 18th April ¦ PT & UAT ¦ SI SDL ¦ PCW 8.7 ¦ Role type column values are not flowing in UI, so in SDL for a PCW version | 2 - High | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | SDL | New | Product Test