## Sheet1
ID | Title | Defect Record | TextVerification | Node Name | StageFound | Severity | State | Category | mySP RCA | Re open Count | Created Date | Closed Date | Work Item Type | AD POC | SM POC | M POC
4367003 | 21 Feb ¦ PLD ¦ Unassigned ¦ After assignment deal flowing in unassigned grid. | 4224175 | Cross Service PLD | Pacemakers | User Acceptance Test | 3 - Medium | Closed | Functional | Code Issue | 1 | 2026-02-13 | 2026-04-03 | Bug | madhuri.chintala | c.dhiman | sona.job
4372095 | Pilot User Error: Staffing import operation failed: Import was not successful: Excel import failed due to system error. _Trigger Date - 2/15/2026 | Prod | Agent-SCA | agentcrafters | Production | 2 - High | Ready to Deploy | Functional | Not reproduceable / Invalid data | 0 | 2026-02-18 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4372099 | Pilot User Error: Staffing file import operation failed: Import was not successful: Excel import failed due to system error _Trigger Date - 2/15/2026 | Prod | Agent-SCA | agentcrafters | Production | 2 - High | Ready to Deploy | Functional | Not reproduceable / Invalid data | 0 | 2026-02-18 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4372103 | Pilot User Error: Staffing file import operation failed: Error: conversationId or messageId not provided in context. Execution stopped. _Trigger Date - 2/15/2026 | Prod | Agent-SCA | agentcrafters | Production | 2 - High | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-02-18 | 2026-04-07 | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4383717 | Pilot user bug_Feb 21st¦ UAT1¦ Mobilization Calculator¦ Bottom Up¦ For Subcontractor Profiles, FTES are not displaying in wave mapping | Prod user bug | Mobilization Calculator | Everest | User Acceptance Test | 2 - High | Active | Functional |  | 0 | 2026-02-20 |  | Bug | srinivasan.sivakumar | suresh.devarajan | nityanand.giri
4409942 | Regression ¦Pilot User¦ : UAT__AI-Foundry__Facing multiple issues during deal configuration | Regression | AMS Solution Configuration Agent | agentcrafters | User Acceptance Test | 2 - High | Ready to Test | Functional | Code Issue | 0 | 2026-03-04 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4411096 | March 28 ¦¦ PROD ¦¦ DSP ¦¦ BPMS ¦¦ Issue in Bulk upload template | SA defect | DSP | Ninjawarriors | Product Test | 2 - High | Ready to Test | functional |  | 0 | 2026-03-05 |  | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4415534 | March 28} UAT¦ UI Issues in SVC | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | PT In Test | UI |  | 0 | 2026-03-09 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4416137 | ¦ Prod ¦ DSP ¦ BPMS ¦ Productivity Detail ¦ BPMS productivity Percentage calculation is incorrect, and Data spread across multiple slides. | Prod Bug | DSP | Ninjawarriors | Product Test | 3 - Medium | Closed | UI | Code Issue | 0 | 2026-03-10 | 2026-04-07 | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4419582 | May 9 ¦¦ UAT2¦¦ DSP ¦¦ Staffing Headcount ¦¦ Data is blank in PPT/PDF | SA Defect | DSP | Ninjawarriors | Product Test | 2 - High | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-03-10 | 2026-03-30 | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4420975 | UAT____AI Foundry_The message is incorrect when the deal is not eligible for Gen AI Embedded | 4318876 | AMS Solution Configuration Agent | CodeCrafters | User Acceptance Test | 3 - Medium | Blocked in UAT | Functional | Code Issue | 2 | 2026-03-11 |  | Bug | madhuri.chintala | c.dhiman | sona.job
4422932 | 28th March ¦ PT ¦ Login as SA > Multitower Deal (AMS, SI) Digital DCSO not generated for AMS still Green Tick Displayed under opportunity workflow |  | DCSO | TechStars | Product Test | 3 - Medium | Deferred | functional |  | 0 | 2026-03-12 |  | Bug | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj
4423217 | March 28¦ UAT} PMO cost not displayed under opportunity cost in OBM | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional |  | 1 | 2026-03-12 | 2026-04-02 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4426359 | [Automated Tracking bug]: Prod ¦ OCP ¦ Simulation Failed |  |  | CodingCrusaders | Production | 3 - Medium | Closed |  | Environment Issue | 0 | 2026-03-14 | 2026-04-03 | Bug | srinivasan.ks | vishnupriya.aluru | K.devaraj
4427830 | Mar28th_UAT_Gen AI_Retrospective learning _ Benchmark Opportunity List _ Sort icon is missing | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-03-16 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4428315 | 28th March ¦ PT/UAT ¦ Available Hours ¦ Getting system error when updated excel file is imported. | 4367340 | AMS | TechCoders | Product Test | 2 - High | Resolved | Functional |  | 0 | 2026-03-16 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4428622 | 28th Mar UAT ¦ Gen AI ¦ OBM ¦ Performance of expand row button | 4223629 | Gen AI | QDI - Opportunity Metrics | User Acceptance Test | 3 - Medium | Ready to Test |  |  | 0 | 2026-03-16 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4428627 | 28th Mar UAT ¦ Gen AI ¦ OBM ¦ RAG indicators not displayed although current and average values exist | 4223629 | Gen AI | QDI - Opportunity Metrics | User Acceptance Test | 3 - Medium | Ready to Test |  |  | 0 | 2026-03-16 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4432704 | Mar28th_UAT_Gen AI_SVC_IMS Security is missing & data issue | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-03-17 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4432710 | Mar28th_UAT_Gen AI_BenchMark Opp pop up_IMS Security is missing | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-03-17 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4432734 | March 28¦ UAT¦ OBM¦ IMS security tab is not displayed under the Opportunity metrics and cost metrics table | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | Closed |  |  | 0 | 2026-03-17 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4434967 | UAT__AI--Foundry___Gen AI: Differentiation is marked apart from GenWizard still getting incorrect message in Agent and also unable to see update on UI under Generative AI screen. | 4318876 | AMS Solution Configuration Agent | agentcrafters | User Acceptance Test | 2 - High | Ready to Deploy | Functional | Lack of environment knowledge / Inadequate version control on environment/ Lack of availability of the proper environment | 0 | 2026-03-18 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4436636 | 28th March ¦ UAT ¦ Available Hrs ¦ Annual hrs in excel is not displayed in yellow for subk profiles. | 4367340 | AMS | TechCoders | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-03-19 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4436693 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ CDAT - MFE ¦ Edit and Add comment popups are not opening |  | Angular Upgrade Drop 3 - Higher Environment Sanity Testing Issue Fixing | MYISP_Revamp_UI | Sanity Testing | 3 - Medium | Closed |  | Code Issue | 0 | 2026-03-19 | 2026-03-19 | Bug | srinivasan.ks | mahesh.kt | vikrant.r.mohite
4436955 | 28th March_UAT2_OBM_In IMS the Number of opportunities which is selected in Benchmark Opportunity filter is not available in Table in Opportunity cost and metrics tab | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-03-19 | 2026-04-07 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4436981 | Regression : UAT___AI--Foundry____Agent shows MMP generated successfully but it is still at Sent to MMP state | Regression | AMS Solution Configuration Agent | agentcrafters | User Acceptance Test | 2 - High | Blocked | Functional | Code Issue | 0 | 2026-03-19 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4438691 | 28th March ¦ UAT2 ¦ DCSO ¦ Under Digital DCSO after generating file status is not highlighted to green and uploading the file not highlighted to blue color. | 4278081 | DCSO | TechStars | User Acceptance Test | 4 - Low | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-03-23 | 2026-03-23 | Bug | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj
4438839 | UI Inconsistency ¦¦ AMS/SI¦¦ Tax Input ¦¦ UI Issues under Tax Input | UI Incosistency | UI Inconsistency | MYISP_Revamp_UI | Product Test | 4 - Low | Closed | UI |  | 0 | 2026-03-23 | 2026-04-02 | Bug | srinivasan.ks | mahesh.kt | vikrant.r.mohite
4439180 | UAT__AI--Foundry___Gen AI: Differentiation is marked apart from GenWizard, GenAI tracking section marked as Non embedded but reason not selected still showing as GenAI config save successfully. | 4318876 | AMS Solution Configuration Agent | agentcrafters | User Acceptance Test | 2 - High | Active | Functional | Insufficient application knowledge / Invalid data | 0 | 2026-03-23 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4439703 | UAT___AI__Foundry___Agent is running through ramp up and staffing steps even though prompt is related to update of Pricing input screen in existing version | 4390112 | AMS Refactoring Scope | agentcrafters | User Acceptance Test | 3 - Medium | Ready to Deploy | Functional | Code Issue | 2 | 2026-03-24 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4439710 | 28th March_UAT2_OBM_Client type field is missing in Demographics section | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional | New Feature / Enhancement | 0 | 2026-03-24 | 2026-04-06 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4439739 | 28th March_UAT2_OBM_Demographics section data is not displaying properly for SI and IMS | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Re-open | Functional |  | 1 | 2026-03-24 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4443664 | 28th Mar UAT ¦ Gen AI ¦ SVC ¦ Solution Standards RAG indicator not shown | 4373741 | Gen AI | QDI - Opportunity Metrics | User Acceptance Test | 2 - High | Closed | Funcational |  | 0 | 2026-03-25 | 2026-04-06 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4444377 | Mar28th_UAT_Gen AI_Benchmark Opp pop up _Latency in UI and Benchmark opp missing in OBM table for IMS and SI Sg | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | UI | Code Issue | 1 | 2026-03-26 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4444390 | 28th March ¦ UAT2 ¦ SI AEP ¦ Profiles are not flowing for AEP Versions | Regression | AEP | DevStormers | User Acceptance Test | 3 - Medium | Active | Functional |  | 0 | 2026-03-26 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4444409 | Mar 28 ¦ Prod Env ¦ Agent AI Foundry ¦ US_ 4351206 ¦ Profile NRR ¦ Total NRR count is not getting Added in Active tab. | 4318876 | AMS Solution Configuration Agent | agentcrafters | Product Test | 2 - High | Re-open | Functional | Inadequacy of available test data / Incorrect Data | 0 | 2026-03-26 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4445143 | Regression ¦ UAT___AI__Foundry____Pricing input : Agent not able to configure Group wide Hourly rate. | Regression | AMS Refactoring Scope | agentcrafters | User Acceptance Test | 2 - High | Active | Functional | Requirement Clarity Issue | 0 | 2026-03-26 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4445257 | April 03_UAT_Gen AI_OBM values are not matching with solution version Data for AMS | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | Closed | Functionality | Code Issue | 0 | 2026-03-26 | 2026-04-07 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4445260 | April 03_UAT_Gen AI_OBM values are not matching with solution version Data for SI | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | Re-open | Functionality | Code Issue | 1 | 2026-03-26 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446042 | April 03_UAT_Gen AI_SVC values are not matching with solution version Data for SI | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | Closed | Functionality | Code Issue | 1 | 2026-03-27 | 2026-04-06 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446043 | April 03_UAT_Gen AI_SVC values are not matching with solution version Data for AMS | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | Closed | Functionality |  | 0 | 2026-03-27 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446307 | 28th March ¦ UAT2 ¦ Gen AI ¦ SVC ¦ OBM ¦Spacing between the text is not as per the attached screenshot in the US. | 4445983 | Gen AI | QDI - Opportunity Metrics | User Acceptance Test | 4 - Low | Closed | UI | UX Design / UI Issue | 0 | 2026-03-27 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446839 | [Automated Tracking bug]: Prod ¦ OCP ¦ Simulation Failed with Exception Message |  |  | Simulators | Production | 3 - Medium | Active |  |  | 0 | 2026-03-28 |  | Bug | srinivasan.ks | vishnupriya.aluru | K.devaraj
4446855 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ OCP and MMP are getting skipped with "Capability, Specialty, Skill does NOT EXISTS in some of the profiles" error even though valid skills are already available. | Sanity | AMS Solution Configuration Agent | agentcrafters | Product Test | 3 - Medium | Ready to Deploy | Functional |  | 1 | 2026-03-28 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4446926 | Mar 28¦¦ Prod Sanity ¦¦OBM Pilot user testing_Cost table Value mismatch issue ¦¦ OBM and SVC tables | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | UI | Environment Issue | 0 | 2026-03-28 | 2026-04-01 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446931 | Mar 28¦¦ Prod Sanity ¦¦OBM_New result set should not create if we update the benchmark details in edit span of search | 4223629 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Ready for Prod Deployment | Functional |  | 1 | 2026-03-28 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446932 | Mar 28 ¦¦ Prod Sanity ¦¦ OBM ¦ AMS service group is not displayed in Opportunity Metrics table | Sanity | Gen AI | QDI - Opportunity Metrics | Production | 3 - Medium | Ready to Test | Functional |  | 0 | 2026-03-28 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446938 | Mar 28 ¦¦ Prod Sanity ¦¦ OBM ¦ Copy buttons appear in between Gen AI Insights of service groups | Sanity | Gen AI | QDI - Opportunity Metrics | Production | 3 - Medium | Closed | Functional |  | 0 | 2026-03-28 | 2026-04-01 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446942 | Mar 28¦¦ Prod Sanity ¦¦OBM Pilot user testing_KDA Table Value mismatch issue¦¦LCR and C2S ¦¦ SVC | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Ready to Test | UI | Insufficient application knowledge / Invalid data | 1 | 2026-03-28 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446943 | Mar 28 ¦¦ Prod Sanity ¦¦ SVC ¦¦ Default pricing route should be MMP DCTA for single-tower deals | Sanity | Gen AI | QDI - Opportunity Metrics | Production | 3 - Medium | Ready to Test | Functional | Code Issue | 0 | 2026-03-28 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446945 | Mar 28¦¦ Prod Sanity ¦¦ AI--Foundry ¦¦ Agent is not displaying info message if staffing is imported with rate card applied to records even though Pricing input is not hourly rate | 4318876 | AMS Solution Configuration Agent | agentcrafters | User Acceptance Test | 2 - High | Re-open | Functional |  | 0 | 2026-03-28 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4446956 | Mar 28¦¦ Prod Sanity ¦¦ AI--Foundry ¦¦ Agent is calling "Save Pricing Configuration" step twice | 4390112 | AMS Refactoring Scope | agentcrafters | User Acceptance Test | 3 - Medium | Ready to Deploy | Functional |  | 0 | 2026-03-28 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4446959 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ Multiple functional issues in Rate card import functionality | Sanity | AMS Solution Configuration Agent | agentcrafters | Product Test | 2 - High | Ready to Deploy | Functional |  | 0 | 2026-03-28 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4446967 | Mar 28 ¦ Prod Sanity ¦ DCSO ¦ Extension deal Generate DCSO is Enabled for All SG. | Sanity | DCSO | Pirates | User Acceptance Test | 3 - Medium | Closed | Functional | Inadequacy of available test data / Incorrect Data | 0 | 2026-03-28 | 2026-04-02 | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4446968 | Mar 28 ¦ Prod Sanity ¦ OBM ¦ Opportunity Metrics - Data Mismatch Issue | Prod Sanity | OBM | QDI - Opportunity Metrics | Product Test | 3 - Medium | Ready to Test | Functional | Insufficient application knowledge / Invalid data | 1 | 2026-03-28 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4446969 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ Not getting version hyperlink even after successful version creation | Prod Sanity | AMS Solution Configuration Agent | agentcrafters | User Acceptance Test | 2 - High | Resolved in Production | Functional | Not reproduceable / Invalid data | 1 | 2026-03-28 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4446972 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ Import PMO is displaying System error message. | Sanity | AMS Solution Configuration Agent | agentcrafters | Product Test | 2 - High | Ready to Deploy | Functional |  | 0 | 2026-03-28 |  | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4447047 | March 28th ¦¦ Prod Sanity ¦¦ DSP ¦ Scope ¦ Detailed scope ¦ "Hyper care" field is not highlighting even It was selected in WRWS service offerings | 4373652 | DSP | TechWarriors | User Acceptance Test | 3 - Medium | Active | Functional | Existing Prod Issue | 0 | 2026-03-28 |  | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4447072 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ Imported Pricing input details are not reflecting on Groupwide pricing input screen | Sanity | AMS Solution Configuration Agent | agentcrafters | Product Test | 2 - High | Closed | Functional | Design Issue | 0 | 2026-03-29 | 2026-03-30 | Bug | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan
4448011 | April 18th ¦ AMS ¦ Prod ¦ Regression ¦ MMP throwing system error | Regression | AMS | TechCoders | Regression Test | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-03-30 | 2026-04-02 | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4449492 | Mar 28¦¦ Prod¦¦ Under IT Spend Predictor Report dropdowns field is not displaying any Data | 4361786 | DATA Refresh | CodeCrafters | Production | 2 - High | Closed | Functional | Code Issue | 0 | 2026-03-30 | 2026-04-03 | Bug | madhuri.chintala | c.dhiman | sona.job
4451687 | April 18 ¦¦ PROD ¦¦ DSP ¦¦ List of version is not present in existing old dsp versions in Appendix | Sanity | DSP | NinjaWarriors | Product Test | 3 - Medium | New |  |  | 0 | 2026-03-31 |  | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4452033 | April 18 ¦¦ Prod ¦¦ Estimator/Calculator ¦¦ IMS Mobilization is displaying in gallery tab |  | gallery | Everest | Sanity Testing | 3 - Medium | New |  |  | 0 | 2026-03-31 |  | Bug | srinivasan.sivakumar | suresh.devarajan | nityanand.giri
4457525 | Apr 4th ¦ Regression ¦ UAT2 ¦ CDAT PMO¦ Define Team ¦ On click of Dashboard/Manage breadcrumb navigating to old screen. | Regression | CDAT | MYISP_Revamp_UI | Product Test | 2 - High | Ready for Prod Deployment | Functional | Code Issue | 0 | 2026-04-01 |  | Bug | srinivasan.ks | mahesh.kt | vikrant.r.mohite
4458123 | April 18 ¦ myISP ¦ PT ¦ Sanity ¦ SI ¦ Named Resource generation remains in Queued state | Sanity | SI | TechAvengers | Sanity Testing | 3 - Medium | Closed | Functional | Performance Issue | 0 | 2026-04-01 | 2026-04-01 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4458177 | 18th April¦ AMS/SI/BPMS ¦ PT/UAT ¦ Newly Created Opportunities are not flowing in PT/UAT from MMS | Sanity | SI | NGTransformers | Sanity Testing | 2 - High | Closed | Functional | Integration Issue | 0 | 2026-04-01 | 2026-04-03 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4458191 | April 18 ¦ myISP ¦ PT ¦ Sanity ¦ SI ¦ MMP FFP generation stuck in In Progress status | Sanity | SI | DevStormers | Sanity Testing | 2 - High | Closed | Functional | Integration Issue | 0 | 2026-04-01 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4458205 | 18th April ¦ SI ¦ PT ¦ OCP Simulation is stuck at first step | Sanity | SI | Insurgents | Sanity Testing | 1 - Critical | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-01 | 2026-04-01 | Bug | srinivasan.ks | vishnupriya.aluru | K.devaraj
4458211 | April 18 ¦ myISP ¦ PT ¦ Sanity ¦ SI ¦ Version creation through Cart fails with System Error for specific releases | Sanity | SI | DevStormers | Sanity Testing | 3 - Medium | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-01 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4458251 | 18 Apr ¦ myISP ¦ PT/UAT¦ SI_Staffing Baseline, Unable to import the Staffing OU, Getting error | Sanity | NextGen SI | TechAvengers | Sanity Testing | 2 - High | Closed | Functional | Code Issue | 0 | 2026-04-01 | 2026-04-03 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4458261 | 18th April ¦ SI ¦ Sanity ¦ PT ¦ PCW 8.6 ¦ Data refresh throws runtime error |  | PCW | Tech Ensemble | Sanity Testing | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-04-01 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4458308 | 18 Apr ¦ myISP ¦ PT¦ SI_Generate Pricing _Generate MMP FFP template is stuck in InProgress status for long time | Sanity | NextGen SI | TechAvengers | Sanity Testing | 2 - High | Closed | Functional | Duplicate Bug | 0 | 2026-04-01 | 2026-04-01 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4458510 | APR 18 ¦ OBM ¦ UAT ¦ LLM Insights not generated | Sanity | Gen AI | QDI - Opportunity Metrics | User Acceptance Test | 2 - High | Ready to Test | Functional |  | 0 | 2026-04-01 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4458778 | April 18_UAT_Gen AI_SVC KDA¦ LCR without Seat charges (without COLA) field is missing in SVC KDA table for AMS |  | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-04-01 | 2026-04-02 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4458799 | 18th April ¦ myISP ¦ PT ¦ Sanity ¦ In Central PMO role, by clicking Actions icon it is showing "Access Denied" | Sanity | PMO dashboard | TechWarriors | Sanity Testing | 3 - Medium | Closed | Functional | Environment Issue | 0 | 2026-04-01 | 2026-04-06 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4458801 | 18th April¦ Sanity ¦ PT ¦ CDAT PMO/Lead ¦ PMO Tracker Dashboard ¦ On click opportunity workflow getting access denied | Sanity | SI | TechWarriors | Sanity Testing | 2 - High | Closed | Functional | Environment Issue | 0 | 2026-04-01 | 2026-04-06 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4458816 | UAT2 env ¦¦OBM ¦¦ SVC _ KDA Table Value mismatch issue ¦¦ SI SG | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | Active | Data |  | 0 | 2026-04-01 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4458820 | UAT2 env ¦¦OBM ¦¦ Cost Table PMO column Value mismatch ¦¦ SI SG | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Data | Code Issue | 0 | 2026-04-01 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4458828 | UAT2 env ¦¦OBM ¦¦ AMS¦ SVC _ KDA Table Value mismatch issue | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Data |  | 0 | 2026-04-01 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4458980 | UAT2 env ¦¦Query¦ OBM ¦¦ SI/AMS/IMS¦ SVC _ KDA & Cost Table Missing fields | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | UI |  | 1 | 2026-04-01 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4458981 | April_18 ¦ AMS ¦ Showing Warning message post filling all Mandatory fields in Create interim | Sanity | Create Interim deal | GoRetro | Sanity Testing | 3 - Medium | Closed | Functional | Incorrect Environment Setup / Inadequate Documentation | 0 | 2026-04-01 | 2026-04-03 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4459230 | [Automated Tracking bug]: Prod ¦ OCP ¦ Simulation Failed with Validation Message |  |  | CodingCrusaders | Production | 3 - Medium | Closed |  | Insufficient application knowledge / Invalid data | 0 | 2026-04-02 | 2026-04-02 | Bug | srinivasan.ks | vishnupriya.aluru | K.devaraj
4459240 | 18th Apr ¦ UAT ¦ SI ¦ MMP FFP template download is stuck and still showing as “in progress.” | Sanity testing | SI | DevStormers | Sanity Testing | 1 - Critical | Closed | Functional | Integration Issue | 0 | 2026-04-02 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4459244 | 18th Apr ¦ UAT ¦ SI DCTA ¦ View KDA is not getting enabled for MMP DCTA KDA | Sanity | SI DCTA | Insurgents | Sanity Testing | 1 - Critical | Closed | Functional | Integration Issue | 0 | 2026-04-02 | 2026-04-02 | Bug | srinivasan.ks | vishnupriya.aluru | K.devaraj
4459438 | 18 Apr ¦ myISP ¦ UAT¦ SI_Rate Card Screen ,On click of Rate Card Export OU , Status is Queued | Sanity | NextGen SI | TechWizards | Product Test | 2 - High | Closed | Functional | Integration Issue | 0 | 2026-04-02 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4459443 | 18th April ¦ SI ¦ Sanity ¦ UAT ¦ PCW 8.7 ¦ SDL download throws runtime error |  | PCW | Tech Ensemble | Sanity Testing | 2 - High | Closed | Functional | Incorrect Environment Setup / Inadequate Documentation | 0 | 2026-04-02 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4459446 | 18th April ¦ myISP ¦ UAT1 ¦ Sanity ¦ In Central PMO role, after clicking Manage it is not showing any Opportunities count | Sanity | PMO dashboard | GoRetro | Sanity Testing | 3 - Medium | Closed | Functional | Environment Issue | 0 | 2026-04-02 | 2026-04-03 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4459455 | 18th April¦ Sanity ¦ PT ¦ CDAT SME/CM SME ¦ CDAT SME Driven ¦ On click of CDAT SME Driven role is getting changed and all screens are not getting displayed inside CDAT | Sanity | CDAT | TechWarriors | Sanity Testing | 2 - High | Closed | Functional | Environment Issue | 0 | 2026-04-02 | 2026-04-06 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4459456 | 18th April ¦ SI ¦ Sanity ¦ UAT ¦ PCW 8.7 ¦ MMP export throws 500 error |  | PCW | Tech Ensemble | Sanity Testing | 2 - High | Closed | Functional | Code Issue | 1 | 2026-04-02 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4459508 | 18 Apr ¦ myISP ¦ UAT ¦ SI_Generate Pricing _Generate MMP FFP template is stuck in InProgress status for long time | Sanity | NextGen SI | DevStormers | Product Test | 2 - High | Closed | Functional | Duplicate Bug | 0 | 2026-04-02 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4459537 | 18th April ¦ myISP ¦ UAT ¦ Sanity ¦ Export is getting queued | Sanity | review approval | CodeCrafters | Sanity Testing | 3 - Medium | Closed | Functional |  | 0 | 2026-04-02 | 2026-04-07 | Bug | madhuri.chintala | c.dhiman | sona.job
4459704 | 18th April ¦ AMS ¦ Sanity ¦ UAT ¦ OCP simulation failing with validation error in newly created deal | Sanity | AMS Sanity | CodingCrusaders | Sanity Testing | 2 - High | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-02 | 2026-04-06 | Bug | srinivasan.ks | vishnupriya.aluru | K.devaraj
4459804 | 18th April¦ Sanity ¦ PT ¦ SA ¦ CDAT SME Driven ¦ On click of CDAT SME Driven role is getting changed | Sanity | CDAT | TechWarriors | Sanity Testing | 2 - High | Closed | Functional | Duplicate Bug | 0 | 2026-04-02 | 2026-04-03 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4459929 | 18th April_UAT2_OBM_Few field values are not matching between OBM and KDA in IMS | Sanity | Gen AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-04-02 | 2026-04-07 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4459953 | 18th April¦ Sanity ¦ UAT¦ CDAT¦ Gap ID is missing for few gaps in assessment outcome screen | Sanity | CDAT | TechTribe | Sanity Testing | 3 - Medium | Closed | Functional | Environment Issue | 0 | 2026-04-02 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4459971 | 18th April¦ Sanity ¦ UAT¦ CDAT¦ CDAT tracking status is not getting saved in Assessment details page | Sanity | CDAT | TechTribe | Sanity Testing | 3 - Medium | Ready to Test | Functional | Environment Issue | 0 | 2026-04-02 |  | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4460514 | April 18 ¦ PT ¦ SI ¦ DSCO¦ Blank page displayed on clicking Digital DCSO in Digital Documentation |  | PCW | TechStars | User Acceptance Test | 2 - High | New | Functional |  | 0 | 2026-04-02 |  | Bug | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj
4460517 | 18 Apr_UAT_SI_Staffing Baseline_ Unable to search the technologies in the search box of the dropdown | Sanity | NextGen SI | TechAvengers | Product Test | 3 - Medium | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-02 | 2026-04-03 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460519 | 18th Apr ¦ UAT ¦ SI DCTA ¦Fixed Billing is configured in release wise pricing input but in griddy its taking as Target Margin | Sanity | SI DCTA | DevStormers | Product Test | 3 - Medium | Ready to Test | Functional | Code Issue | 0 | 2026-04-02 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460521 | April 18 ¦ SI ¦ Sanity ¦ PT ¦ PCW 8.6 ¦ Role Type column not renamed to Role Category in 8.6 template |  | PCW | Tech Ensemble | Sanity Testing | 3 - Medium | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-02 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460523 | 18th Apr ¦ UAT ¦ SI DCTA ¦ RP is throwing system error (Scenario Specific) | 4373911 | STD Role | TechWizards | Product Test | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-04-02 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460539 | 18 Apr_UAT_SI_Staffing Baseline_ In the Exported Staffing OU file , MOM values are showing from year 2 , not from year 1 | 4373911 | NextGen SI | TechAvengers | Product Test | 4 - Low | Closed | Functional | Code Issue | 0 | 2026-04-02 | 2026-04-03 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460549 | 18 Apr_UAT_SI_Staffing Baseline_ Export of Staffing OU is not working as expected | 4373911 | NextGen SI | TechAvengers | Product Test | 2 - High | Closed | Functional | Code Issue | 0 | 2026-04-02 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460550 | Apr 18 ¦¦ UAT¦¦ SI ¦ PCW 8.7 Template¦¦ Staffing Baseline ¦¦ When we entered manually values in profile city tier column we are not getting the error except for cty A Rate type | 4373911 | myISP | Tech Ensemble | Product Test | 2 - High | Closed | Functional | Design Issue | 0 | 2026-04-02 | 2026-04-02 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460651 | 18 Apr_UAT_SI_Profiles Screen, Getting Duplicate Profile entry Error on click of Save | Sanity | NextGen SI | TechWizards | Product Test | 4 - Low | Closed | Functional | Performance Issue | 0 | 2026-04-02 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4460680 | 18th April ¦ SI ¦ PT ¦ Report & compliance screen is not loading | 4389877 | SI | CodeCrafters | Product Test | 1 - Critical | Closed | Functional | Incorrect Environment Setup / Inadequate Documentation | 0 | 2026-04-02 | 2026-04-03 | Bug | madhuri.chintala | c.dhiman | sona.job
4460790 | April18th¦Sanity¦PT¦BPMS¦Review approval tile is not loading for both screen Reporting & compliance, Solution review & approval | Sanity | Opportunity workflow | mySPIntegratedSolutionPlatform | Product Test | 2 - High | New | Functional |  | 0 | 2026-04-02 |  | Bug
4461219 | 18th Apr¦ UAT ¦ SI ¦ MMP FFP template is not getting completed and stuck at InProgress status | 4389877 | MMP FFP | DevStormers | Product Test | 1 - Critical | Closed | Functional | Integration Issue | 1 | 2026-04-03 | 2026-04-03 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4461238 | 18th April ¦ PT ¦ Sanity ¦ Manage is not clickable and roles are not displaying | Sanity | Sanity | NGTransformers | Sanity Testing | 1 - Critical | Closed | Functional | Environment Issue | 0 | 2026-04-03 | 2026-04-03 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4461350 | Apr 18 ¦ UAT ¦ Current Deal is not Shown for IMS Security | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 1 - Critical | Closed | Functional |  | 0 | 2026-04-03 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461372 | April 18 ¦ UAT Sanity ¦ PLD ¦ DFD requests are not flowing to PLD | Sanity | DFD-Sanity | Pacemakers | Sanity Testing | 1 - Critical | Closed | Functional | Environment Issue | 1 | 2026-04-03 | 2026-04-07 | Bug | madhuri.chintala | c.dhiman | sona.job
4461378 | 18th April ¦ UAT ¦ Angular Upgrade ¦ Unable to add skill inventory using the Apply skill inventory icon. | 4429397 | AMS | MYISP_Revamp_UI | Product Test | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-04-03 | 2026-04-06 | Bug | srinivasan.ks | mahesh.kt | vikrant.r.mohite
4461409 | Prod sanity ¦¦ SnC ¦¦ SnC calculators and Asset calculator are not displaying in Gallery | Sanity | SnC calculator | TechWarriors | Sanity Testing | 1 - Critical | Ready for Prod Deployment | Functionl | Performance Issue | 1 | 2026-04-03 |  | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4461424 | 18th April¦ UAT ¦ SI DCTA ¦ Custom rate card data is not flowing in MMP griddy | Regression | SI | TechSprinters | User Acceptance Test | 3 - Medium | BA clarification | Functional |  | 0 | 2026-04-03 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4461534 | April 18th ¦¦DFD¦¦PT Sanity ¦¦ The DFD Screen is not loading | Sanity | DFD | BackDoorGuardians | Product Test | 1 - Critical | Closed | Functional | Environment Issue | 0 | 2026-04-03 | 2026-04-03 | Bug | madhuri.chintala | c.dhiman | sona.job
4461622 | UAT2_OBM_Opp metrics table_ columns showing expand icon but not having sub-columns | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | BA clarification | UI |  | 1 | 2026-04-03 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461623 | UAT2_OBM_ Current deal should not in Opp benchmark pop up | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | Functional | Insufficient application knowledge / Invalid data | 0 | 2026-04-03 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461625 | UAT2_OBM_ space issue between benchmark opp pop up and glance data | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 4 - Low | Closed | UI | UX Design / UI Issue | 0 | 2026-04-03 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461710 | Apr 18 ¦ UAT ¦ OBM ¦ SVC ¦ IMS Security Data Mismatch | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 3 - Medium | Active | Functional | Code Issue | 2 | 2026-04-03 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461719 | April 18th ¦¦PLD¦¦PT Sanity ¦¦ The Request is not flowing to PLD | Sanity | PLD | Pacemakers | Product Test | 1 - Critical | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-03 | 2026-04-06 | Bug | madhuri.chintala | c.dhiman | sona.job
4461737 | UAT2_OBM_ Opp metrics _ All fields issue _ Missing fileds in UI/Sequence issue/fields placed in wrong place in OBM UI_ AMS SG | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | UI | Design Issue | 0 | 2026-04-03 | 2026-04-03 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461741 | Apr 18 ¦ UAT ¦ OBM ¦ IMS Security SVC - KDA Multiple versions are showing in compare Versions | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 1 - Critical | Closed |  | Code Issue | 0 | 2026-04-03 | 2026-04-04 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461752 | UAT2_OBM_ Deal details are missing in Opp benchmark deals pop up due to which it's not showing in OBM Table_ all 3 SGs | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Closed | UI | Inadequacy of available test data / Incorrect Data | 0 | 2026-04-03 | 2026-04-06 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4461753 | 18th April¦ Sanity ¦ PT ¦ CDAT SME¦ CDAT SME Driven¦ Assessment Outcome ¦ Invalid extra options displayed in edit gap comments popup | Sanity | CDAT | MYISP_Revamp_UI | Sanity Testing | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-04-03 | 2026-04-07 | Bug | srinivasan.ks | mahesh.kt | vikrant.r.mohite
4461770 | 18th Apr¦ UAT ¦ SI ¦When the Technology role is selected, the corresponding Standard Role is highlighted in red in staffing OU | 4373911 | STD | TechWizards | Product Test | 3 - Medium | Ready to Deploy | Functional |  | 0 | 2026-04-03 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4461774 | 18 Apr ¦ myISP ¦ UAT¦ SI Staffing Baseline ¦¦ Under Technology Consulting - Creative Agency Services coming it should be come as SAP from dropdown | 4373911 | Staffing Baseline | TechAvengers | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-04-03 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462015 | UAT2_OBM_ Benchmark / In-progress deal validation _ Cost & KDA Mismatch _ AMS SG | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Active | UI | Code Issue | 0 | 2026-04-03 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4462077 | 18th Apr¦PT/ UAT ¦ SI ¦ MMP FFP template is not getting completed and stuck at InProgress status | 4389877 | MMP FFP | DevStormers | Product Test | 1 - Critical | Closed | Functional | Code Issue | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462080 | 18th April ¦ PT ¦ BPMS Sanity ¦ Inspire is not loading | Sanity | BPMS | myISP_BPMS | Sanity Testing | 1 - Critical | Closed | Functional | Environment Issue | 0 | 2026-04-06 | 2026-04-07 | Bug | Rajsingh.rajput | biju.balakrishnan | m.ohlan
4462093 | 18th April ¦ UAT ¦ SI ¦ Technology tier is populating as N/A in staffing OU for IMS and BPMS SG | 4373911 | STD Role | TechWizards | Product Test | 4 - Low | Closed | Functional | Inadequacy of available test data / Incorrect Data | 0 | 2026-04-06 | 2026-04-07 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462130 | April 18 ¦ PT ¦ SI ¦ Overwrite column allows free text copy‑paste and does not revert to dropdown values during MMP export |  | PCW | Tech Ensemble | User Acceptance Test | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462179 | 18 Apr_UAT_SI_Staffing Baseline_ In the Exported Staffing OU file(with Macros) ,Technology Tier column is not viewable properly | 4373911 | NextGen SI | TechAvengers | Product Test | 3 - Medium | Ready to Test | Functional | Code Issue | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462183 | April 18 ¦ PT ¦ SI ¦ Offline MMP FFP Export validation for Role Type not working – Role Type becomes blank in PCW and exported MMP for non-applicable SSGs |  | PCW | Tech Ensemble | Product Test | 2 - High | Closed | Functional |  | 0 | 2026-04-06 | 2026-04-07 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462256 | 18 Apr_UAT_SI_Staffing Baseline_ Import is not working as Expected | 4373911 | NextGen SI | TechAvengers | Product Test | 3 - Medium | Closed | Functional | Insufficient application knowledge / Invalid data | 0 | 2026-04-06 | 2026-04-07 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462276 | 18 Apr ¦ myISP ¦ UAT¦ SI Staffing Baseline ¦¦ Technology Role dropdown list is not populated for when Technology was non-SAP → later changed non-SI/CON-CAS SG | 4373911 | Staffing Baseline | TechAvengers | Product Test | 3 - Medium | Closed | Functioanl |  | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462284 | [Query]18th Apr¦ UAT ¦ SI ¦When Role type is changed to select the screen is getting saved and it is taking the existing role type is this expected? | 4373911 | STD Role | TechWizards | Product Test | 4 - Low | Awaiting UAT deployment | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462287 | 18 Apr ¦ myISP ¦ UAT¦ SI Staffing Baseline ¦¦ Technology Role and Standard Role values are cleared instantly. | 4373911 | Staffing Baseline | TechAvengers | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462288 | 18th April ¦ UAT ¦ SI ¦ Technology role is not populating for Technology IX/SAP for SI SG | 4373911 | STD Role | TechWizards | Product Test | 3 - Medium | Closed | Functional | Insufficient application knowledge / Invalid data | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462289 | 18 Apr_UAT_SI_Staffing Baseline_UI_ I icon is not viewable for the Technology Tier , Technology role , Standard role and Role type column | 4373911 | NextGen SI | TechWizards | Product Test | 2 - High | Awaiting UAT deployment | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462296 | 18 Apr_UAT_SI_Staffing Baseline_Staffing OU _ Note is not viewable for the Technology tier, Standard role ,Technology role and Role type header | 4373911 | NextGen SI | TechAvengers | Product Test | 2 - High | Closed | Functional | Design Issue | 0 | 2026-04-06 | 2026-04-07 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462311 | 18 Apr ¦ myISP ¦ UAT¦ SI Staffing Baseline ¦¦ Technology Role & Standard Role wherever not applicable should be disabled and not be shown with Select picklist | 4373911 | Staffing Baseline | TechAvengers | Product Test | 4 - Low | Awaiting UAT deployment | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462312 | 18 Apr_UAT_SI_Staffing Baseline_Staffing OU _ Note is not added properly as per the US for Standard role Column | 4373911 | NextGen SI | TechWizards | Product Test | 3 - Medium | Closed | Functional | Duplicate Bug | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462318 | 18 Apr_UAT_SI_Staffing Baseline_ I icon is not viewable for the Technology Role column | 4373911 | Staffing Baseline | TechAvengers | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462325 | April 18th ¦¦ Prod ¦¦ DSP Summary _ Review & Approvals Screen _ Signoff Status & Stage 2B/3B is not present in PPT/PDF | Prod Bug | DSP | Pirates | Product Test | 3 - Medium | New | Functional |  | 0 | 2026-04-06 |  | Bug | srinivasan.ks | murugan.ssubramanian | pandidurai.ks
4462326 | 18 Apr_UAT_SI_Staffing Baseline_Staffing OU _ Standard Role column is not Auto populating when Technology role is selected | 4373911 | NextGen SI | TechWizards | Product Test | 2 - High | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462431 | 18th April ¦ UAT ¦ Super User ¦ Dashboard breadcrumb redirecting to PMO Manage | Regression | myISP | TechWarriors | User Acceptance Test | 3 - Medium | Ready to Deploy | Functional | Existing Prod Issue | 0 | 2026-04-06 |  | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4462433 | APRIL UAT ¦ SI KDA REPORTS ISSUE 1 | 4386341 | SI KDA REPORTS ISSUE | myISP_IMS | User Acceptance Test | 3 - Medium | Active |  |  | 0 | 2026-04-06 |  | Bug | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra
4462436 | Gen AI ¦¦ OBM ¦¦ Align UX with Figma Prototype | 4373741 | Gen AI | QDI - Opportunity Metrics | User Acceptance Test | 3 - Medium | Active | Funcational |  | 0 | 2026-04-06 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4462476 | 18th April ¦ UAT ¦ SI ¦ When SG/SSG is Updated in profile screen the Role type is not getting mapped according to updated SG in staffing baseline | 4373911 | STD Role | TechWizards | Product Test | 3 - Medium | Ready to Deploy | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462488 | 18 Apr_UAT_SI_Staffing Baseline_Staffing OU _Technology role column is not highlighted in Red , post removing it | 4373911 | NextGen SI | TechWizards | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462506 | APRIL UAT ¦ MMP Resource Template issue 1 | 4386341 | SI KDA REPORTS ISSUE | myISP_IMS | User Acceptance Test | 3 - Medium | Ready to Test |  |  | 0 | 2026-04-06 |  | Bug | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra
4462511 | April 18th ¦¦PLD¦¦PT Sanity ¦¦ The data is not loading in Assigned Tab and Unassigned Tab in PLD | Sanity | PLD | DevNinjas | Product Test | 2 - High | Closed | Functional | Code Issue | 0 | 2026-04-06 | 2026-04-07 | Bug | madhuri.chintala | c.dhiman | sona.job
4462512 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role should initially have dropdown values before Technology Role is selected (SAP,Salesforce and Custom Development Solutions under SI) | 4373911 | SI-PCW | Tech Ensemble | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462520 | 18 Apr_UAT_PCW_ For a Checked in version , Standard role is not populating in Staffing UI | 4373911 | NextGen SI | TechAvatar | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462534 | 18 Apr_UAT_PCW 8.7 Template_Unable to generate SDL , getting Indicative LCR field empty error | 4373911 | NextGen SI | TechAvatar | Product Test | 3 - Medium | Closed | Functional |  | 0 | 2026-04-06 | 2026-04-06 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462540 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role is not coming back after refresh for SI SG | 4373911 | SI-PCW | TechAvatar | Product Test | 2 - High | Active | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462585 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Forecast data is not coming back | Sanity | SI - PCW | Tech Ensemble | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462587 | 18th April ¦ PT ¦ BPMS Sanity ¦ Getting error message in SEP screen | Sanity | BPMS | myISP_BPMS | Sanity Testing | 1 - Critical | Closed | Functional | Code Issue | 0 | 2026-04-06 | 2026-04-07 | Bug | Rajsingh.rajput | biju.balakrishnan | m.ohlan
4462588 | 18th Apr ¦ UAT ¦ SI ¦ Few fields are not getting populated in UI and Staffing OU Reports in copied version | 4373911 | STD role | TechWizards | Product Test | 3 - Medium | Closed | Functional | Code Issue | 0 | 2026-04-06 | 2026-04-07 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462634 | UAT2_OBM_ Activae tab is not clearly visible issues | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Resolved | UI | Duplicate Bug | 0 | 2026-04-06 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4462642 | Apr 18 ¦ UAT ¦ OBM ¦ IMS - CORE ¦ Missing Values in OBM | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 3 - Medium | Re-open | Functional |  | 0 | 2026-04-06 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4462656 | April 18th¦ OBM¦ Clicking on expand option in a metric table, token error displayed | Sanity | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | Ready to Test |  | Code Issue | 0 | 2026-04-06 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4462668 | 18th Apr ¦ UAT ¦ SI ¦ Few Accenture Role/Type is getting highlighted in Red in MMP FFP Template | 4389877 | MMP FFP | BA Support | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-06 |  | Bug | arul.vasu | arul.vasu | varsha.b.rani
4462685 | UAT2_OBM_ Recommendations for your solution issue | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | New | UI |  | 0 | 2026-04-06 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4462709 | 18th Apr¦ UAT ¦ SI ¦ For few countries Role type is not getting populated in MMP FFP Template | 4389877 | MMP FFP | DevStormers | Product Test | 3 - Medium | Ready to Test | Functional | Environment Issue | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4462715 | APRIL UAT ¦ MMP Resource Template issue 2 | 4386341 | SI KDA REPORTS ISSUE | myISP_IMS | User Acceptance Test | 3 - Medium | Active |  |  | 0 | 2026-04-06 |  | Bug | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra
4463613 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role is not retained when Technology is changed from SAP to non-SAP (SI SG) | 4373911 | SI-PCW | Tech Ensemble | Product Test | 4 - Low | New | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4463621 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Standard Role is not retained when SG is changed from SI to non-SI (SAP tech) | 4373911 | SI-PCW | Tech Ensemble | Product Test | 4 - Low | New | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4463627 | 18th Apr ¦ PT & UAT ¦ PCW 8.7 ¦ Wrong validation message when Technology Role is not selected for applicable SI profiles | 4373911 | SI-PCW | Tech Ensemble | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-06 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4464301 | 18th Apr ¦ PT/UAT¦ SI ¦when triggers are in progress all buttons in the Generate Pricing screen are enabled | Sanity | SI | TechSprinters | Product Test | 2 - High | Ready to Deploy | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4464339 | Apr 18 ¦ UAT ¦ OBM ¦ Submit Button is Disabled | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 4 - Low | Closed | Functional | UX Design / UI Issue | 0 | 2026-04-07 | 2026-04-07 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4464358 | 18th April¦ PCW ¦ The 8.7 template should have first in order of dropdown | Regression | Offline | TechAvengers | User Acceptance Test | 4 - Low | Closed | Functional | Not reproduceable / Invalid data | 0 | 2026-04-07 | 2026-04-07 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4464367 | Apr 18 ¦ UAT ¦ OBM ¦ SVC ¦ Issue in Cost and Metrics at Glance | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 4 - Low | Closed | Functional | Code Issue | 0 | 2026-04-07 | 2026-04-07 | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4464374 | 18th April ¦ UAT ¦ SI DCTA ¦ Price is displaying as 0 in DCTA KDA | Regression | SI | Simulators | User Acceptance Test | 3 - Medium | Closed | Functional | Integration Issue | 0 | 2026-04-07 | 2026-04-07 | Bug | srinivasan.ks | vishnupriya.aluru | K.devaraj
4464439 | 18th April¦ UAT ¦ SI ¦ For "CON-CAS" Client Ratecard is not flowing in myISP Ratecard UI | Regression | SI | TechSprinters | User Acceptance Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4464475 | Apr 18 ¦ UAT ¦ OBM ¦ SVC ¦ Cost and Metrics at Glance - Response Issue | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 1 - Critical | New | Functional |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4464910 | OBM ¦PROD validation ¦ AMS insights showing 'No data' when PBI shows data | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 2 - High | For Rejection | Data |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4464985 | OBM ¦PROD validation ¦ PBI column width is not uniform | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | BA clarification | Data |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4465797 | 18th April ¦ UAT ¦ SI ¦ Getting duplicate profiles in target version while doing carting | Regression | SI | TechAvengers | User Acceptance Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4465804 | 18th April_UAT2_OBM_When there is no data for Onshore LCR including seat charge (without COLA), then that field is not present under LCR field | Sanity | GEN AI | QDI - Opportunity Metrics | Product Test | 1 - Critical | Ready to Test | Functional |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4465929 | OBM ¦PROD validation ¦ Benchmark opp selected vs what is displayed in PBI is different | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 1 - Critical | Ready to Test | Data |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4465936 | 18th Apr ¦UAT ¦ SI ¦ The Role type is populating for other SSG which is not mentioned in the Role type sheet | 4373911 | STD Role | TechAvengers | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4465941 | 18th April ¦ UAT ¦ SI SDL ¦ Profile city tire and Role type column values are not flowing in SDL | Regression | SDL | TechAvengers | User Acceptance Test | 3 - Medium | Ready to Test | Functional | Code Issue | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4465961 | 18 Apr ¦ myISP ¦ UAT¦ SI Staffing Baseline ¦¦ From OU Validations & Error messages is not showing in UI | 4373911 | myISP | TechAvengers | Product Test | 2 - High | Ready to Deploy | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4466165 | 18th April¦ PCW ¦ 8.7 ¦ Client Workbook ¦ While creating Client workbook from ACN workbook DNP forecast sheet is coming instead of OC Forecast. | Regression | Offline | Tech Ensemble | User Acceptance Test | 4 - Low | Ready to Test | Functional | Code Issue | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4466176 | [Query]18th Apr¦ UAT ¦ SI DCTA¦ Newly Added Parameters Profile City Tier, Role type, Standard Role are the same field names we can able to see in JSON or any other name we should follow | 4373911 | SI DCTA | TechSprinters | Product Test | 3 - Medium | Closed | Functional | Requirement Clarity Issue | 0 | 2026-04-07 | 2026-04-07 | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4466177 | APRIL UAT ¦ SI KDA REPORTS ISSUE 2 | 4386341 | SI KDA REPORTS ISSUE | myISP_IMS | User Acceptance Test | 3 - Medium | New |  |  | 0 | 2026-04-07 |  | Bug | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra
4466178 | 18 Apr_UAT_SI_Staffing Baseline_Staffing OU _Facing performance issue in Staffing Import | 4373911 | NextGen SI | TechWizards | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4466202 | APRIL UAT ¦ LCM INFRA & COTS REPLATFROM UI | 4386341 | LCM COTS REPLATFROM UI | myISP_IMS | User Acceptance Test | 3 - Medium | New |  |  | 0 | 2026-04-07 |  | Bug | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra
4466282 | 18th April¦ UAT ¦ SI ¦ In Technology Role dropdown few roles are missing for SAP, Salesforce, Custom Development solutions Technology | 4373911 | STD Role | TechSprinters | User Acceptance Test | 3 - Medium | BA clarification | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4466851 | UAT2_OBM_ Benchmark deal validation _ SVC/ OBM - Cost table _ IMS Core + Security Deal _ Value mismatch issue | 4373741 | GEN AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Ready to Test | UI |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4466857 | 18th April¦ UAT ¦ SI ¦ For applicable SG and Technology "Technology Role" is not highlighting in Amber and without configuring "Technology Role" Screen is getting saved in Staffing Baseline | 4373911 | STD Role | TechAvengers | User Acceptance Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4467455 | 18th Apr¦ PT ¦ Apr PT Env is not loading showing Bad gateway | Sanity | Sanity | NGTransformers | Sanity Testing | 1 - Critical | Closed | Functional | Environment Issue | 0 | 2026-04-07 | 2026-04-07 | Bug | madhuri.chintala | sankaran.viswanathan | sowjanya.kari
4467462 | APRIL UAT ¦ SI KDA REPORTS Variance Logic | 4386341 | SI KDA REPORTS ISSUE | myISP_IMS | User Acceptance Test | 3 - Medium | New |  |  | 0 | 2026-04-07 |  | Bug | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra
4467554 | 18th Apr ¦UAT ¦ SI ¦Role type values are not populating as per staffing baseline Screen in MMP FFP Template | 4389877 | MMP FFP | BA Support | Product Test | 2 - High | BA clarification | Functional | Duplicate Bug | 0 | 2026-04-07 |  | Bug | arul.vasu | arul.vasu | varsha.b.rani
4467583 | Apr 18 ¦ UAT 2¦ OBM ¦ IMS _Opportunity is getting blank in OBM metrices table | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 1 - Critical | New | Functional |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4467585 | Apr 18 ¦¦ PLD ¦¦ PT Sanity ¦¦ Save button is not working in Edit SA Assignment Popup | Sanity | PLD | Pacemakers | Product Test | 3 - Medium | Active | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | c.dhiman | sona.job
4467592 | Apr 18 ¦ UAT 2¦ OBM ¦ 0’ value is impacting the average Onshore LCR | Sanity | OBM | QDI - Opportunity Metrics | Product Test | 1 - Critical | New | Functional |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4467768 | 18th April_UAT2_OBM_BPMS is displaying instead of IMS Security in Overview of RAG Parameter Graph | Sanity | Gen AI | QDI - Opportunity Metrics | Product Test | 3 - Medium | Ready to Test | Functional |  | 0 | 2026-04-07 |  | Bug | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar
4467787 | 18th April ¦ PT & UAT ¦ SI SDL ¦ PCW 8.7 ¦ Role type column values are not flowing in UI, so in SDL for a PCW version | 4373911 | SDL | TechAvengers | Product Test | 2 - High | New | Functional |  | 0 | 2026-04-07 |  | Bug | madhuri.chintala | jayanth.kumar | mervinkumar.manickam
4436840 | 28th March ¦ UAT ¦ Available hrs ¦ Monthly values are not displayed in yellow even after changing the Default value to 'No' for PMO section in the export excel. | 4367340 | AMS | TechCoders | Product Test | 4 - Low | Active | Functional |  | 0 | 2026-03-19 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4437674 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hours ¦ Annual Hours values are editable in Available Hrs export in case of default value is Yes but still columns are highlighting in grey. | 4367340 | AMS | TechCoders | User Acceptance Test | 3 - Medium | Re-open | Functional |  | 1 | 2026-03-20 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4437685 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hours ¦ Annual hours are still editable even though Default value is marked as "No" in export for Subk Profiles. | 4367340 | AMS | TechCoders | User Acceptance Test | 2 - High | Re-open | Functional |  | 1 | 2026-03-20 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4438003 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hrs Export ¦ Not getting any validations for PMO Annual hrs >3000 and more than 4 decimals months value | 4367340 | AMS | TechCoders | User Acceptance Test | 2 - High | For Rejection | Functional |  | 0 | 2026-03-20 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4438166 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hours ¦ Avl hours export shows completed state only after navigating to other tab and navigating back to Export/Import tab | 4367340 | AMS | TechCoders | User Acceptance Test | 2 - High | Resolved | Functional |  | 0 | 2026-03-20 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4438171 | 28th Mar ¦ UAT2 ¦ AMS-Avl Hours ¦ After editing few months in Annual Hours total is getting updated, but in exported report non edited months is getting updated as zero. | 4367340 | AMS | TechCoders | Product Test | 2 - High | For Rejection | Functional |  | 0 | 2026-03-20 |  | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4459725 | 18th April ¦ AMS ¦ Sanity ¦ UAT ¦ RP simulation failing with validation error in newly created deal | Sanity | AMS Sanity | TechCoders | Sanity Testing | 2 - High | Closed | Functional | Integration Issue | 0 | 2026-04-02 | 2026-04-03 | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak
4461681 | 18th April ¦ UAT ¦ Angular Upgrade ¦ ADL is getting queued. | 4429397 | AMS | TechCoders | Product Test | 2 - High | Closed | Fuctional | Integration Issue | 0 | 2026-04-03 | 2026-04-07 | Bug | srinivasan.ks | vishnupriya.aluru | Francis.Deepak