## Milestone
User story Freeze Date | Cut off for PT hand over | Cut off for UAT hand over | UAT Completion | Functional Bug closure | Code Freeze | Initial GNG decision | Final Go/No Go Decision | Final Go-Live
2026-03-23 | 2026-04-07 | 2026-04-10 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-14 | 2026-04-16 | 2026-04-18

## PT status
Module (TextVerification) | Parent Title | Feature ID | PT Lead | Title | ID | Primary Tester | Secondary Tester | Test Planning | BA Review | TFS upload | PT Status | Manual Test cases generated from GHC | Useful Test cases from GHC | Tester Created test case count | Reviwed Final Test case count | Coverage for Manual Test cases from GHC% | Accuracy for Manual test cases from GHC% | TFS state | Passed | Failed | Blocked | Not Run | Total | Execution % | Pass % | Comments | Node Name | MPOC
Drop 3 - Angular upgrade v19 to v21 | Angular upgrade version 19 to version 21 - 18th April | 4429397 | Pirtheebaa | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4429413 | Mary/Janardhan |  | Completed | Completed | Completed | Completed | 48 | 10 | 14 | 24 | 40% | 40% |  | 20 | 0 | 0 | 0 | 20 | 100% | 100% |  | MYISP_Revamp_UI | vikrant.r.mohite
Drop 3 - Angular upgrade v19 to v21 | Angular upgrade version 19 to version 21 - 18th April | 4429397 | Leena | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4429519 | Harshitha |  | Completed | In Progress | Not Started | In Progress | 15 | 10 | 0 | 10 | 95% | 95% |  | 6 | 0 | 0 | 4 | 10 | 60% | 100% |  | MYISP_Revamp_UI | vikrant.r.mohite
Drop 3 - Angular upgrade v19 to v21 | Angular upgrade version 19 to version 21 - 18th April | 4429397 | Rajeswari | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4429521 | PavithraJabeen | Agnes | Completed | Completed | In Progress | In Progress | 40 | 40 | 0 | 40 | 100% | 100% |  | 28 | 0 | 0 | 12 | 40 | 70% | 100% |  | MYISP_Revamp_UI | vikrant.r.mohite
Drop 3 - Angular upgrade v19 to v21 | Angular upgrade version 19 to version 21 - 18th April | 4429397 | Jaya | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4429530 | Anu | Sriram | Completed | Completed | Not Started | In Progress | 26 | 17 | 17 | 17 | 90% | 90% |  | 13 | 0 | 0 | 4 | 17 | 76.47% | 100% |  | MYISP_Revamp_UI | vikrant.r.mohite
AMS | Available Hours OU Report | 4439196 | Jaya | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export/Import status tab in Available Hours screen | 4439199 | Anu | Ihsana | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 15 | 15 | 0% | 0%
AMS | Available Hours OU Report | 4439196 | Jaya | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for Staffing | 4439323 | Anu | Ihsana | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 17 | 17 | 0% | 0%
AMS | Available Hours OU Report | 4439196 | Jaya | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for PMO | 4439343 | Anu | Ihsana | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 7 | 7 | 0% | 0%
AMS | Available Hours OU Report | 4439196 | Jaya | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for Staffing | 4439357 | Anu | Ihsana | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 7 | 7 | 0% | 0%
AMS | Available Hours OU Report | 4439196 | Jaya | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for PMO | 4439362 | Anu | Ihsana | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 10 | 10 | 0% | 0%
DCSO | myISP - Digital DCSO | 4278081 | Shini | As a myisp Solution Architect, I want the DCSO tab to be removed from the SI KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | 4362582 | Jeba |  | Completed | Completed | Completed | Completed | [7 empty] | 3 | 0 | 0 | 0 | 3 | 100% | 100% |  | Insurgents | K.devaraj
DCSO | myISP - Digital DCSO | 4278081 | Shini | As a myisp Solution Architect, I want the DCSO tab to be removed from the AMS KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | 4362592 | Jeba |  | Completed | Completed | Completed | Completed | [7 empty] | 3 | 0 | 0 | 0 | 3 | 100% | 100% |  | Insurgents | K.devaraj
MMP FFP | MMP FFP Export update - April release | 4389877 | Kavi | As a myISP SA, I want to change the logic to populate "Role Type" and "Accenture Role/Rate" in MMP FFP so that it is aligned with Dynamic Target Pricing implementation | 4391224 | Manisa | Sathya | Completed | Completed | Completed | In Progress | 39 | 27 | 0 | 27 | 100% | 80% |  | 11 | 7 | 0 | 9 | 27 | 66.67% | 61.11% | Delivered UAT for parallel testing with open bugs-4467554(H),4462668(M),4462709(M) | DevStormers | mervinkumar.manickam
SI DCTA | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Kavi | As a myISP SA, I want to apply filter FFP Visible = False in addition to other filters while displaying Standard Role in staffing so that it is aligned with MMP standards | 4393527 | Manisa | Sathya | Completed | Completed | Completed | In Progress | 41 | 27 | 0 | 27 | 100% | 75% |  | 13 | 0 | 0 | 14 | 27 | 48.15% | 100% |  | TechSprinters | mervinkumar.manickam
SI DCTA | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Kavi | As a myISP SA, I want to add new columns in the DCTA JSON file so that dynamic target pricing can be computed | 4377948 | Manisa | Sathya | Completed | Completed | Completed | In Progress | 53 | 27 | 0 | 27 | 100% | 85% |  | 7 | 0 | 0 | 20 | 27 | 25.93% | 100% |  | TechSprinters | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Kavi | As a SA,I want the Profile city Tier field to auto-populate from the Rate Type column in the Staffing Baseline screen | 4359188 | Manisa | Sathya | Completed | Completed | Completed | In Progress | 51 | 35 | 0 | 35 | 100% | 80% |  | 25 | 0 | 0 | 10 | 35 | 71.43% | 100% |  | TechWizards | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Kavi | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) | 4359328 | Sathya | Manisa | Completed | Completed | Completed | In Progress | 65 | 51 | 0 | 51 | 100% | 80% |  | 20 | 5 | 0 | 26 | 51 | 49.02% | 80% | Bug-4462284(L),4462476(M),4465936(M) | TechWizards | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Kavi | As a SA I want to select standard role from an SSG-specific dropdown selection | 4359507 | Sathya | Manisa | Completed | Completed | Completed | In Progress | 54 | 38 | 0 | 38 | 100% | 75% |  | 28 | 0 | 0 | 10 | 38 | 73.68% | 100% |  | TechWizards | mervinkumar.manickam
PCW | MMP FFP Export update - April release | 4389877 | Anand | API - Enhance the defaulting logics to populate 'Accenture Role/Rate' in offline MMP FFP Export | 4368135 | Sairam | Sneha | Completed | Completed | In Progress | In Progress | 10 | 3 | 3 | 3 | 100% | 80% |  | 2 | 0 | 0 | 1 | 3 | 66.67% | 100% | Delivered to Parallol UAT | TechAvatar | suraj.sukumaran
SI - PCW | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | API - Save the Technology Tier, Profile City Tier, Role Type, Technology Role and Standard Role from Staffing Baseline | 4368224 | Viji | Naveen S | Completed | Completed | In Progress | In Progress | 44 | 11 | 8 | 11 | 100% | 100% |  | 6 | 2 | 0 | 2 | 10 | 80% | 75% | Bug id : 4462520(M),4462534(M), Delivered to UAT for Parallel Testing | TechAvatar | suraj.sukumaran
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Kavi | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) - OU changes | 4368812 | Sathya | Manisa | Completed | Completed | Completed | In Progress | 61 | 42 | 0 | 42 | 100% | 80% |  | 15 | 3 | 0 | 24 | 42 | 42.86% | 83.33% | Bug-4461770(M) | TechWizards | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | As a SA I want to select standard role from an SSG-specific dropdown selection- OU changes | 4368862 | Viji | Sneha | Completed | Completed | In Progress | In Progress | 42 | 12 | 8 | 8 | 100% | 90% |  | 5 | 0 | 0 | 3 | 8 | 62.5% | 100% | Delivered to UAT for Parallel testing | TechWizards | mervinkumar.manickam
SDL | Standard Role Implementation in SI Staffing Baseline - Analysis | 4277501 | Anand | As a Solution Architect, I want to see dynamic target pricing parameters in SDL SI DL regardless of rate card configuration | 4371046 | Sneha | Viji | Completed | Completed | Not Started | In Progress | 30 | 8 | 13 | 13 | 70% | 70% |  | 7 | 1 | 0 | 3 | 11 | 72.73% | 87.5% | Delivered for parallel testing, Bug : 4465941 (M) | DevStormers | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG. | 4372847 | Sneha | Naveen S | Completed | Completed | Not Started | In Progress | 43 | 30 | 24 | 24 | 70% | 70% |  | 8 | 8 | 0 | 8 | 24 | 66.67% | 50% | Bug 4462287(M),Bug 4462311(L), Bug: 4462289 (H), Delivered for parallel testing | TechWizards | mervinkumar.manickam
PCW | MMP FFP Export update - April release | 4389877 | Anand | PCW - Pass Role Type column to API as an input filter parameter for defaulting logics of offline MMP FFP Export | 4395067 | Sairam | Naveen S | Completed | Completed | In Progress | In Progress | 11 | 2 | 8 | 10 | 70% | 70% |  | 8 | 0 | 0 | 2 | 10 | 80% | 100% | Delivered to Parallol UAT | Tech Ensemble | suraj.sukumaran
Online SI | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | Rename existing 'Role Type' column in Staffing OU Template | 4411451 | Sairam | Sneha | Completed | Completed | In Progress | Completed | 10 | 3 | 1 | 4 | 100% | 90% |  | 3 | 0 | 0 | 0 | 3 | 100% | 100% | Delivered to UAT | TechAvengers | mervinkumar.manickam
SI - PCW | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | PCW - Add Technology Role and Standard Role Column in Staffing Baseline to populate the Roles of SI, CON-CAS | 4381707 | Naveen S | Viji | Completed | Completed | Not Started | Blocked | 76 | 12 | 2 | 14 | 85.72% | 100% |  | 8 | 3 | 3 | 0 | 14 | 78.57% | 57.14% | Bug 4462540(H), Bug 4462512(M) | Tech Ensemble | suraj.sukumaran
SI - PCW | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | PCW - Add Role Type Column in Staffing Baseline to populate the Role Types for SI, CON-CAS, AMS, IMS and BPMS | 4386371 | Naveen S | Sairam | Completed | Completed | Not Started | In Progress | 71 | 17 | 0 | 17 | 100% | 100% |  | 9 | 0 | 0 | 4 | 13 | 69.23% | 100% | Delivered to UAT for Parallel testing | Tech Ensemble | suraj.sukumaran
SI - PCW | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | PCW - Add Profile City Tier Column in Staffing Baseline to populate the Profile City Tier value for all profiles | 4386372 | Sneha | Viji | Completed | Completed | Not Started | Completed | 37 | 15 | 20 | 20 | 80% | 80% |  | 20 | 0 | 0 | 0 | 20 | 100% | 100% | Delivered to UAT | Tech Ensemble | suraj.sukumaran
SI - PCW | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | PCW - Rename existing 'Role Type' column in PCW 8.7 Template and Show a warning message in PCW 8.6 template | 4386373 | Naveen S | Sairam | Completed | Completed | Not Started | In Progress | 51 | 12 | 0 | 12 | 100% | 100% |  | 11 | 1 | 0 | 0 | 12 | 100% | 91.67% | Bug 4462585(M) Delivered to UAT for parallel testing | Tech Ensemble | suraj.sukumaran
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology - OU Changes | 4386942 | Viji | Naveen S | Completed | Completed | In Progress | In Progress | 35 | 11 | 5 | 8 | 100% | 80% |  | 7 | 1 | 0 | 0 | 8 | 100% | 87.5% | Bug id : 4462256(M), 4462256(M), Delivered to UAT | TechAvengers | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | As a SA, auto-populate Profile City Tier from Rate Type in Staffing Baseline-OU Changes | 4386944 | Viji | Sneha | Completed | Completed | In Progress | Completed | 40 | 10 | 5 | 9 | 100% | 100% |  | 9 | 0 | 0 | 0 | 9 | 100% | 100% | Delivered to UAT | TechAvengers | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG.- OU changes | 4386945 | Sneha | Sairam | Completed | Completed | Not Started | In Progress | 54 | 20 | 26 | 26 | 80% | 80% |  | 16 | 6 | 0 | 4 | 26 | 84.62% | 72.73% | Bug : 4465961 (H) | TechWizards | mervinkumar.manickam
STD Role | Standard Role Implementation in PCW & Online SI - April Release | 4373911 | Anand | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology | 4359294 | Naveen S | Viji | Completed | Completed | Not Started | In Progress | 53 | 10 | 0 | 10 | 100% | 100% |  | 5 | 0 | 0 | 5 | 10 | 50% | 100% |  | TechWizards | mervinkumar.manickam
Manage screen AMS VT Report link | Moving current AMSVT to PBI AMSVT. | 4446745 | Devika | As a AMS VT user, I want the AMSVT production URL to be updated in the Manage screen, So that the system redirects me to the correct AMSVT Link.. | 4446747 | Alekhya | Chaitanya | Completed | Completed | Not Started | Completed | 11 | 3 | 2 | 3 | 100% | 100% |  | 3 | 0 | 0 | 0 | 3 | 100% | 100% |  | GoRetro | sowjanya.kari
PMO reporting Layer | Addition of "Mergers and Acquisitions" column in PMO Reporting layer | 4458987 | Devika | As a user of the PMO Reporting layer report, I want to add a new column as "Mergers and Acquisitions" in report, so that I can see the newly added column data directly in the report. | 4459023 | Alekhya | Chaitanya | Completed | Completed | Not Started | Not Started | 10 | 5 | 4 | 5 | 100% | 100% |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | Cognilytics | anil.kadiri
LCM COTS Enhancements | LCM Infra - COTs App Replatform | 4386341 | Vaidheki | SI KDA Enhancement - COTS App Replatform Support | 4446805 | Keerthana | Liharshini | In Progress | Not Started | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | myISP_IMS | supriya.a.dhingra
LCM COTS Enhancements | LCM Infra - COTs App Replatform | 4386341 | Vaidheki | MMP FFP Resource Template - COTS App Replatform Handling | 4446806 | Keerthana | Liharshini | In Progress | Not Started | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | myISP_IMS | supriya.a.dhingra
LCM COTS Enhancements | LCM Infra - COTs App Replatform | 4386341 | Vaidheki | PCW Integration - COTS App Replatform Support | 4446807 | Keerthana | Liharshini | In Progress | Not Started | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | myISP_IMS | supriya.a.dhingra
LCM COTS Enhancements | LCM Infra - COTs App Replatform | 4386341 | Vaidheki | Reverse Order Logic - LCM Infrastructure Migration | 4446808 | Keerthana | Liharshini | In Progress | Not Started | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | myISP_IMS | supriya.a.dhingra
LCM COTS Enhancements | LCM Infra - COTs App Replatform | 4386341 | Vaidheki | Reverse Order Logic Extension - LCM Infra Override | 4446809 | Keerthana | Liharshini | In Progress | Not Started | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | myISP_IMS | supriya.a.dhingra
April MRDB | IMS BAU - Monthy MRDB | 4386335 | Vaidheki | Monthly MRDB - April'26 Release | 4450477 | Keerthana | Liharshini | In Progress | Not Started | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | myISP_IMS | supriya.a.dhingra
DFD | DFD - Reinvention Partner field addition in SA request | 4458972 | Himanshu | As a DFD requestor, I should get a Reinvention Partner dropdown in all the SA request forms | 4458973 | Anusha | Manjunath | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 25 | 25 | 0% | 0% |  | BackDoorGuardians | sona.job
DFD | DFD - Reinvention Partner field addition in SA request | 4458972 | Himanshu | AS a DFD requestor, I should get Reinvention partner field value in the existing SA requests | 4458985 | Manjunath | Anusha | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 34 | 34 | 0% | 0% |  | BackDoorGuardians | sona.job
DFD | DFD - Reinvention Partner field addition in SA request | 4458972 | Himanshu | As a DFD requestor, I should get Reinvention Partner field in SA mail templates when request is created/edited | 4458995 | Manjunath | Anusha | Completed | Completed | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 32 | 32 | 0% | 0% |  | BackDoorGuardians | sona.job
LCM COTS Enhancements | LCM Infra - COTs App Replatform | 4386341 | Vaidheki | LCM Infra Assessment - Questionnaire Update for Migration Type-Based Volume Selection | 4446804 |  |  | Not Started | Not Started | Not Started | Not Started | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0% | 0%

## TFS Details
Parent Title | mySP Initiative | Sub Initiative | TextVerification | Parent | ID | Title | State | Node Name | Testing POC | Planned for PT Date | Actual PT Date | Planned UAT Date | Actual UAT Date | Assigned To | Production Deployment Date | Story Points | Original Estimate | Priority | ETA | UT Results Attached | Code Review Completed | Created By | Created Date | Tags | Area Path | Iteration Path | Plan | Remaining | TextVerification1 | ExternalRef ID
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4359294 | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology | PT In Test | TechWizards | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-23 20:27 | 2026-03-23 05:30 | 2026-04-08 05:30 |  | Sargurunathan, Naveenkumar <n.sargurunathan@accenture.com> | 2026-04-18 05:30 |  |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-10 11:59 | Standard Role Configuration | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R58 and R59\Sprint148 |  |  | Tech Tier | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4368862 | As a SA I want to select standard role from an SSG-specific dropdown selection- OU changes | Ready for Test | TechWizards | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-03 05:30 |  | Sivakumar, Vijayalakshmi <v.b.sivakumar@accenture.com> | 2026-04-18 05:30 | 13 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-16 11:15 |  | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R58 and R59\Sprint148 |  |  | OU | mervinkumar.manickam
Standard Role Implementation in SI Staffing Baseline - Analysis | Rapid Soln | NextGen SI | SDL | 4277501 | 4371046 | As a Solution Architect, I want to see dynamic target pricing parameters in SDL SI DL regardless of rate card configuration | Ready for Test | DevStormers | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-03 05:30 |  | Malapati, Sai Sneha Latha <sai.sneha.l.malapati@accenture.com> | 2026-04-18 05:30 | 1 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-17 10:42 | April-2026; Enhancement; Export; reporting; SDL; SI-DL; Staffing | AutomationProcess_29697\mySPRapidSolutioning\DevStormers | AutomationProcess_29697 |  |  | STD role | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4372847 | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG. | Ready for Test | TechWizards | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-06 05:30 |  | Malapati, Sai Sneha Latha <sai.sneha.l.malapati@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-18 13:44 | Standard Role Configuration | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R61\Sprint154 |  |  | tr | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Platform Consolidation | NextGen | SI - PCW | 4373911 | 4381707 | PCW - Add Technology Role and Standard Role Column in Staffing Baseline to populate the Roles of SI, CON-CAS | PT In Test | Tech Ensemble | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-04-01 01:30 | 2026-03-20 05:30 | 2026-04-03 05:30 |  | Sargurunathan, Naveenkumar <n.sargurunathan@accenture.com> | 2026-04-18 05:30 | 7 |  | 2 |  | Yes | Yes | Akbar Basha, Musrath <musrath.akbar.basha@accenture.com> | 2026-02-20 12:05 | PCW | AutomationProcess_29697\mySPIntegratedSolutionPlatform\Tech Ensemble | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DCTA | suraj.sukumaran
Standard Role Implementation in PCW & Online SI - April Release | Platform Consolidation | NextGen | SI - PCW | 4373911 | 4386371 | PCW - Add Role Type Column in Staffing Baseline to populate the Role Types for SI, CON-CAS, AMS, IMS and BPMS | PT In Test | Tech Ensemble | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-04-01 01:30 | 2026-03-20 05:30 | 2026-04-06 05:30 |  | Sargurunathan, Naveenkumar <n.sargurunathan@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Akbar Basha, Musrath <musrath.akbar.basha@accenture.com> | 2026-02-21 02:10 | PCW | AutomationProcess_29697\mySPIntegratedSolutionPlatform\Tech Ensemble | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DCTA | suraj.sukumaran
Standard Role Implementation in PCW & Online SI - April Release | Platform Consolidation | NextGen | SI - PCW | 4373911 | 4386372 | PCW - Add Profile City Tier Column in Staffing Baseline to populate the Profile City Tier value for all profiles | Ready for Test | Tech Ensemble | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-04-01 01:30 | 2026-03-20 05:30 | 2026-04-06 05:30 |  | Malapati, Sai Sneha Latha <sai.sneha.l.malapati@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | NA | Akbar Basha, Musrath <musrath.akbar.basha@accenture.com> | 2026-02-21 02:33 | PCW | AutomationProcess_29697\mySPIntegratedSolutionPlatform\Tech Ensemble | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DCTA | suraj.sukumaran
Standard Role Implementation in PCW & Online SI - April Release | Platform Consolidation | NextGen | SI - PCW | 4373911 | 4386373 | PCW - Rename existing 'Role Type' column in PCW 8.7 Template and Show a warning message in PCW 8.6 template | PT In Test | Tech Ensemble | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-04-01 01:30 | 2026-03-20 05:30 | 2026-04-03 05:30 |  | Sargurunathan, Naveenkumar <n.sargurunathan@accenture.com> | 2026-04-18 05:30 | 2 |  | 2 |  | Yes | NA | Akbar Basha, Musrath <musrath.akbar.basha@accenture.com> | 2026-02-21 02:50 | PCW | AutomationProcess_29697\mySPIntegratedSolutionPlatform\Tech Ensemble | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DCTA | suraj.sukumaran
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4386942 | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology - OU Changes | Ready for Test | TechAvengers | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-03 05:30 |  | Sivakumar, Vijayalakshmi <v.b.sivakumar@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-23 11:26 |  | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechAvengers | AutomationProcess_29697 |  |  | Online SI | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4386944 | As a SA, auto-populate Profile City Tier from Rate Type in Staffing Baseline-OU Changes | Ready for Test | TechAvengers | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-06 05:30 |  | Sivakumar, Vijayalakshmi <v.b.sivakumar@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-23 11:26 |  | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechAvengers | AutomationProcess_29697 |  |  | Online SI | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4386945 | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG.- OU changes | Ready for Test | TechWizards | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-06 05:30 |  | Malapati, Sai Sneha Latha <sai.sneha.l.malapati@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-23 11:26 |  | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697 |  |  | OU | mervinkumar.manickam
MMP FFP Export update - April release | Platform Consolidation | NextGen SI | PCW | 4389877 | 4368135 | API - Enhance the defaulting logics to populate 'Accenture Role/Rate' in offline MMP FFP Export | In Test | TechAvatar | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-04-02 01:30 | 2026-04-02 18:08 | 2026-04-03 05:30 |  | Pamarthi, Sairam <sairam.pamarthi@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Akbar Basha, Musrath <musrath.akbar.basha@accenture.com> | 2026-02-13 20:35 | PCW | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechAvatar | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R52 |  |  | MMP FFP | suraj.sukumaran
Standard Role Implementation in PCW & Online SI - April Release | Platform Consolidation | NextGen | SI - PCW | 4373911 | 4368224 | API - Save the Technology Tier, Profile City Tier, Role Type, Technology Role and Standard Role from Staffing Baseline | PT In Test | TechAvatar | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-04-01 01:30 | 2026-03-24 00:06 | 2026-04-03 05:30 |  | Sivakumar, Vijayalakshmi <v.b.sivakumar@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Akbar Basha, Musrath <musrath.akbar.basha@accenture.com> | 2026-02-13 22:08 | PCW | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechAvatar | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DCTA | suraj.sukumaran
MMP FFP Export update - April release | Platform Consolidation | NextGen SI | PCW | 4389877 | 4395067 | PCW - Pass Role Type column to API as an input filter parameter for defaulting logics of offline MMP FFP Export | In Test | Tech Ensemble | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-04-02 01:30 | 2026-04-02 18:09 | 2026-04-03 05:30 |  | Pamarthi, Sairam <sairam.pamarthi@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Akbar Basha, Musrath <musrath.akbar.basha@accenture.com> | 2026-02-28 02:45 | PCW | AutomationProcess_29697\mySPIntegratedSolutionPlatform\Tech Ensemble | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R52 |  |  | MMP FFP | suraj.sukumaran
Standard Role Implementation in PCW & Online SI - April Release | Platform Consolidation | NextGen | Online SI | 4373911 | 4411451 | Rename existing 'Role Type' column in Staffing OU Template | In Test | TechAvengers | B Gadad, Anand <anand.b.gadad@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-03 05:30 |  | Pamarthi, Sairam <sairam.pamarthi@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Parivallal, Aiswarya <aiswarya.parivallal@accenture.com> | 2026-03-05 19:20 |  | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechAvengers | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | Staffing OU | mervinkumar.manickam
Angular upgrade version 19 to version 21 - 18th April | Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | Ready for Test | MYISP_Revamp_UI | Damodaran, J. <j.damodaran@accenture.com> | 2026-04-02 20:26 | 2026-04-02 22:44 | 2026-04-10 05:30 |  | Nanditha Uddaraju, Anuradha <a.nanditha.uddaraju@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Kamble, Pallavi <pallavi.kamble@accenture.com> | 2026-03-16 19:15 | Angular upgrade v19 to v21; Cost Price Engine UI; PT Regression; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\MYISP_Revamp_UI | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | Cost Price Engine UI | vikrant.r.mohite
Available Hours OU Report | Rapid Soln | OCP | AMS | 4439196 | 4439199 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export/Import status tab in Available Hours screen | Active | TechMavericks | Damodaran, J. <j.damodaran@accenture.com> | 2026-04-08 22:00 |  | 2026-04-09 00:30 |  | Jallipalli, Nikhila <nikhila.jallipalli@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-03-23 17:29 | CCB Approved | AutomationProcess_29697\mySPRapidSolutioning\TechMavericks | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | AMS - Available Hours | Francis.Deepak
Available Hours OU Report | Rapid Soln | OCP | AMS | 4439196 | 4439323 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for Staffing | Active | TechCoders | Damodaran, J. <j.damodaran@accenture.com> | 2026-04-08 22:00 |  | 2026-04-09 00:30 |  | Anirudh, Channagiri <channagiri.anirudh@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-03-23 18:59 | CCB Approved | AutomationProcess_29697\mySPRapidSolutioning\TechCoders | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | AMS - Available Hours | Francis.Deepak
Available Hours OU Report | Rapid Soln | OCP | AMS | 4439196 | 4439343 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for PMO | Active | TechCoders | Damodaran, J. <j.damodaran@accenture.com> | 2026-04-08 22:00 |  | 2026-04-09 00:30 |  | Anirudh, Channagiri <channagiri.anirudh@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-03-23 19:35 | CCB Approved | AutomationProcess_29697\mySPRapidSolutioning\TechCoders | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | AMS - Available Hours | Francis.Deepak
Available Hours OU Report | Rapid Soln | OCP | AMS | 4439196 | 4439357 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for Staffing | Active | TechMavericks | Damodaran, J. <j.damodaran@accenture.com> | 2026-04-08 23:00 |  | 2026-04-09 00:30 |  | Vasant Pawar, Deepti <deepti.vasant.pawar@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-03-23 19:51 | CCB Approved | AutomationProcess_29697\mySPRapidSolutioning\TechMavericks | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | AMS - Available Hours | Francis.Deepak
Available Hours OU Report | Rapid Soln | OCP | AMS | 4439196 | 4439362 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for PMO | Active | TechMavericks | Damodaran, J. <j.damodaran@accenture.com> | 2026-04-08 23:00 |  | 2026-04-09 00:30 |  | Vasant Pawar, Deepti <deepti.vasant.pawar@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-03-23 20:06 | CCB Approved | AutomationProcess_29697\mySPRapidSolutioning\TechMavericks | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | AMS - Available Hours | Francis.Deepak
Angular upgrade version 19 to version 21 - 18th April | Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | Das, Leena <leena.a.das@accenture.com> | 2026-04-02 20:24 | 2026-04-02 05:30 | 2026-04-03 18:53 | 2026-04-03 18:53 | Udhayakumar, Harshitha <h.udhayakumar@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Kamble, Pallavi <pallavi.kamble@accenture.com> | 2026-03-16 19:12 | Angular upgrade v19 to v21; Digital Documentation - MFE; PT Regression; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\MYISP_Revamp_UI | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | Digital Documentation - MFE | vikrant.r.mohite
DFD - Reinvention Partner field addition in SA request | Platform Consolidation | DFD | DFD | 4458972 | 4458973 | As a DFD requestor, I should get a Reinvention Partner dropdown in all the SA request forms | New | BackDoorGuardians | Jain, Himanshu <himanshu.m.jain@accenture.com> | 2026-04-10 23:30 |  | 2026-04-16 05:30 |  | Singh, Sudhakar <sudhakar.a.singh@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-04-01 19:22 | CCB Approved; Po Input | AutomationProcess_29697\BackDoorGuardians | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DFD Enhancement | sona.job
DFD - Reinvention Partner field addition in SA request | Platform Consolidation | DFD | DFD | 4458972 | 4458985 | AS a DFD requestor, I should get Reinvention partner field value in the existing SA requests | Active | BackDoorGuardians | Jain, Himanshu <himanshu.m.jain@accenture.com> | 2026-04-10 23:30 |  | 2026-04-15 05:30 |  | Mishra, Alok E. <alok.e.mishra@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-04-01 19:31 | CCB Approved; Po Input | AutomationProcess_29697\BackDoorGuardians | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DFD Enhancement | sona.job
DFD - Reinvention Partner field addition in SA request | Platform Consolidation | DFD | DFD | 4458972 | 4458995 | As a DFD requestor, I should get Reinvention Partner field in SA mail templates when request is created/edited | Active | BackDoorGuardians | Jain, Himanshu <himanshu.m.jain@accenture.com> | 2026-04-10 23:30 |  | 2026-04-15 05:30 |  | Thirumanikumar, Sneha <sneha.thirumanikumar@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  |  |  | Vijay Deshpande, Prajakta <p.vijay.deshpande@accenture.com> | 2026-04-01 19:40 | CCB Approved; Po Input | AutomationProcess_29697\BackDoorGuardians | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | DFD Enhancement | sona.job
Moving current AMSVT to PBI AMSVT. | Platform Consolidation | Analytics | Manage screen AMS VT Report link | 4446745 | 4446747 | As a AMS VT user, I want the AMSVT production URL to be updated in the Manage screen, So that the system redirects me to the correct AMSVT Link.. | In Test | GoRetro | Kalaivanan, Devika <devika.kalaivanan@accenture.com> | 2026-04-04 02:30 | 2026-04-02 17:12 | 2026-04-08 23:30 | 2026-04-03 22:40 | Alekhyareddy, Osuru <osuru.alekhyareddy@accenture.com> | 2026-04-18 05:30 |  |  | 2 |  | Yes | Yes | Rani Agurla, Sowmya <sowmya.rani.agurla@accenture.com> | 2026-03-27 20:14 | CCB Approved; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\GoRetro | AutomationProcess_29697\mySolutionPlannerRapidSolutioning |  |  | AMS VT | sowjanya.kari
Addition of "Mergers and Acquisitions" column in PMO Reporting layer | Platform Consolidation | Analytics | PMO reporting Layer | 4458987 | 4459023 | As a user of the PMO Reporting layer report, I want to add a new column as "Mergers and Acquisitions" in report, so that I can see the newly added column data directly in the report. | Active | Cognilytics | Kalaivanan, Devika <devika.kalaivanan@accenture.com> | 2026-04-07 05:30 |  | 2026-04-10 05:30 |  | Satravada, Rakesh <r.a.satravada@accenture.com> | 2026-04-18 23:30 | 4 |  | 2 |  |  |  | Rani Agurla, Sowmya <sowmya.rani.agurla@accenture.com> | 2026-04-01 19:46 | CCB Approved; Po Input; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\Cognilytics | AutomationProcess_29697\mySolutionPlannerRapidSolutioning |  |  | Analytics | anil.kadiri
Angular upgrade version 19 to version 21 - 18th April | Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | Kalia Moorthy, Rajarajeswari <r.kalia.moorthy@accenture.com> | 2026-04-02 20:24 | 2026-04-02 22:48 |  |  | Mohandass, Pavithra <p.mohandass@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Kamble, Pallavi <pallavi.kamble@accenture.com> | 2026-03-16 19:13 | Angular upgrade v19 to v21; CDAT - MFE; PT Regression; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\MYISP_Revamp_UI | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | CDAT - MFE | vikrant.r.mohite
Angular upgrade version 19 to version 21 - 18th April | Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | Krishnan, Pirtheebaa <pirtheebaa.krishnan@accenture.com> | 2026-04-02 20:26 | 2026-04-03 00:30 |  |  | Veluri, Janardhan <janardhan.veluri@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Kamble, Pallavi <pallavi.kamble@accenture.com> | 2026-03-16 18:29 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\MYISP_Revamp_UI | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform |  |  | Solution Components (AMS) – MFE | vikrant.r.mohite
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4368812 | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) - OU changes | PT In Test | TechWizards | Selvamani, Kavichandrika <k.b.selvamani@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-08 23:30 |  | Bid, Manisa <manisa.bid@accenture.com> | 2026-04-18 05:30 | 13 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-16 10:56 |  | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R58 and R59\Sprint148 |  |  | role type ou | mervinkumar.manickam
MMP FFP Export update - April release | Rapid Soln | NextGen SI | MMP FFP | 4389877 | 4391224 | As a myISP SA, I want to change the logic to populate "Role Type" and "Accenture Role/Rate" in MMP FFP so that it is aligned with Dynamic Target Pricing implementation | PT In Test | DevStormers | Selvamani, Kavichandrika <k.b.selvamani@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-07 23:30 |  | Senthilkumar, Sathya Priya <sathya.senthilkumar@accenture.com> | 2026-04-18 05:30 | 1 |  | 2 |  | Yes | Yes | Aggarwal, Sugandha <sugandha.a.aggarwal@accenture.com> | 2026-02-25 11:22 |  | AutomationProcess_29697\mySPRapidSolutioning\DevStormers | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R64\Sprint162 |  |  | MMP FFP | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | DCTA | SI DCTA | 4373911 | 4393527 | As a myISP SA, I want to apply filter FFP Visible = False in addition to other filters while displaying Standard Role in staffing so that it is aligned with MMP standards | PT In Test | TechSprinters | Selvamani, Kavichandrika <k.b.selvamani@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-09 05:30 |  | Senthilkumar, Sathya Priya <sathya.senthilkumar@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Aggarwal, Sugandha <sugandha.a.aggarwal@accenture.com> | 2026-02-26 15:58 |  | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechSprinters | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R64\Sprint160 |  |  | SI DCTA | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | DCTA | SI DCTA | 4373911 | 4377948 | As a myISP SA, I want to add new columns in the DCTA JSON file so that dynamic target pricing can be computed | PT In Test | TechSprinters | Selvamani, Kavichandrika <k.b.selvamani@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-09 05:30 |  | Senthilkumar, Sathya Priya <sathya.senthilkumar@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Aggarwal, Sugandha <sugandha.a.aggarwal@accenture.com> | 2026-02-19 16:01 | Standard Role Configuration | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechSprinters | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R64\Sprint160 |  |  | SI DCTA | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4359328 | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) | PT In Test | TechWizards | Selvamani, Kavichandrika <k.b.selvamani@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-08 05:30 |  | Bid, Manisa <manisa.bid@accenture.com> | 2026-04-18 05:30 | 5 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-10 12:13 | Field Management; Profile Screen; Role Type; Standard Role Configuration | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R65\Sprint163 |  |  | Role type | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4359507 | As a SA I want to select standard role from an SSG-specific dropdown selection | PT In Test | TechWizards | Selvamani, Kavichandrika <k.b.selvamani@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-08 05:30 |  | Bid, Manisa <manisa.bid@accenture.com> | 2026-04-18 05:30 | 7 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-10 12:56 | Standard Role Configuration | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R65\Sprint163 |  |  | STD role field | mervinkumar.manickam
Standard Role Implementation in PCW & Online SI - April Release | Rapid Soln | NextGen SI | STD Role | 4373911 | 4359188 | As a SA,I want the Profile city Tier field to auto-populate from the Rate Type column in the Staffing Baseline screen | PT In Test | TechWizards | Selvamani, Kavichandrika <k.b.selvamani@accenture.com> | 2026-03-20 05:30 | 2026-03-23 05:30 | 2026-04-08 23:30 |  | Bid, Manisa <manisa.bid@accenture.com> | 2026-04-18 05:30 | 3 |  | 2 |  | Yes | Yes | Ganesan, Mathangi <mathangi.a.ganesan@accenture.com> | 2026-02-10 11:11 | Standard Role Configuration | AutomationProcess_29697\mySPIntegratedSolutionPlatform\TechWizards | AutomationProcess_29697\mySolutionPlannerIntegratedSolutionPlatform\R65\Sprint163 |  |  | Staffing baseline | Mervinkumar.manickam
LCM Infra - COTs App Replatform | Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | 4446804 | LCM Infra Assessment - Questionnaire Update for Migration Type-Based Volume Selection | Active | myISP_IMS | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-04-07 05:30 |  | 2026-04-10 05:30 |  | P K, Prabitha <prabitha.p.k@accenture.com> | 2026-04-18 05:30 | 2 |  | 2 |  | Yes | Yes | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-03-27 21:42 | IMS BAU; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\myISP_IMS | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R65\Sprint163 |  |  | LCM COTS Enhancements | supriya.a.dhingra
LCM Infra - COTs App Replatform | Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | 4446805 | SI KDA Enhancement - COTS App Replatform Support | Active | myISP_IMS | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-04-07 05:30 |  | 2026-04-10 05:30 |  | P K, Prabitha <prabitha.p.k@accenture.com> | 2026-04-18 05:30 | 2 |  | 2 |  | Yes | Yes | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-03-27 21:42 | IMS BAU; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\myISP_IMS | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R65\Sprint163 |  |  | LCM COTS Enhancements | supriya.a.dhingra
LCM Infra - COTs App Replatform | Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | 4446806 | MMP FFP Resource Template - COTS App Replatform Handling | Active | myISP_IMS | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-04-07 05:30 |  | 2026-04-10 05:30 |  | P K, Prabitha <prabitha.p.k@accenture.com> | 2026-04-18 05:30 | 1 |  | 2 |  | Yes | Yes | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-03-27 21:42 | IMS BAU; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\myISP_IMS | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R65\Sprint163 |  |  | LCM COTS Enhancements | supriya.a.dhingra
LCM Infra - COTs App Replatform | Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | 4446807 | PCW Integration - COTS App Replatform Support | Active | myISP_IMS | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-04-07 05:30 |  | 2026-04-10 05:30 |  | P K, Prabitha <prabitha.p.k@accenture.com> | 2026-04-18 05:30 | 2 |  | 2 |  | Yes | Yes | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-03-27 21:43 | IMS BAU; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\myISP_IMS | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R65\Sprint163 |  |  | LCM COTS Enhancements | supriya.a.dhingra
LCM Infra - COTs App Replatform | Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | 4446808 | Reverse Order Logic - LCM Infrastructure Migration | Active | myISP_IMS | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-04-07 05:30 |  | 2026-04-10 05:30 |  | P K, Prabitha <prabitha.p.k@accenture.com> | 2026-04-18 05:30 | 2 |  | 2 |  | Yes | Yes | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-03-27 21:43 | IMS BAU; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\myISP_IMS | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R65\Sprint163 |  |  | LCM COTS Enhancements | supriya.a.dhingra
LCM Infra - COTs App Replatform | Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | 4446809 | Reverse Order Logic Extension - LCM Infra Override | Active | myISP_IMS | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-04-07 05:30 |  | 2026-04-10 05:30 |  | P K, Prabitha <prabitha.p.k@accenture.com> | 2026-04-18 05:30 | 2 |  | 2 |  | Yes | Yes | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-03-27 21:43 | IMS BAU; UAT Testing Not Required | AutomationProcess_29697\mySPIntegratedSolutionPlatform\myISP_IMS | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R65\Sprint163 |  |  | LCM COTS Enhancements | supriya.a.dhingra
IMS BAU - Monthy MRDB | Platform Consolidation | Inspire | April MRDB | 4386335 | 4450477 | Monthly MRDB - April'26 Release | Active | myISP_IMS | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-04-07 05:30 |  |  |  | P K, Prabitha <prabitha.p.k@accenture.com> | 2026-04-18 05:30 | 1 |  | 2 |  | Yes | Yes | Srinivasan, Vaidheki <vaidheki.srinivasan@accenture.com> | 2026-03-31 10:23 | IMS BAU | AutomationProcess_29697\mySPIntegratedSolutionPlatform\myISP_IMS | AutomationProcess_29697\mySolutionPlannerRapidSolutioning\R65\Sprint163 |  |  | April MRDB | supriya.a.dhingra
myISP - Digital DCSO | Rapid Soln | NextGen | DCSO | 4278081 | 4362582 | As a myisp Solution Architect, I want the DCSO tab to be removed from the SI KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | PT In Test | Insurgents | Vv, Shini <shini.vv@accenture.com> | 2026-04-06 17:30 | 2026-04-03 16:50 | 2026-04-09 05:30 |  | Momin, Jeba <jeba.momin@accenture.com> | 2026-04-18 05:30 | 2 |  | 2 |  | Yes | Yes | Ashok, Sindhuja <sindhuja.ashok@accenture.com> | 2026-02-11 12:38 | Autocreate; DCSO | AutomationProcess_29697\mySPRapidSolutioning\Insurgents | AutomationProcess_29697\mySolutionPlannerRapidSolutioning |  |  | DCSO | K.devaraj
myISP - Digital DCSO | Rapid Soln | NextGen | DCSO | 4278081 | 4362592 | As a myisp Solution Architect, I want the DCSO tab to be removed from the AMS KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | PT In Test | Insurgents | Vv, Shini <shini.vv@accenture.com> | 2026-04-06 17:30 | 2026-04-03 16:50 | 2026-04-09 05:30 |  | Momin, Jeba <jeba.momin@accenture.com> | 2026-04-18 05:30 |  |  | 2 |  | Yes | Yes | Ashok, Sindhuja <sindhuja.ashok@accenture.com> | 2026-02-11 12:41 | Autocreate; DCSO | AutomationProcess_29697\mySPRapidSolutioning\Insurgents | AutomationProcess_29697\mySolutionPlannerRapidSolutioning |  |  | DCSO | K.devaraj

## Environment Details
System | PT | UAT
myISP | https://myISPnextgen.ciostage.accenture.com | https://myispnextgen-uat.ciotest.accenture.com/
MMS | https://accenture--AprAglTst.sandbox.my.salesforce.com/ | https://accenture--q3stg.sandbox.lightning.force.com/l |  | Test Rebar beta - Switch on Jan 12th - Marqtrtst
MMP | MMP Test | MMP Stage |  | Test rebar stage - No change - Q2 stage.
myISP - Apr 18th Release
| PT | UAT | POC | Comments
myISP | https://myISPnextgen.ciostage.accenture.com | https://myispnextgen-uat.ciotest.accenture.com/ | Release POCs
IMS |  | https://myispims-opsstage.ciostage.accenture.com/ | Aqil/Release POCs
BPMS | https://bpmssolutionestimator.myisppt2.accenture.com/
MDA |  | MDA Instance 1 | Pirtheebaa
Analytics |  | Analytics Instance 1 | Shini
DATA KDA |  |  | Devika
SSA |  | SSA Stage | Devika
SCA |  | SCA UAT 2 | Kavi
Costing SCC |  |  | Jaya
AC- Gen Wizard |  |  | Nandini
Gen AI |  |  | Hajara
IDRA |  |  | Jaya
AAI - Apps |  |  | Nandini
AC - Gen AI Assets |  |  | Nandini
mydiagnostics |  |  | Nandini
CDAT |  |  | Raji

## (DO NOT TOUCH) STATUS PIVOT
Node Name | (All)
MPOC | (All)
Feature ID | Parent Title | Count of Title | Count of Test Planning | Count of BA Review | Sum of Passed | Sum of Failed | Sum of Blocked | Sum of Not Run | Sum of Total | Execution % | Pass %
4278081 | myISP - Digital DCSO | 2 | 2 | 2 | 4 | 0 | 0 | 2 | 6 | 66.67% | 100%
(blank) | (blank) | [8 empty] | 0% | 0%
4386341 | LCM Infra - COTs App Replatform | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4386335 | IMS BAU - Monthy MRDB | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4429397 | Angular upgrade version 19 to version 21 - 18th April | 4 | 4 | 4 | 60 | 1 | 0 | 26 | 87 | 70.11% | 98.36%
4389877 | MMP FFP Export update - April release | 3 | 3 | 3 | 21 | 7 | 0 | 12 | 40 | 70% | 75%
4373911 | Standard Role Implementation in PCW & Online SI - April Release | 18 | 18 | 18 | 212 | 29 | 0 | 136 | 377 | 63.93% | 87.97%
4277501 | Standard Role Implementation in SI Staffing Baseline - Analysis | 1 | 1 | 1 | 7 | 1 | 0 | 3 | 11 | 72.73% | 87.5%
4446745 | Moving current AMSVT to PBI AMSVT. | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 3 | 100% | 100%
4458987 | Addition of "Mergers and Acquisitions" column in PMO Reporting layer | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4458972 | DFD - Reinvention Partner field addition in SA request | 3 | 3 | 3 | 0 | 0 | 0 | 68 | 68 | 0% | 0%
4439196 | Available Hours OU Report | 5 | 5 | 5 | 0 | 0 | 0 | 56 | 56 | 0% | 0%
Grand Total |  | 45 | 45 | 45 | 307 | 38 | 0 | 303 | 648 | 53.24% | 88.99%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%
[10 empty] | 0% | 0%