## Story Summary
mySP Initiative | Sub Initiative | TextVerification | Parent | Parent Title | ID | Title | State | Node Name | M POC | SM POC | AD POC | Testing POC | Planned for PT Date | Actual PT Date | Planned UAT Date | Actual UAT Date | Story Points | Tags | Testing NA stories | PT testable stories | UAT Testable Stories | UAT Testing NA stories | PT delivered | PT NOT delivered | UAT delivered | UAT NOT delivered | Passed | Failed | Blocked | Not Run
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359188 | As a SA,I want the Profile city Tier field to auto-populate from the Rate Type column in the Staffing Baseline screen | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T18:00:00Z |  | 3 | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 25 | 0 | 0 | 10
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359294 | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-23T14:57:00Z | 2026-03-23T00:00:00Z | 2026-04-08T00:00:00Z |  |  | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 5 | 0 | 0 | 5
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359328 | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T00:00:00Z |  | 5 | Field Management; Profile Screen; Role Type; Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 20 | 5 | 0 | 26
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359507 | As a SA I want to select standard role from an SSG-specific dropdown selection | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T00:00:00Z |  | 7 | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 28 | 0 | 0 | 10
Rapid Soln | NextGen | DCSO | 4278081 | myISP - Digital DCSO | 4362582 | As a myisp Solution Architect, I want the DCSO tab to be removed from the SI KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | PT In Test | Insurgents | K.devaraj | vishnupriya.aluru | srinivasan.ks | Vv, Shini | 2026-04-06T12:00:00Z | 2026-04-03T11:20:00Z | 2026-04-09T00:00:00Z |  | 2 | Autocreate; DCSO | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0
Rapid Soln | NextGen | DCSO | 4278081 | myISP - Digital DCSO | 4362592 | As a myisp Solution Architect, I want the DCSO tab to be removed from the AMS KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | PT In Test | Insurgents | K.devaraj | vishnupriya.aluru | srinivasan.ks | Vv, Shini | 2026-04-06T12:00:00Z | 2026-04-03T11:20:00Z | 2026-04-09T00:00:00Z |  |  | Autocreate; DCSO | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0
Platform Consolidation | NextGen SI | PCW | 4389877 | MMP FFP Export update - April release | 4368135 | API - Enhance the defaulting logics to populate 'Accenture Role/Rate' in offline MMP FFP Export | UAT In Test | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-04-01T20:00:00Z | 2026-04-02T12:38:00Z | 2026-04-03T00:00:00Z | 2026-04-06T16:10:00Z | 3 | parallel testing; Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 1
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4368224 | API - Save the Technology Tier, Profile City Tier, Role Type, Technology Role and Standard Role from Staffing Baseline | UAT In Test | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-23T18:36:00Z | 2026-04-03T00:00:00Z | 2026-04-06T15:53:00Z | 5 | PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 6 | 2 | 0 | 2
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4368812 | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) - OU changes | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T18:00:00Z |  | 13 |  | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 15 | 3 | 0 | 24
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4368862 | As a SA I want to select standard role from an SSG-specific dropdown selection- OU changes | UAT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-07T10:57:00Z | 13 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 5 | 0 | 0 | 3
Rapid Soln | NextGen SI | SDL | 4277501 | Standard Role Implementation in SI Staffing Baseline - Analysis | 4371046 | As a Solution Architect, I want to see dynamic target pricing parameters in SDL SI DL regardless of rate card configuration | UAT In Test | DevStormers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T12:17:00Z | 1 | April-2026; Enhancement; Export; parallel testing; reporting; SDL; SI-DL; Staffing | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 7 | 1 | 0 | 3
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4372847 | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG. | UAT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-06T16:23:00Z | 5 | parallel testing; Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 8 | 8 | 0 | 8
Rapid Soln | DCTA | SI DCTA | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4377948 | As a myISP SA, I want to add new columns in the DCTA JSON file so that dynamic target pricing can be computed | PT In Test | TechSprinters | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-09T00:00:00Z |  | 5 | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 7 | 0 | 0 | 20
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4381707 | PCW - Add Technology Role and Standard Role Column in Staffing Baseline to populate the Roles of SI, CON-CAS | Blocked in PT | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-03T00:00:00Z |  | 7 | PCW | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 8 | 3 | 3 | 0
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386371 | PCW - Add Role Type Column in Staffing Baseline to populate the Role Types for SI, CON-CAS, AMS, IMS and BPMS | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-07T14:25:00Z | 5 | Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 9 | 0 | 0 | 4
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386372 | PCW - Add Profile City Tier Column in Staffing Baseline to populate the Profile City Tier value for all profiles | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-06T12:56:00Z | 3 | PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 20 | 0 | 0 | 0
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386373 | PCW - Rename existing 'Role Type' column in PCW 8.7 Template and Show a warning message in PCW 8.6 template | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T13:06:00Z | 2 | Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 11 | 1 | 0 | 0
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386942 | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology - OU Changes | UAT In Test | TechAvengers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T15:57:00Z | 5 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 7 | 1 | 0 | 0
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386944 | As a SA, auto-populate Profile City Tier from Rate Type in Staffing Baseline-OU Changes | UAT In Test | TechAvengers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-07T10:55:00Z | 3 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 9 | 0 | 0 | 0
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386945 | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG.- OU changes | UAT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-06T19:12:00Z | 5 | parallel testing | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 16 | 6 | 0 | 4
Rapid Soln | NextGen SI | MMP FFP | 4389877 | MMP FFP Export update - April release | 4391224 | As a myISP SA, I want to change the logic to populate "Role Type" and "Accenture Role/Rate" in MMP FFP so that it is aligned with Dynamic Target Pricing implementation | UAT In Test | DevStormers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-07T18:00:00Z | 2026-04-07T16:58:00Z | 1 | Parallel UAT | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 11 | 7 | 0 | 9
Rapid Soln | DCTA | SI DCTA | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4393527 | As a myISP SA, I want to apply filter FFP Visible = False in addition to other filters while displaying Standard Role in staffing so that it is aligned with MMP standards | PT In Test | TechSprinters | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-09T00:00:00Z |  | 5 |  | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 13 | 0 | 0 | 14
Platform Consolidation | NextGen SI | PCW | 4389877 | MMP FFP Export update - April release | 4395067 | PCW - Pass Role Type column to API as an input filter parameter for defaulting logics of offline MMP FFP Export | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-04-01T20:00:00Z | 2026-04-02T12:39:00Z | 2026-04-03T00:00:00Z | 2026-04-06T16:10:00Z | 3 | parallel testing; Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 8 | 0 | 0 | 2
Platform Consolidation | PCW | PCW | 4436130 | PCW Technical BAU Activity - April release | 4411262 | [ Technical ] PCW - Sonar Qubes, Prod Support, Reverse Engineering Documentation, Unit Test Case Creation | New | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-04-18T00:00:00Z |  |  |  | 5 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen | Online SI | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4411451 | Rename existing 'Role Type' column in Staffing OU Template | UAT In Test | TechAvengers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T10:38:00Z | 3 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 3 | 0 | 0 | 0
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Krishnan, Pirtheebaa | 2026-04-02T14:56:00Z | 2026-04-02T19:00:00Z |  |  | 3 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 20 | 0 | 0 | 0
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Das, Leena | 2026-04-02T14:54:00Z | 2026-04-02T00:00:00Z | 2026-04-03T13:23:00Z | 2026-04-03T13:23:00Z | 3 | Angular upgrade v19 to v21; Digital Documentation - MFE; PT Regression; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 4
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Kalia Moorthy, Rajarajeswari | 2026-04-02T14:54:00Z | 2026-04-02T17:18:00Z |  |  | 3 | Angular upgrade v19 to v21; CDAT - MFE; PT Regression; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 28 | 0 | 0 | 12
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Damodaran, J. | 2026-04-02T14:56:00Z | 2026-04-02T17:14:00Z | 2026-04-10T00:00:00Z |  | 3 | Angular upgrade v19 to v21; Cost Price Engine UI; PT Regression; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 4
Platform Consolidation | NextGen | MYISP_Revamp_UI_MFE_Host | 4310290 | Ownership & Maintenance of MFE Host Component | 4429566 | 18th April ¦ Technical ¦ MFE Host ¦ Planned Work Intake | New | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | MYISP_Revamp_UI_MFE_Host; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen | MYISP_Revamp_UI_MFE_Host | 4310290 | Ownership & Maintenance of MFE Host Component | 4429575 | 18th April ¦ Technical ¦ MFE Host ¦ Ad‑hoc Engineering Request (Code changes) Intake | New | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | MYISP_Revamp_UI_MFE_Host; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen | MYISP_Revamp_UI_MFE_Host | 4310290 | Ownership & Maintenance of MFE Host Component | 4431421 | 18th April ¦ Technical ¦ MFE Host ¦ Support & Enablement Work Tracking | New | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | MYISP_Revamp_UI_MFE_Host; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade Readiness | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4432313 | Technical ¦ Angular Upgrade Drop 3 ¦ Analyze Legacy Application for Upgrade Readiness ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Analyze for Upgrade Readiness; Angular Upgrade Drop 3; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade Readiness | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4432322 | Technical ¦ Angular Upgrade Drop 3 ¦ Analyze Legacy Application for Upgrade Readiness ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Analyze for Upgrade Readiness; Angular Upgrade Drop 3; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade Readiness | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4432327 | Technical ¦ Angular Upgrade Drop 3 ¦ Analyze Legacy Application for Upgrade Readiness ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Analyze for Upgrade Readiness; Angular Upgrade Drop 3; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade Readiness | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4432328 | Technical ¦ Angular Upgrade Drop 3 ¦ Analyze Legacy Application for Upgrade Readiness ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Analyze for Upgrade Readiness; Angular Upgrade Drop 3; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade of Angular Core and Dependencies | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4432365 | Technical ¦ Angular Upgrade Drop 3 ¦ Upgrade of Angular Core Framework to v21 ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Testing NA; Upgrade of Angular Core and Dependencies | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade of Angular Core and Dependencies | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4432373 | Technical ¦ Angular Upgrade Drop 3 ¦ Upgrade of Angular Core Framework to v21 ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Testing NA; Upgrade of Angular Core and Dependencies | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade of Angular Core and Dependencies | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4432390 | Technical ¦ Angular Upgrade Drop 3 ¦ Upgrade of Angular Core Framework to v21 ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Testing NA; Upgrade of Angular Core and Dependencies | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Upgrade of Angular Core and Dependencies | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4432400 | Technical ¦ Angular Upgrade Drop 3 ¦ Upgrade of Angular Core Framework to v21 ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Testing NA; Upgrade of Angular Core and Dependencies | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local environment Sanity Testing | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4432415 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Local environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local environment Sanity Testing | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4432421 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Local environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local environment Sanity Testing | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4432424 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Local environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local environment Sanity Testing | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4432428 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular Upgrade Drop 3; Local environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local Environment Sanity Testing Issue Fixing | 4432415 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ Solution Components (AMS) MFE | 4434600 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing Issue Fixing ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Local Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local Environment Sanity Testing Issue Fixing | 4432421 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ Digital Documentation - MFE | 4434605 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing Issue Fixing ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Local Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local Environment Sanity Testing Issue Fixing | 4432424 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ CDAT - MFE | 4434670 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing Issue Fixing ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Local Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Local Environment Sanity Testing Issue Fixing | 4432428 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing ¦ Cost Price Engine UI | 4434697 | Technical ¦ Angular Upgrade Drop 3 ¦ Local Environment Sanity Testing Issue Fixing ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Local Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher environment Sanity Testing | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4434704 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher environment Sanity Testing | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4434712 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher environment Sanity Testing | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4434717 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher environment Sanity Testing | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4434720 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher Environment Sanity Testing Issue Fixing | 4434704 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ Solution Components (AMS) MFE | 4434726 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing Issue Fixing ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher Environment Sanity Testing Issue Fixing | 4434712 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ Digital Documentation - MFE | 4434770 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing Issue Fixing ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher Environment Sanity Testing Issue Fixing | 4434717 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ CDAT - MFE | 4434808 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing Issue Fixing ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Higher Environment Sanity Testing Issue Fixing | 4434720 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing ¦ Cost Price Engine UI | 4434845 | Technical ¦ Angular Upgrade Drop 3 ¦ Higher Environment Sanity Testing Issue Fixing ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Higher Environment Sanity Testing Issue Fixing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - New Feature implementation | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4434896 | Technical ¦ Angular Upgrade Drop 3 ¦ New Feature implementation ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; New Feature implementation; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - New Feature implementation | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4434899 | Technical ¦ Angular Upgrade Drop 3 ¦ New Feature implementation ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; New Feature implementation; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - New Feature implementation | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4434909 | Technical ¦ Angular Upgrade Drop 3 ¦ New Feature implementation ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; New Feature implementation; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - New Feature implementation | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4434912 | Technical ¦ Angular Upgrade Drop 3 ¦ New Feature implementation ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; New Feature implementation; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Functional Validation Support | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4434929 | Technical ¦ Angular Upgrade Drop 3 ¦ Functional Validation Support ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Functional Validation Support; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Functional Validation Support | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4434931 | Technical ¦ Angular Upgrade Drop 3 ¦ Functional Validation Support ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Functional Validation Support; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Functional Validation Support | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4434932 | Technical ¦ Angular Upgrade Drop 3 ¦ Functional Validation Support ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Functional Validation Support; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Functional Validation Support | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4434935 | Technical ¦ Angular Upgrade Drop 3 ¦ Functional Validation Support ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Functional Validation Support; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Supporting Regression Testing | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4434937 | Technical ¦ Angular Upgrade Drop 3 ¦ Support Regression Testing by PT Team ¦ Solution Components (AMS) MFE | Active | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Supporting Regression Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Supporting Regression Testing | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4434939 | Technical ¦ Angular Upgrade Drop 3 ¦ Support Regression Testing by PT Team ¦ Digital Documentation - MFE | Active | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Supporting Regression Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Supporting Regression Testing | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | 4434940 | Technical ¦ Angular Upgrade Drop 3 ¦ Support Regression Testing by PT Team ¦ CDAT - MFE | Active | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Supporting Regression Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Supporting Regression Testing | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4434942 | Technical ¦ Angular Upgrade Drop 3 ¦ Support Regression Testing by PT Team ¦ Cost Price Engine UI | Active | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Supporting Regression Testing; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Code merging | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | 4434944 | Technical ¦ Angular Upgrade Drop 3 ¦ Code merge ¦ Solution Components (AMS) MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Code merging; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Code merging | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | 4434947 | Technical ¦ Angular Upgrade Drop 3 ¦ Code merge ¦ Digital Documentation - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Code merging; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Code merging |  |  | 4434951 | Technical ¦ Angular Upgrade Drop 3 ¦ Code merge ¦ CDAT - MFE | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Code merging; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Angular Upgrade Drop 3 - Code merging | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | 4434954 | Technical ¦ Angular Upgrade Drop 3 ¦ Code merge ¦ Cost Price Engine UI | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular Upgrade Drop 3; Code merging; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen | MYISP_Revamp_UI_MFE_Host | 4429566 | 18th April ¦ Technical ¦ MFE Host ¦ Planned Work Intake | 4436406 | 18th April ¦ Technical ¦ MFE Host ¦ New Feature implementation | Ready for Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | MYISP_Revamp_UI_MFE_Host; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen SI | SI - PCW |  |  | 4438495 | [Analysis] API - Identify if the deal is Pure Technology Service/Capability Deal - Copy | New | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand |  |  |  |  | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen SI | PCW |  |  | 4438496 | [Analysis] API - Save the Adjustment % of Hourly Seat Charges from DNP Baseline into YoY adjustment % columns for all the Contract Years across the Deal Duration - Copy | New | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand |  |  |  |  | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen SI | SI - PCW |  |  | 4438497 | [Analysis] PCW - Add a new field in Pricing to determine if the deal is Pure Technology Service deal - Copy | New | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand |  |  |  |  | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NextGen SI | PCW |  |  | 4438498 | [Analysis] PCW - Auto-populate Local Currency in DNP sheets when Local Currency is blank - Copy | New | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | [5 empty] | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NextGen SI | PCW |  |  | 4438499 | [Analysis] PCW - Convert ACN One-time Amount (USD) to Primary (Deal) Currency during DNP Cost Calculation for 'One Time' Cost Types - Copy | New | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | [5 empty] | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen SI | PCW |  |  | 4438500 | [Analysis] PCW - IPC Toolkit Cost Update - Copy | New | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand |  |  |  |  | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NextGen SI | PCW |  |  | 4438501 | [Analysis] PCW - MMP FFP Export: Send only filtered staffing rows to API for Role Type, Accenture Role/Rate and Pricing Workstream identification - Copy | New | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | [5 empty] | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen SI | PCW |  |  | 4438502 | [Analysis] PCW - Update the FFP Roles at SSG level in Staffing Baseline - Copy | New | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand |  |  |  |  | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NextGen SI | PCW |  |  | 4438503 | [Analysis] PCW API ¦ Move Rate Card Career Level from Solution Level to Solution Version Level with One-Time Data Migration - Copy | New | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | [5 empty] | 1 | PCW; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4438718 | Technical ¦ Create AIDC Pack Overview Presentation for UI Design Pack | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439199 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export/Import status tab in Available Hours screen | Active | TechMavericks | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T16:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 15
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439323 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for Staffing | Active | TechCoders | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T16:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 17
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439343 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for PMO | Active | TechCoders | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T16:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 7
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439357 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for Staffing | Active | TechMavericks | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T17:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 7
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439362 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for PMO | Active | TechMavericks | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T17:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 10
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442689 | Technical ¦ AIDC Pack Overview Presentation for BA Pack | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442692 | Technical ¦ AIDC Pack Overview Presentation for Dev Pack | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442724 | Technical ¦ AIDC Pack Overview Presentation for Testing Pack | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442728 | Technical ¦ Figma Naming Convention Standardization (Post Update) | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442737 | Technical ¦ Image to HTML Code Generation Using Master Library | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442772 | Technical ¦ Image to HTML Code Generation Using Material Library | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442823 | Technical ¦ New Feature Implementation in Angular Upgrade Presentation | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442835 | Technical ¦ Create Expand/Collapse Plugin | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442842 | Technical ¦ New Component Generation When Not Available in Master Library | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442910 | Technical ¦ Figma to Master Library Code Generation (Component-wise) | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442968 | Technical ¦ Analyze UI Design Pack and Define Improvement Plan | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4442973 | Technical ¦ Update Master Library Instruction Files and Enable Code Generation from Figma | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 5 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Analytics | Manage screen AMS VT Report link | 4446745 | Moving current AMSVT to PBI AMSVT. | 4446747 | As a AMS VT user, I want the AMSVT production URL to be updated in the Manage screen, So that the system redirects me to the correct AMSVT Link.. | In Test | GoRetro | sowjanya.kari | sankaran.viswanathan | madhuri.chintala | Kalaivanan, Devika | 2026-04-03T21:00:00Z | 2026-04-02T11:42:00Z | 2026-04-08T18:00:00Z | 2026-04-03T17:10:00Z | 2 | CCB Approved; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446804 | LCM Infra Assessment - Questionnaire Update for Migration Type-Based Volume Selection | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446805 | SI KDA Enhancement - COTS App Replatform Support | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446806 | MMP FFP Resource Template - COTS App Replatform Handling | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 1 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446807 | PCW Integration - COTS App Replatform Support | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446808 | Reverse Order Logic - LCM Infrastructure Migration | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446809 | Reverse Order Logic Extension - LCM Infra Override | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | April MRDB | 4386335 | IMS BAU - Monthy MRDB | 4450477 | Monthly MRDB - April'26 Release | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  |  |  | 1 | IMS BAU | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | NextGen | MYISP_Revamp_UI_MFE_Host | 4310290 | Ownership & Maintenance of MFE Host Component | 4452028 | 18th April ¦ Technical ¦ MFE Host ¦ Stabilize Unit Test Cases and Maintain Code Coverage for MFE Host | New | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 3 | MYISP_Revamp_UI_MFE_Host; Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 4452428 | IPT -Support | Active | TechSprinters | mervinkumar.manickam | jayanth.kumar | madhuri.chintala |  | 2026-04-18T00:00:00Z |  |  |  | 3 | Testing NA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | DFD | DFD | 4458972 | DFD - Reinvention Partner field addition in SA request | 4458973 | As a DFD requestor, I should get a Reinvention Partner dropdown in all the SA request forms | Active | BackDoorGuardians | sona.job | c.dhiman | madhuri.chintala | Jain, Himanshu | 2026-04-10T18:00:00Z |  | 2026-04-10T18:00:00Z |  | 5 | CCB Approved; Po Input | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 25
Platform Consolidation | DFD | DFD | 4458972 | DFD - Reinvention Partner field addition in SA request | 4458985 | AS a DFD requestor, I should get Reinvention partner field value in the existing SA requests | Active | BackDoorGuardians | sona.job | c.dhiman | madhuri.chintala | Jain, Himanshu | 2026-04-10T18:00:00Z |  | 2026-04-10T18:00:00Z |  | 3 | CCB Approved; Po Input | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 34
Platform Consolidation | DFD | DFD | 4458972 | DFD - Reinvention Partner field addition in SA request | 4458995 | As a DFD requestor, I should get Reinvention Partner field in SA mail templates when request is created/edited | Active | BackDoorGuardians | sona.job | c.dhiman | madhuri.chintala | Jain, Himanshu | 2026-04-10T18:00:00Z |  | 2026-04-10T18:00:00Z |  | 3 | CCB Approved; Po Input | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 32
Platform Consolidation | Analytics | PMO reporting Layer | 4458987 | Addition of "Mergers and Acquisitions" column in PMO Reporting layer | 4459023 | As a user of the PMO Reporting layer report, I want to add a new column as "Mergers and Acquisitions" in report, so that I can see the newly added column data directly in the report. | Ready for Test | Cognilytics | anil.kadiri | vishnupriya.aluru | srinivasan.ks | Kalaivanan, Devika | 2026-04-07T21:00:00Z |  | 2026-04-10T00:00:00Z |  | 4 | CCB Approved; Po Input; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rapid Soln | NextGen | Angular upgrade - Agentic AI |  |  | 4462085 | Technical ¦ Generate Angular Code from Design System (POC) | Closed | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks |  | 2026-04-07T00:00:00Z |  |  |  | 2 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; Testing NA; UAT Testing Not Required | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Testable stories
mySP Initiative | Sub Initiative | TextVerification | Parent | Parent Title | ID | Title | State | Node Name | M POC | SM POC | AD POC | Testing POC | Planned for PT Date | Actual PT Date | Planned UAT Date | Actual UAT Date | Story Points | Tags | Testing NA stories | PT testable stories | UAT Testable Stories | UAT Testing NA stories | PT delivered | PT NOT delivered | UAT delivered | UAT NOT delivered | Passed | Failed | Blocked | Not Run | Total | Execution % | Pass %
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359188 | As a SA,I want the Profile city Tier field to auto-populate from the Rate Type column in the Staffing Baseline screen | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T18:00:00Z |  | 3 | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 25 | 0 | 0 | 10
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359294 | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-23T14:57:00Z | 2026-03-23T00:00:00Z | 2026-04-08T00:00:00Z |  |  | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 5 | 0 | 0 | 5
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359328 | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T00:00:00Z |  | 5 | Field Management; Profile Screen; Role Type; Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 20 | 5 | 0 | 26
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4359507 | As a SA I want to select standard role from an SSG-specific dropdown selection | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T00:00:00Z |  | 7 | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 28 | 0 | 0 | 10
Rapid Soln | NextGen | DCSO | 4278081 | myISP - Digital DCSO | 4362582 | As a myisp Solution Architect, I want the DCSO tab to be removed from the SI KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | PT In Test | Insurgents | K.devaraj | vishnupriya.aluru | srinivasan.ks | Vv, Shini | 2026-04-06T12:00:00Z | 2026-04-03T11:20:00Z | 2026-04-09T00:00:00Z |  | 2 | Autocreate; DCSO | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0
Rapid Soln | NextGen | DCSO | 4278081 | myISP - Digital DCSO | 4362592 | As a myisp Solution Architect, I want the DCSO tab to be removed from the AMS KDA/Reports screen So that users do not access or generate DCSO information from the KDA / Reports interface. | PT In Test | Insurgents | K.devaraj | vishnupriya.aluru | srinivasan.ks | Vv, Shini | 2026-04-06T12:00:00Z | 2026-04-03T11:20:00Z | 2026-04-09T00:00:00Z |  |  | Autocreate; DCSO | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 0
Platform Consolidation | NextGen SI | PCW | 4389877 | MMP FFP Export update - April release | 4368135 | API - Enhance the defaulting logics to populate 'Accenture Role/Rate' in offline MMP FFP Export | UAT In Test | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-04-01T20:00:00Z | 2026-04-02T12:38:00Z | 2026-04-03T00:00:00Z | 2026-04-06T16:10:00Z | 3 | parallel testing; Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 1
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4368224 | API - Save the Technology Tier, Profile City Tier, Role Type, Technology Role and Standard Role from Staffing Baseline | UAT In Test | TechAvatar | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-23T18:36:00Z | 2026-04-03T00:00:00Z | 2026-04-06T15:53:00Z | 5 | PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 6 | 2 | 0 | 2
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4368812 | As a SA, add Role Type field in Staffing Baseline (auto-populated from Std Location Type & Service Group) - OU changes | PT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-08T18:00:00Z |  | 13 |  | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 15 | 3 | 0 | 24
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4368862 | As a SA I want to select standard role from an SSG-specific dropdown selection- OU changes | UAT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-07T10:57:00Z | 13 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 5 | 0 | 0 | 3
Rapid Soln | NextGen SI | SDL | 4277501 | Standard Role Implementation in SI Staffing Baseline - Analysis | 4371046 | As a Solution Architect, I want to see dynamic target pricing parameters in SDL SI DL regardless of rate card configuration | UAT In Test | DevStormers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T12:17:00Z | 1 | April-2026; Enhancement; Export; parallel testing; reporting; SDL; SI-DL; Staffing | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 7 | 1 | 0 | 3
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4372847 | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG. | UAT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-06T16:23:00Z | 5 | parallel testing; Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 8 | 8 | 0 | 8
Rapid Soln | DCTA | SI DCTA | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4377948 | As a myISP SA, I want to add new columns in the DCTA JSON file so that dynamic target pricing can be computed | PT In Test | TechSprinters | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-09T00:00:00Z |  | 5 | Standard Role Configuration | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 7 | 0 | 0 | 20
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4381707 | PCW - Add Technology Role and Standard Role Column in Staffing Baseline to populate the Roles of SI, CON-CAS | Blocked in PT | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-03T00:00:00Z |  | 7 | PCW | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 8 | 3 | 3 | 0
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386371 | PCW - Add Role Type Column in Staffing Baseline to populate the Role Types for SI, CON-CAS, AMS, IMS and BPMS | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-07T14:25:00Z | 5 | Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 9 | 0 | 0 | 4
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386372 | PCW - Add Profile City Tier Column in Staffing Baseline to populate the Profile City Tier value for all profiles | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-06T12:56:00Z | 3 | PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 20 | 0 | 0 | 0
Platform Consolidation | NextGen | SI - PCW | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386373 | PCW - Rename existing 'Role Type' column in PCW 8.7 Template and Show a warning message in PCW 8.6 template | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-31T20:00:00Z | 2026-03-20T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T13:06:00Z | 2 | Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 11 | 1 | 0 | 0
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386942 | As a SA, I want the Technology Tier field to auto-populate based on the selected Technology - OU Changes | UAT In Test | TechAvengers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T15:57:00Z | 5 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 7 | 1 | 0 | 0
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386944 | As a SA, auto-populate Profile City Tier from Rate Type in Staffing Baseline-OU Changes | UAT In Test | TechAvengers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-07T10:55:00Z | 3 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 9 | 0 | 0 | 0
Rapid Soln | NextGen SI | STD Role | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4386945 | As a SA, add Technology & Standard Role columns in Staffing Baseline for auto-population/selection based on Tech Group & SSG.- OU changes | UAT In Test | TechWizards | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-06T00:00:00Z | 2026-04-06T19:12:00Z | 5 | parallel testing | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 16 | 6 | 0 | 4
Rapid Soln | NextGen SI | MMP FFP | 4389877 | MMP FFP Export update - April release | 4391224 | As a myISP SA, I want to change the logic to populate "Role Type" and "Accenture Role/Rate" in MMP FFP so that it is aligned with Dynamic Target Pricing implementation | UAT In Test | DevStormers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-07T18:00:00Z | 2026-04-07T16:58:00Z | 1 | Parallel UAT | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 11 | 7 | 0 | 9
Rapid Soln | DCTA | SI DCTA | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4393527 | As a myISP SA, I want to apply filter FFP Visible = False in addition to other filters while displaying Standard Role in staffing so that it is aligned with MMP standards | PT In Test | TechSprinters | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | Selvamani, Kavichandrika | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-09T00:00:00Z |  | 5 |  | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 13 | 0 | 0 | 14
Platform Consolidation | NextGen SI | PCW | 4389877 | MMP FFP Export update - April release | 4395067 | PCW - Pass Role Type column to API as an input filter parameter for defaulting logics of offline MMP FFP Export | UAT In Test | Tech Ensemble | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-04-01T20:00:00Z | 2026-04-02T12:39:00Z | 2026-04-03T00:00:00Z | 2026-04-06T16:10:00Z | 3 | parallel testing; Parallel UAT; PCW | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 8 | 0 | 0 | 2
Platform Consolidation | NextGen | Online SI | 4373911 | Standard Role Implementation in PCW & Online SI - April Release | 4411451 | Rename existing 'Role Type' column in Staffing OU Template | UAT In Test | TechAvengers | mervinkumar.manickam | jayanth.kumar | madhuri.chintala | B Gadad, Anand | 2026-03-20T00:00:00Z | 2026-03-23T00:00:00Z | 2026-04-03T00:00:00Z | 2026-04-06T10:38:00Z | 3 |  | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 3 | 0 | 0 | 0
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429413 | As a myISP Solution Architect, I want to see the Solution Components (AMS) MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Krishnan, Pirtheebaa | 2026-04-02T14:56:00Z | 2026-04-02T19:00:00Z |  |  | 3 | Angular upgrade v19 to v21; PT Regression; Solution Components (AMS)-MFE; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 20 | 0 | 0 | 0
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429519 | As a myISP Solution Architect, I want to see the Digital Documentation - MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Das, Leena | 2026-04-02T14:54:00Z | 2026-04-02T00:00:00Z | 2026-04-03T13:23:00Z | 2026-04-03T13:23:00Z | 3 | Angular upgrade v19 to v21; Digital Documentation - MFE; PT Regression; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 6 | 0 | 0 | 4
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429521 | As a myISP Solution Architect, I want to see the CDAT - MFE App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Kalia Moorthy, Rajarajeswari | 2026-04-02T14:54:00Z | 2026-04-02T17:18:00Z |  |  | 3 | Angular upgrade v19 to v21; CDAT - MFE; PT Regression; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 28 | 0 | 0 | 12
Rapid Soln | NextGen | Drop 3 - Angular upgrade v19 to v21 | 4429397 | Angular upgrade version 19 to version 21 - 18th April | 4429530 | As a myISP Solution Architect, I want to see the Cost Price Engine UI App migrated to Angular 21 | PT In Test | MYISP_Revamp_UI | vikrant.r.mohite | mahesh.kt | srinivasan.ks | Damodaran, J. | 2026-04-02T14:56:00Z | 2026-04-02T17:14:00Z | 2026-04-10T00:00:00Z |  | 3 | Angular upgrade v19 to v21; Cost Price Engine UI; PT Regression; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 13 | 0 | 0 | 4
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439199 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export/Import status tab in Available Hours screen | Active | TechMavericks | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T16:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 15
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439323 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for Staffing | Active | TechCoders | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T16:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 17
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439343 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Export option in Available Hours template for PMO | Active | TechCoders | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T16:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 7
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439357 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for Staffing | Active | TechMavericks | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T17:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 7
Rapid Soln | OCP | AMS | 4439196 | Available Hours OU Report | 4439362 | AMS OCP/DCTA: As a mySolutionPlanner developer, I should be able to get the Import option in Available Hours template for PMO | Active | TechMavericks | Francis.Deepak | vishnupriya.aluru | srinivasan.ks | Damodaran, J. | 2026-04-08T17:30:00Z |  | 2026-04-08T19:00:00Z |  | 3 | CCB Approved | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 10
Platform Consolidation | Analytics | Manage screen AMS VT Report link | 4446745 | Moving current AMSVT to PBI AMSVT. | 4446747 | As a AMS VT user, I want the AMSVT production URL to be updated in the Manage screen, So that the system redirects me to the correct AMSVT Link.. | In Test | GoRetro | sowjanya.kari | sankaran.viswanathan | madhuri.chintala | Kalaivanan, Devika | 2026-04-03T21:00:00Z | 2026-04-02T11:42:00Z | 2026-04-08T18:00:00Z | 2026-04-03T17:10:00Z | 2 | CCB Approved; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446804 | LCM Infra Assessment - Questionnaire Update for Migration Type-Based Volume Selection | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446805 | SI KDA Enhancement - COTS App Replatform Support | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446806 | MMP FFP Resource Template - COTS App Replatform Handling | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 1 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446807 | PCW Integration - COTS App Replatform Support | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446808 | Reverse Order Logic - LCM Infrastructure Migration | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | LCM COTS Enhancements | 4386341 | LCM Infra - COTs App Replatform | 4446809 | Reverse Order Logic Extension - LCM Infra Override | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  | 2026-04-10T00:00:00Z |  | 2 | IMS BAU; UAT Testing Not Required | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | Inspire | April MRDB | 4386335 | IMS BAU - Monthy MRDB | 4450477 | Monthly MRDB - April'26 Release | Active | myISP_IMS | supriya.a.dhingra | rajaraman.mahalingam | Rajsingh.rajput | Srinivasan, Vaidheki | 2026-04-07T00:00:00Z |  |  |  | 1 | IMS BAU | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Platform Consolidation | DFD | DFD | 4458972 | DFD - Reinvention Partner field addition in SA request | 4458973 | As a DFD requestor, I should get a Reinvention Partner dropdown in all the SA request forms | Active | BackDoorGuardians | sona.job | c.dhiman | madhuri.chintala | Jain, Himanshu | 2026-04-10T18:00:00Z |  | 2026-04-10T18:00:00Z |  | 5 | CCB Approved; Po Input | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 25
Platform Consolidation | DFD | DFD | 4458972 | DFD - Reinvention Partner field addition in SA request | 4458985 | AS a DFD requestor, I should get Reinvention partner field value in the existing SA requests | Active | BackDoorGuardians | sona.job | c.dhiman | madhuri.chintala | Jain, Himanshu | 2026-04-10T18:00:00Z |  | 2026-04-10T18:00:00Z |  | 3 | CCB Approved; Po Input | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 34
Platform Consolidation | DFD | DFD | 4458972 | DFD - Reinvention Partner field addition in SA request | 4458995 | As a DFD requestor, I should get Reinvention Partner field in SA mail templates when request is created/edited | Active | BackDoorGuardians | sona.job | c.dhiman | madhuri.chintala | Jain, Himanshu | 2026-04-10T18:00:00Z |  | 2026-04-10T18:00:00Z |  | 3 | CCB Approved; Po Input | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 32
Platform Consolidation | Analytics | PMO reporting Layer | 4458987 | Addition of "Mergers and Acquisitions" column in PMO Reporting layer | 4459023 | As a user of the PMO Reporting layer report, I want to add a new column as "Mergers and Acquisitions" in report, so that I can see the newly added column data directly in the report. | Ready for Test | Cognilytics | anil.kadiri | vishnupriya.aluru | srinivasan.ks | Kalaivanan, Devika | 2026-04-07T21:00:00Z |  | 2026-04-10T00:00:00Z |  | 4 | CCB Approved; Po Input; UAT Testing Not Required | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Consolidated PT_UAT Status
Parent ID | Parent Title | Product Owner | Total PT stories | PT Delivered | PT Not Delivered | PT Execution% | PT Pass% | Total UAT stories | UAT Delivered | UAT Not Delivered | UAT Execution% | UAT Pass% | Total Open Bugs for Parent ID | Critical | High | Medium | Low
4277501 | Standard Role Implementation in SI Staffing Baseline - Analysis | prema.ponnurangam | 1 | 1 | 0 | 72.73% | 87.5% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0
4278081 | myISP - Digital DCSO | rinil.jose | 2 | 2 | 0 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0
4373911 | Standard Role Implementation in PCW & Online SI - April Release | prema.ponnurangam and rinil.jose | 18 | 18 | 0 | 72.37% | 88.74% | 0 | 0 | 0 | 0% | 0% | 15 | 0 | 3 | 10 | 2
4386335 | IMS BAU - Monthy MRDB | srividhya.ls | 1 | 0 | 1 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0
4386341 | LCM Infra - COTs App Replatform | srividhya.ls | 6 | 0 | 6 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 5 | 0 | 0 | 5 | 0
4389877 | MMP FFP Export update - April release | prema.ponnurangam and shampa.pal | 3 | 3 | 0 | 71.11% | 87.04% | 0 | 0 | 0 | 0% | 0% | 2 | 0 | 1 | 1 | 0
4429397 | Angular upgrade version 19 to version 21 - 18th April | mahesh.kt | 4 | 4 | 0 | 76.62% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0
4439196 | Available Hours OU Report | pooja.balani | 5 | 0 | 5 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0
4446745 | Moving current AMSVT to PBI AMSVT. | pooja.balani | 1 | 1 | 0 | 100% | 100% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0
4458972 | DFD - Reinvention Partner field addition in SA request | aditi.b.deshpande | 3 | 0 | 3 | 0% | 0% | UAT NOT Applicable | UAT NOT Applicable | UAT NOT Applicable | UAT NOT Applicable | UAT NOT Applicable | 0 | 0 | 0 | 0 | 0
4458987 | Addition of "Mergers and Acquisitions" column in PMO Reporting layer | neelam.j.mohite | 1 | 1 | 0 | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0