## Bug Summary
ID | Title | Severity | Node Name | AD POC | SM POC | M POC | Defect Record | TextVerification | State | StageFound
4150441 | Oct 11th_PT/UAT¦CDAT Gen AI¦IMS¦ When contract or solution plan reference added does not have adequate details for selected nudge, then in findings incorrect result is displayed | 3 - Medium | GENAI-CDAT | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4103302 | GEN AI | Deferred | Product Test
4186269 | 8th Nov ¦ UAT1 ¦ PCW ¦ ONLINE SDL ¦ Fixed cost types ¦ When the Calculation criteria is blank and not matching with Staffing baseline -ATCP/ATC Mobilization Support fixed cost type is not flowing to online SDL | 2 - High | DevStormers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4151999 | PCW | Ready to Deploy | User Acceptance Test
4316849 | Suggestion¦ Jan 10th ¦ UAT¦ Mobilization Calculator¦ Bottom Up¦ Under Wave Mapping , in Map groups & Waves total FTE row, Mapped , Unmapped groups should display as per Figma | 3 - Medium | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | Regression | Mobilization Calculator | Blocked in UAT | User Acceptance Test
4341461 | AI Foundry _SSA_ US-4330655_ UAT_ Export OU File is not appearing in the Output Summary for Deal-wide Pricing. | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4319023 | AMS Solution Configuration Agent | Active | Product Test
4363137 | Tracking - Feb 21st ¦ PT ¦ SA Team Manger ¦ The Font for SA Team Manager is Maximized | 3 - Medium | GoRetro | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4336238 | SA Team Manager | Ready to Deploy | Product Test
4373531 | Regression : UAT__AI-Foundry___Prompt Library___Sustainability section should not be green as No cost is selected for its version | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | Solution Agent AMS | Blocked in UAT | User Acceptance Test
4383717 | Pilot user bug_Feb 21st¦ UAT1¦ Mobilization Calculator¦ Bottom Up¦ For Subcontractor Profiles, FTES are not displaying in wave mapping | 2 - High | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | Prod user bug | Mobilization Calculator | Active | User Acceptance Test
4386496 | Feb 21¦¦ Prod Sanity ¦¦ PLD ¦¦ Hyphen is displaying in client name column in unassigned/assigned grid for cross service lead | 3 - Medium | Pacemakers | madhuri.chintala | c.dhiman | sona.job |  | PLD | Deferred | Product Test
4398595 | ¦¦ Prod ¦¦ March 14th ¦¦ DSP _ UI issue in Cost Assumptions PPT/PDF | 3 - Medium | Ninjawarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Prod Bug | DSP | Active | Product Test
4409942 | Regression ¦Pilot User¦ : UAT__AI-Foundry__Facing multiple issues during deal configuration | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Solution Configuration Agent | Active | User Acceptance Test
4415534 | March 28} UAT¦ UI Issues in SVC | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | Active | Product Test
4421616 | Mar 28 ¦ GenAI-PT- S2C¦ Image is coming in response and blank screen in UI for S2C Nudge | 3 - Medium | AAME - S2C |  |  |  | User story |  | Deferred | Product Test
4425443 | UAT__AI--Foundry___Groups: Agent is not throwing any warning after importing Groups with Service types having mismatched Contract Offering as mentioned in User story. | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Active | User Acceptance Test
4425577 | March 28th_UAT2_MDA_IMS_DNP_Deal Pivot_Getting data mismatch in DNP Cost by Phase/Country tab | 2 - High | SolutionDataLake | srinivasan.ks | vishnupriya.aluru | vishal.v.nadpurohit | 4356899 | DNP Deal Pivot | Active | Product Test
4425603 | UAT____AI Foundry_Default profiles not getting added for Turkey but Agent shows as data saved successfully | 4 - Low | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4390112 | AMS Solution Configuration Agent | Active | User Acceptance Test
4431144 | March 28th_UAT2_MDA_IMS_DNP_Deal Pivot_Getting data mismatch in DNP Cost by SD - Tools and Connectivity Details. | 2 - High | SolutionDataLake | srinivasan.ks | vishnupriya.aluru | vishal.v.nadpurohit | 4356899 | DNP Deal Pivot | Active | User Acceptance Test
4432440 | UAT____AI Foundry_SC004 Costing: Agent is not giving proper validation when trying to import incorrect file. | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Active | User Acceptance Test
4435161 | Mar 28 ¦ SI ¦ PT & UAT ¦ AEP Refresh ¦¦ Tax Input screen¦¦ Under Subcontractors post saving, grid getting blinking and Nature of work dropdown selection column also working slowly. | 3 - Medium | DevStormers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4139936 | myISP | Active | Product Test
4435622 | Existing prod issue ¦ Mar28th_UAT2_MDA_AMS_HC/PY_Mobilization values are not flowing in the table for AMS MMP route. | 3 - Medium | SolutionDataLake | srinivasan.ks | vishnupriya.aluru | vishal.v.nadpurohit | 4368157 | AMS MMP | Active | myI_Production-Beta
4438224 | 28th Mar ¦¦ PT and UAT2 ¦¦ Other SG Version Dropdown Disabled for below IMS roles | 2 - High | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj |  | DCSO | Deferred | Product Test
4439689 | 28th March: SSA: Response is inconsistent | 2 - High | GEN AI - Solution Super Agent | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Regression | Gen AI | Active | User Acceptance Test
4439981 | UAT___AI-Foundry____ PMO export is not available in prompt response and also not getting navigation hyperlink for the version | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution configuration Agent | Active | User Acceptance Test
4440949 | Regression : UAT___AI--Foundry____Profiles : Import profile shows profiles added successfully but no changes in UI | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Solution Configuration Agent | Active | User Acceptance Test
4441769 | 28th March ¦ UAT2 ¦ DCSO ¦ IMS ¦ SI Version dropdown is enabled in IMS single tower deal | 3 - Medium | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj | 4278081 | DCSO | Deferred | User Acceptance Test
4443431 | 28th March PT ¦ DCSO ¦ File Tampering Error multiple issues | 3 - Medium | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj | 4278081 | DCSO | Resolved | Product Test
4443599 | UAT___AI--Foundry___PMO: Agent is not throwing proper validation if PMO exported file is imported without profile column | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Active | User Acceptance Test
4443608 | 9 May ¦ UAT2 ¦ Value Shaping ¦ User configured data in Configurator and in calculation's given SOP text as "XX" then SOP value is SVP is coming two times which is not expected | 3 - Medium | Spartans | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | Regression | Value Shaping | Active | Regression Test
4443706 | Mar 28 ¦ UAT ¦ Agent AI Foundry ¦ NRR Export downloads Enterprise ID Template instead of NRR | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Active | Product Test
4444295 | Mar 28 ¦ UAT ¦ Agent AI Foundry ¦ Resource Type is not getting added by default for profiles added via NRR | 4 - Low | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Active | Product Test
4444999 | March 28th¦UAT2¦ Value Shaping ¦ SVP¦ Getting different Size of Prize Inputs in summary screen when compared to SOP inputs in Tag KPI & Add details | 3 - Medium | Spartans | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | Regression. | Value Shaping | Ready to Deploy | User Acceptance Test
4445150 | Regression ¦ UAT___AI__Foundry____Pricing input : Custom Infra Cost Shows All Locations Instead of USA-Specific Data. | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Refactoring Scope | Active | User Acceptance Test
4445840 | Regression ¦ 28th March ¦ UAT2 ¦ DCSO ¦ SI ¦ Staffing Inventory not matching in UI with Generated DCSO Template. | 4 - Low | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj | Regression | DCSO | Deferred | User Acceptance Test
4446233 | Mar28th ¦ Regression ¦ UAT2 ¦ MDA ¦ AMS ¦ HC/PY_Mobilization values are not flowing in the table for AMS OCP route | 3 - Medium | SolutionDataLake | srinivasan.ks | vishnupriya.aluru | vishal.v.nadpurohit | Regression | AMS OCP | Active | User Acceptance Test
4446864 | Mar 28¦¦ Prod Sanity ¦¦ PLD ¦¦ Read more is appearing unnecessarily when we added even a single small comment | 4 - Low | Pacemakers | madhuri.chintala | c.dhiman | sona.job |  | PLD | Deferred | Sanity Testing
4446909 | SRA ¦ Mar 28 ¦ Opportunity context data ¦ DLC canvas ver Data in SRA mistmatch with DLC context in myisp | 3 - Medium | Gen AI - Solution Review Agent | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar |  |  | Active | Production
4446918 | Mar 28 ¦ Prod Sanity ¦ Gen AI ¦ YOY Gen AI Productivity and Agents Embedded in Solution 4th Year columns not getting displayed in Gen AI with values. | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Sanity | AMS Solution Configuration Agent | Ready to Deploy | Product Test
4446921 | Mar 28¦¦ Prod Sanity ¦¦ AI--Foundry ¦¦ Groups: group import is getting failed and not all details are getting updated based in imported file | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4318876 | AMS Solution Configuration Agent | Active | User Acceptance Test
4446940 | Mar 28 ¦ Prod Sanity ¦ Agent AI Foundry ¦ Import Costing PMO Is not working Agent shows Imported Successfuly but not refelecting in UI. | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Sanity | AMS Solution Configuration Agent | Active | User Acceptance Test
4448165 | Mar28 ¦¦ Prod Sanity ¦¦ MDA: Few Sub-services of Transition>Mobilization is not flowing in IMS Pyramid Deal Pivot report | 3 - Medium | SolutionDataLake | srinivasan.ks | vishnupriya.aluru | vishal.v.nadpurohit | 4356899 | MDA | Active | Product Test
4461683 | May 9 PT ¦¦ Copy/Cart/AEP Version Status screen ¦¦ Copy and Cart version status struck st Queued. | 2 - High | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Sanity | myISP | Re-open | Product Test
4462269 | Gen AI ¦¦ OBM ¦¦ Feedback buttons for Gen AI Insights missing | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Regression | Gen AI | Active | User Acceptance Test
4462273 | Gen AI ¦¦ OBM ¦¦ Blinking Notification for Service Group(s) | 4 - Low | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Regression | Gen AI | Active | User Acceptance Test
4464475 | Apr 18 ¦ UAT ¦ OBM ¦ SVC ¦ Cost and Metrics at Glance - Response Issue | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | OBM | Active | Product Test
4464985 | OBM ¦PROD validation ¦ PBI column width is not uniform | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | Re-open | Product Test
4465805 | May 9_UAT_DSP_Staffing plan_Data is not displaying in staffing plan screen | 2 - High | NinjaWarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Sanity | DSP | New | Product Test
4465936 | 18th Apr ¦UAT ¦ SI ¦ The Role type is populating for other SSG which is not mentioned in the Role type sheet | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD Role | Ready to Deploy | Product Test
4466178 | 18 Apr_UAT_SI_Staffing Baseline_Staffing OU _Facing performance issue in Staffing Import and Export | 3 - Medium | TechWizards | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | NextGen SI | Active | Product Test
4466857 | 18th April¦ UAT ¦ SI ¦ For applicable SG and Technology "Technology Role" is not highlighting in Amber and without configuring "Technology Role" Screen is getting saved in Staffing Baseline | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD Role | Deferred | User Acceptance Test
4467554 | 18th Apr ¦UAT ¦ SI ¦Role type values are not populating as per staffing baseline Screen in MMP FFP Template | 2 - High | DevStormers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4389877 | MMP FFP | Active | Product Test
4467592 | Apr 18 ¦ UAT 2¦ OBM ¦ 0’ value is impacting the average Onshore LCR | 1 - Critical | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | OBM | BA clarification | Product Test
4468466 | May ¦ UAT ¦ BPMS ¦ Estimators/Calculators ¦ Calculators ¦ Calculator issue | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | Sanity | Mobilization Calculator | Active | Sanity Testing
4470171 | May 9_UAT_DSP_Assessment outcome is getting blank | 3 - Medium | NinjaWarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Sanity | DSP | New | Product Test
4470251 | 18th April ¦ UAT ¦ AMS-Available Hours ¦ Update for subcontractor profiles in excel is not working as expected | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Active | User Acceptance Test
4471485 | 18th Apr ¦ UAT ¦ AMS - Available Hours ¦ Not getting any validation error for staffing profiles on UI if imported with zero and more than max monthly limit values | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Ready to Deploy | User Acceptance Test
4471493 | 18th April¦ UAT ¦ SI/PCW DCTA ¦ Standard Role and Role Type values are not flowing to MMP Griddy | 2 - High | TechSprinters | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | SI DCTA | Active | User Acceptance Test
4471941 | May 9 ¦ SI ¦ PT & UAT ¦ Staffing Baseline ¦ Save Functionality is not working as expected | 2 - High | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Sanity | MyISP | Blocked | Product Test
4472637 | 18th Apr ¦ UAT ¦ AMS - Available Hours ¦ Not getting re-export validation in available hours screen when importing old file after some updates in version. | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Ready to Deploy | User Acceptance Test
4473186 | Regression ¦ AI Foundry ¦ April UAT ¦ Exported staffing file is not available in UI | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | Regression | AMS Solution Configuration Agent | Active | Product Test
4473691 | May 9 ¦¦ PT/UAT ¦¦ S&C ¦¦ After creating versions in S&C calculator versions are not Displaying in Dashboard Tab. | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4341384 | VRO,PVE,PM | New | Product Test
4475130 | 18th April ¦ UAT ¦ AMS-Available Hours ¦ In Validation error total row count and total success count is showing incorrect and under status 'Error ' text is different for two different messages. | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Blocked in PT | Product Test
4475221 | May 9th ¦ PT ¦ Attach Calculator ¦ Choose columns filter in only working on double click. | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Attach Calculator | Active | Product Test
4475886 | May 9th¦ Stage & UAT ¦BPMS¦ UI Alignment Issues in Year-on-Year Productivity Table (Generative AI Tab – Reporting & Compliance, Review Approval) | 3 - Medium | BPMSBloggers | madhuri.chintala | c.dhiman | sona.job | 4437428 | BPMS Onboarding | Ready to Deploy | Product Test
4476258 | 18th April¦ UAT ¦ SI ¦ "Role Type" is not auto populating in existing deals | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4373911 | STD Role | Active | User Acceptance Test
4476439 | SUGGESTION_May 9_PT_DLC_DSP versions are not in order | 4 - Low | NinjaWarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Sanity | DLC | New | Product Test
4477418 | May 9th ¦ DFD ¦ The Icons are not getting displayed for BPMS SG under Actions in Assigned Tab for Super User Access, central PMO and Service Level PMO Access | 3 - Medium | BackDoorGuardians | madhuri.chintala | c.dhiman | sona.job | 4440976 | DFD | Blocked | Product Test
4478308 | 18th Apr ¦ UAT ¦ AMS - Available Hours ¦ The yellow color in the exported file do not match and All columns should be adjustable like staffing export. | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Ready to Deploy | User Acceptance Test
4479040 | 18th April ¦ UAT ¦ AMS-Available Hours ¦ In Validation error total row count and total success count is showing incorrect for interim deal. | 4 - Low | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Active | Product Test
4479126 | Regression ¦ AI Foundry ¦ April UAT ¦ OCP is not getting initiated | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Solution Configuration Agent | Blocked in PT | Product Test
4480748 | 18th Apr ¦ UAT ¦ AMS - Available Hours ¦ Latest imported file status is showing incorrect for PMO in UI. | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Re-open | Product Test
4481355 | Regression ¦ AI Foundry ¦ April UAT ¦ Sustainability details not getting saved in UI | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Solution Configuration Agent | Active | Product Test
4482047 | Query ¦ SI ¦Profiles ¦ May_9th ¦ SI Profiles popup size is excessively large even for minimal data | 4 - Low | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam |  | Solution Components | Ready to Deploy | Product Test
4482151 | May 9th ¦ PT ¦ Attach Calculator ¦ Alignment of Versions is not as shown in VD. | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Attach Calculator | Ready to Deploy | Product Test
4482269 | Apr 18 ¦ UAT 2¦ OBM ¦ Update/Refresh functionality is not working as Expected | 2 - High | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Regression | QDI | New | Product Test
4482275 | Regression: 18th Apr ¦ UAT ¦ AI - Foundry ¦ Agent is not able to apply correct productivity for 1st year | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Regression | AMS Solution Configuration Agent | Re-open | User Acceptance Test
4482797 | 9 May_UAT1_PCW_ Offline version_DNP Screen , in Master costs tab , Cost category is coming as Tools and Assets cost for all the IPC cost types | 3 - Medium | BA Support | arul.vasu | arul.vasu | varsha.b.rani | 4341363 | NextGen SI | Active | Product Test
4483058 | May 9 ¦¦ May PT ¦¦ Page keep on loading when navigated on Value Narrative & getting toaster message as not able to generate the response. | 2 - High | Gen AI - Solution Review Agent | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4420081 | Gen-AI | Active | Product Test
4483520 | 18th April ¦ UAT ¦ AMS-Avl Hours ¦ Import is getting completed with invalid data for staffing. | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Active | Product Test
4483674 | May 9th ¦ PT ¦ Attach Calculator ¦ The cost is coming up as 0K on click on edit icon in attach calculator screen | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Attach Calculator | Active | Product Test
4483795 | 09th May ¦ AMS ¦ PT ¦ Attach Calculator ¦ Facing multiple UI issues in Attach Calculator screen. | 4 - Low | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372017 | Differentiation | Active | Product Test
4484397 | UAT2_OBM/SVC_Latest Tag issue _ All SG | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4373741 | GEN AI | Deferred | Product Test
4484556 | May 9 ¦¦ May PT¦¦ Response is not matching with DB response for Dependencies nudge question. | 3 - Medium | Harvesting solutionPlan | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | User story |  | New | Production
4485117 | May 9 ¦¦ May PT¦¦ Response is not generating SG Wise for all the nudges | 3 - Medium | Harvesting solutionPlan | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | User story |  | New | Production
4485460 | May9th ¦¦ UAT1 ¦¦ IMS MMP Pricing Status struck at SFP | 2 - High | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4440653 | IMS | Active | Product Test
4485493 | May 9th ¦¦ Prod ¦¦ DSP_Transition Overview_UI related PPT/PDF issue | 3 - Medium | Pixel Pioneers | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Prod Bug | DSP | Active | Product Test
4485751 | Apr 18¦ OBM & SVC¦DCTA¦ Data is not flowing in AMS for newly generated KDA | 2 - High | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Regression | GEN AI | Deferred | Product Test
4485814 | OBM_ UAT_ LLM insights not meaningful | 2 - High | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Regression | Gen AI | Active | User Acceptance Test
4485816 | OBM_ UAT_Read More / Read Less | 4 - Low | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Regression | Gen AI | New | User Acceptance Test
4486012 | May 09 ¦ Stage/UAT1 ¦ Value Shaping ¦ Duplicate KPIs are reflecting in KPI dropdown in SVP | 4 - Low | Spartans | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4446213 | Value Shaping | Active | Product Test
4486067 | MAY PT ¦ OCP-SI user story ¦ group screen issue 1 | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra |  |  | Active | Product Test
4486106 | 18th April ¦ UAT ¦ AMS-Available Hours ¦ Regression ¦ On changing default value from "No " to " yes " existing monthly values are getting retained for PMO on import | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | Regression | AMS | Active | User Acceptance Test
4486114 | May9th ¦¦ UAT1 ¦¦ MDA: IMS MMP: Getting POTE group which is not available in MMP View KDA Group | 3 - Medium | Simulators | srinivasan.ks | vishnupriya.aluru | K.devaraj | 4440653 | MDA | BA clarification | Product Test
4486257 | MAT PT/UAT ¦ AMS/SI/IMS ¦ DCSO ¦ For Extension deal and Mergers and Acquisitions deal publish icon shouldn't enable | 3 - Medium | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj | 4420374 | DCSO | Resolved | Product Test
4486361 | 18th April ¦¦ UAT ¦¦ Regression ¦¦ AMS-Available Hours ¦¦ Unable to import staffing and PMO file, OK button is not clickable. | 2 - High | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | 4439196 | AMS | Active | Regression Test
4486499 | May 9 ¦ PT ¦ SRA ¦ Total no. of questions are not increasing in agent info pane for Review Agent | 3 - Medium | GEN AI - Solution Super Agent | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | 4287584 | Gen AI | Ready to Deploy | Product Test
4486529 | May 9th ¦ UAT1 ¦ Review Approvals ¦ List of Reviewer roles not loading properly for BPMS SG | 3 - Medium | BPMSBloggers | madhuri.chintala | c.dhiman | sona.job | 4437646 | Reviewer Approver | Active | User Acceptance Test
4486874 | May 9 ¦¦ May PT ¦¦ Unable to see Deal Level Canvas header in downloaded PPT/PDF/other template decks/All output documents for all SG's | 3 - Medium | Ninjawarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | 4437844 | DSP | Ready to Deploy | Product Test
4487077 | May 9 ¦¦ May PT ¦¦ Able to see both DLC & SGC in Agenda Section when two are unselected manually for all SG's | 3 - Medium | Ninjawarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | 4437844 | DSP | Active | Product Test
4487642 | MAT PT/UAT ¦ AMS/SI/IMS ¦ DCSO ¦ publish icon is not enabled/not working | 1 - Critical | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj | 4420374 | DCSO | Re-open | Product Test
4487880 | Regression : 18th Apr ¦ UAT ¦ Available hours-Toggle Off ¦ Months and values are not updating based on selected year when changing phase of profile | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | Regression | AMS | Active | User Acceptance Test
4487913 | 9 May ¦ UAT 1 ¦ Review Approvals ¦ IMS ¦ In Generative AI, without entering mandatory value on click on save "No record added or modified" message displayed instead of validation message. | 3 - Medium | CodeCrafters | madhuri.chintala | c.dhiman | sona.job | 4443485 | IMS | Ready to Deploy | User Acceptance Test
4487919 | MAY PT ¦ OCP-SI USER STORY ¦ Contingency & PMO, DEAL BILLING,PRICING 2 | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra |  |  | Active | Product Test
4487954 | 9th MAY ¦ SI ¦ PT ¦ Getting error while importing Staffing OU file | 3 - Medium | TechAvengers | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | Sanity | SI | Ready to Deploy | Sanity Testing
4488005 | MAY PT¦ OCP-SI USER STORY ¦ RATE CARDS 3 | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra |  |  | New | Product Test
4488073 | May 9th ¦¦ Prod ¦¦ DSP_Receiving locations_UI issue: Locations table not contained within slide_PPT/PDF issue | 2 - High | Pixel Pioneers | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | Prod Bug | DSP | Active | Product Test
4488444 | Regression : 18th Apr ¦ UAT ¦ Available hours-Toggle Off ¦ On changing default values from "No " to "Yes " for one row, it is retaining values of all the rows for both staffing and PMO | 3 - Medium | TechCoders | srinivasan.ks | vishnupriya.aluru | Francis.Deepak | Regression | AMS | Active | User Acceptance Test
4488498 | 09 May¦PT¦ Attach calculator¦ Unable to select version in attach calculator screen for security and sustainability calculator for SI SG. | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Attach Calculator | Ready to Deploy | Product Test
4488701 | 09 May¦PT¦ Attach calculator¦ Multiple UI issue on Calculator screen and attach/Detach icon | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Attach Calculator | Active | Product Test
4488707 | MAY PT¦ OCP-SI USER STORY ¦ COSMETIC ISSUE UI 4 | 4 - Low | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra |  |  | New | Product Test
4488879 | May 9 ¦ SI ¦ PT & UAT ¦ Rate Card ¦ Custom Rate card ¦ Inconsistence in the filter option for country/Location, Currency, SG-SSG Grid | 3 - Medium | TechWizards | madhuri.chintala | jayanth.kumar | mervinkumar.manickam | 4151502 | Rate card | Ready to Deploy | Product Test
4489208 | MAY PT¦ OCP-SI USER STORY ¦ COSMETIC ISSUE UI 5 | 4 - Low | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra |  |  | New | Product Test
4489351 | 9th May ¦ UAT ¦ SI ¦ Attach Calculator ¦ Package details are not getting removed when the version is exempted for implicit security calculator. | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Calculators | Active | Product Test
4489355 | 9th May ¦ UAT1 ¦ AMS Sanity ¦ Multiple issues identified between View KDA UI and View KDA Report. | 3 - Medium | CreativeCoders | srinivasan.ks | vishnupriya.aluru | K.devaraj | Sanity | AMS Sanity | Active | Sanity Testing
4489436 | 9th May ¦ UAT ¦ SI ¦ Attach Calculator ¦ Pop-up for exemption is in wrong alignment. | 4 - Low | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Calculators | Active | Product Test
4489440 | May9th_UAT1_MDA_In the MDA KDA report, the word "Contingency" is misspelled under the Mobilization Metrics section. | 4 - Low | SolutionDataLake | srinivasan.ks | vishnupriya.aluru | vishal.v.nadpurohit | Sanity | KDA Report | New | Product Test
4489669 | May09- PTEnv- SSA - Review Agent module - Comprehensive Review - L2 Attribute Nudge - Not getting proper response on click of 'Initiate Review' | 2 - High | Gen AI - Solution Review Agent | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4418789 | Gen AI | Blocked in PT | Product Test
4489673 | MAY PT ¦ OCP-SI USER STORY ¦ ocp screen 6 | 4 - Low | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra |  |  | New | Product Test
4490110 | May9th ¦¦ UAT1 ¦¦ MDA: IMS OCP Deal Pivot: SubService_ratio: Number of years should be dynamic to be in sync with other tabs | 4 - Low | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4455343 | MDA | Active | Product Test
4490559 | Apr 18¦¦ Prod Sanity ¦¦ OBM ¦¦ AMS DCTA / OCP - OBM Cost values are not matching with source KDA | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | Gen AI | Deferred | Product Test
4490561 | Apr 18 ¦¦ Prod Sanity ¦¦ SVC ¦¦ AMS OCP/DCTA - SVC KDA is not loading | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | Gen AI | Deferred | Production
4490564 | Apr 18¦¦ Prod Sanity ¦¦ OBM ¦¦ (Deal Specific - 0010771370) SI- getting slowness while clicking any dropdowns in both filters and benckmarks in Span of search | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | Gen AI | Deferred | Production
4490565 | Apr 18¦¦ Prod Sanity ¦¦ SI SG ¦¦ SVC> KDA Table and OBM>Metrics Table¦¦ OCP Route¦¦ Value mismatch issue | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | GEN AI | Deferred | Production
4490567 | Apr 18¦¦ Prod Sanity ¦¦ OBM ¦¦ AMS DCTA / OCP - OBM Metrics, SVC KDA - Offshore Ratio % value is not matching with source KDA | 4 - Low | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | Gen AI | Deferred | Production
4490568 | Apr 18¦¦ Prod Sanity ¦¦ OBM ¦¦ SI- Current column should not come for closed deals in Opportunity benchmark | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | Gen AI _ QDI | Deferred | Product Test
4490572 | Apr 18¦¦ Prod Sanity ¦¦ OBM ¦¦ IMS Core + Security DCTA ¦¦ Opportunity Metrics - Data Mismatch Issue | 3 - Medium | QDI - Opportunity Metrics | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | Sanity | Gen AI | Active | Production
4490719 | Sanity ¦ AI Foundry ¦ May PT ¦ Rampup Configuration is getting failed. | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | Sanity | AMS Solution Configuration Agent | New | Product Test
4490738 | May 9th ¦ UAT ¦ PLD ¦ FTS filed in assigned grid is not updated to "yes" even when FTS mail is triggered | 2 - High | Pacemakers | madhuri.chintala | c.dhiman | sona.job | 4440060 | Super user | Active | Product Test
4490744 | May 9 ¦ S2C ¦ Others ¦ Data AI & Data Migration ¦ Response is not getting generated for One Click Predefined Definition | 2 - High | Solution to Contract | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4438326 | Gen AI | New | Product Test
4490754 | May 9th ¦ UAT ¦ PLD ¦ FTS mail format is incorrect when we trigger mail from operation PLD | 3 - Medium | Pacemakers | madhuri.chintala | c.dhiman | sona.job | 4440060 | Super user | Active | Product Test
4490775 | May 9th ¦ AI Foundry ¦ PT ¦ US-4447669-Output summary is getting displayed with all the input details given in prompt | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4439786 | SCA | New | Product Test
4490793 | May 09 ¦ Agent AI Foundry ¦ US 4443558 ¦ Facing few issues while giving prompt to fetch all screen URLs. | 4 - Low | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4439786 | AMS Solution Configuration Agent | New | Product Test
4490800 | May 9th ¦¦ PT/UAT¦¦ DSP_Row Spacing Issue in Risks Tab UI | 3 - Medium | Pirates | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | PT Bug | DSP | New | Product Test
4490892 | May 9th ¦¦ PT ¦¦ UAT¦¦ DSP_ No Published version for Value story in the deal should be displayed in all tabs when version in Value shaping is not published | 3 - Medium | Pirates | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | 4437844 | DSP | New | Product Test
4490899 | 09 MAY 2026: PT/UAT1: Solution Versions are not displaying in IMS Mobilization Calculator Popup | 2 - High | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | Ready to Deploy | Product Test
4490966 | MAY 9th Rel ¦ PT ¦ New Offerings, Services, Sub Services | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4386339 |  | New | Product Test
4491019 | May9_UAT_ Automation Calculator_In ROI Screen info message is not showing for PA eligible but Assessment not taken deals | 3 - Medium | CrazyCoders | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4367874 | Automation Calculator | Ready to Deploy | Product Test
4491044 | May 9 ¦¦ May PT ¦¦ DLC versions are not flowing into Gen AI - DLC documents | 2 - High | Gen AI - Solution Review Agent | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar |  | DLC | Active | Product Test
4491065 | 09 May ¦ PT ¦ Attach Calculator ¦ AMS/SI ¦Getting error while synching automation calculator | 2 - High | CrazyCoders | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4387285 | Attach Calculators | Active | Product Test
4491081 | May 9th ¦ PT&UAT ¦ Attach Calculator ¦ When clicking on attach and selecting the version unable to select the older versions scroll is not working. | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4313249 | Attach Calculator | Ready to Deploy | Product Test
4491082 | May9¦ UAT¦ Automation Calculator¦ Loader Issue¦ In Attach Calculator>>Calculators>>Automation Calculator>>When user click on Attach icon then taking more time to load the versions. | 3 - Medium | CrazyCoders | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4367874 | Attach Calculator | New | Product Test
4491085 | May 9 ¦¦ May PT ¦¦ Unable to see slide Tagging's in Other Template Based Decks/ All Output Documents for all SG's | 3 - Medium | Ninjawarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | 4437844 | DSP | Active | Product Test
4491097 | 9th May ¦ UAT1 ¦ SI ¦ In KDA Variance Analysis Deal RAG Status is not matching with Adherence score for DATA KDA | 3 - Medium | Insurgents | srinivasan.ks | vishnupriya.aluru | K.devaraj | 4441807 | SI Data | Ready to Deploy | Product Test
4491106 | May09- PTEnv- SSA - Review Agent module - Start New Self Review - DLC ingestion is not working successfully, loading for long time. | 2 - High | Gen AI - Solution Review Agent | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4418789 | Gen AI | Ready to Deploy | Product Test
4491114 | May 9 ¦¦ May PT & UAT ¦¦ Getting issues while adding custom slide functionality. | 3 - Medium | Ninjawarriors | srinivasan.ks | murugan.ssubramanian | pandidurai.ks |  | DSP | Active | Product Test
4491120 | May9 ¦ PT ¦ UI issues in Import Version for Mobilization Calculator pop up | 4 - Low | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491125 | 09 May ¦ PT ¦ On click of define estimator breadcrumb in mobilization calculator screen its navigating to landing page | 3 - Medium | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4386528 | IMS Mobilization Calculator | Active | Product Test
4491127 | May 9th_UAT1_Query_IMS_Reg MDA Sync in closed deals | 3 - Medium | SolutionDataLake | srinivasan.ks | vishnupriya.aluru | vishal.v.nadpurohit | 4454772 | MDA Sync | BA clarification | Product Test
4491156 | May 9th ¦ AI Foundry ¦ PT ¦ US-4447669-When user giving Long input for other fields Values not getting saved in UI | 3 - Medium | CodeCrafters | madhuri.chintala | c.dhiman | sona.job | 4439786 | SCA | BA clarification | Product Test
4491170 | May 9 ¦¦ May PT¦¦ Locked DLC Version is getting deleted by other user | 3 - Medium | Code Mavin | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar |  |  | Active | Production
4491186 | May 09 ¦ Agent AI Foundry ¦ US 4443558 ¦ The user request was only to share the Pricing Input URL but Save Dealwide Pricing and Save Pricing Configuration is getting called | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4439786 | AMS Solution Configuration Agent | New | Product Test
4491187 | 9th May ¦ PT ¦ CDAT PMO ¦ Extra option gets displayed under Contract Submission Status in CDAT PMO Dashboard. | 4 - Low | TechTribe | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | 4459051 | CDAT | Active | Product Test
4491190 | MAY PT ¦ OCP-SI USER STORY ¦ Contingency & PMO 7 | 4 - Low | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra |  |  | New | Product Test
4491193 | May 09 ¦ Agent AI Foundry ¦ US 4443558 ¦ Requested Generate Pricing URL but Generate Pricing Operation is getting failed | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4439786 | AMS Solution Configuration Agent | New | Product Test
4491205 | MAT PT/UAT ¦ BPMS ¦ Status update screen¦ if i search one enterprise id and select that after i am searching another id that is not showing | 4 - Low | NGTransformers | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4437418 | BPMS | Active | Product Test
4491428 | May 9th ¦ PT ¦ Mobilization Calculator ¦¦ The career levels and bill code order is incorrect in filter option in weekly ramp screen. | 3 - Medium | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4232673 | Mobilization - Bottom up Approach | New | Product Test
4491433 | May 09 ¦ Agent AI Foundry ¦ US 4443558 ¦ Groups Screen not enabled from version screen but accessible via agent link | 2 - High | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4439786 | AMS Solution Configuration Agent | Active | Product Test
4491449 | May 09 ¦ Agent AI Foundry ¦ US 4443558 ¦ When Version number is not mentioned in the Get URL prompt, proper validation message should be displayed in output summary | 3 - Medium | agentcrafters | krishnaveni.ayyappan | krishnaveni.ayyappan | shwetha.shriyan | 4439786 | AMS Solution Configuration Agent | New | Product Test
4491456 | 9th May ¦ PT ¦ SRA ¦ marking someone else self review as final self review version is not updating the "MODIFIED BY" field name | 3 - Medium | Gen AI - Solution Review Agent | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4420086 | Gen AI | Ready to Deploy | Product Test
4491465 | May9 ¦ PT ¦ Expand and collapse icons are not showing in the Package Selection Criteria tab. | 4 - Low | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4386528 | IMS Mobilization Calculator | Active | Product Test
4491466 | 09 May¦UAT¦ Attach calculator¦ After detaching the sustainability calculator, the details are still present in staffing and costing screen for AMS. | 2 - High | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Attach Calculator | Active | Product Test
4491498 | 9th May ¦ PT ¦ SRA ¦ unable to unmark the final self review version | 3 - Medium | Gen AI - Solution Review Agent | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4420086 | Gen AI | BA clarification | Product Test
4491506 | May ¦ Calculators ¦CTW Readiness ¦ Not able to download PPT | 4 - Low | CodeCatalyst | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4434343 | BPMS - CXTA | Ready to Deploy | Product Test
4491519 | May 9th Rel ¦ PT ¦ New Offerings, Services, Sub Services - 1 | 3 - Medium | myISP_IMS | Rajsingh.rajput | rajaraman.mahalingam | supriya.a.dhingra | 4386339 |  | New | Product Test
4491520 | 09 May ¦ PT ¦ Order of records are not populating correctly in dashboard based on last modified in calculators screen | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491524 | 09 May ¦ PT ¦ Search icon is not displaying on top of the dashboard grid | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491534 | 09 May ¦ PT ¦ Automation calculator ¦ AMS ¦ The "Exempt" button color is not updating, and the cost values are not being rolled back after exemption | 2 - High | CrazyCoders | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4387285 | Attach Calculators | New | Product Test
4491536 | 09 May ¦ PT ¦ IMS Mobilization calculator launch is in enable mode in gallery tab for all roles | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491549 | 09 May ¦ PT ¦ Opportunity workflow breadcrumb is not working in Mobilization calculator screen | 3 - Medium | Everest | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4386528 | IMS Mobilization Calculator | Active | Product Test
4491550 | 09 May ¦ PT ¦ Automation calculator ¦ SI ¦ Costs are not being rolled back after exemption and toaster message is appearing on the left side, which is not expected. | 2 - High | CrazyCoders | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4387285 | Attach Calculators | New | Product Test
4491552 | May 9 ¦ S2C ¦ Others ¦ Data AI & Data Migration ¦ Getting Older nudge in toaster message | 3 - Medium | Solution to Contract | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | 4438326 | Gen AI | New | Product Test
4491553 | May 9th ¦ PT/UAT ¦ Attach Calculator ¦ Choose columns filter in only working on double click in Asset List. | 3 - Medium | TitansPlus | srinivasan.sivakumar | suresh.devarajan | nityanand.giri | 4372279 | Attach Calculator | Active | Product Test
4491573 | May 9th ¦ UAT1 ¦ DSP ¦ Value story ¦ Sub sections are not visible when opening key callouts in Client diagnostics | 4 - Low | Pixel Pioneers | srinivasan.ks | murugan.ssubramanian | pandidurai.ks | 4437844 | DSP | New | User Acceptance Test
4491581 | May 9 ¦¦ May PT¦¦ Client context - Some Words being cut-off in a BPMS response in DLC nudges | 3 - Medium | Code Mavin | srinivasan.ks | murugan.ssubramanian | n.d.krishnakumar | User story |  | New | Production
4491595 | May9 ¦ PT ¦ Updated On is showing incorrect in Import Version for Mobilization Calculator popup | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491609 | May9 ¦ PT ¦ On removing name and comments in Import Version popup and clicking on save icon, removed data is displaying back | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491611 | May9 ¦ PT ¦ Incorrect alignment is showing when user entered Name and Comments length is long in Import Version popup | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491631 | May9 ¦ PT ¦ Getting data saved successfully toaster message even if no modification done for version in Import Version popup | 3 - Medium | TechWarriors | madhuri.chintala | sankaran.viswanathan | sowjanya.kari | 4386528 | IMS Mobilization Calculator | New | Product Test
4491697 | MAT PT/UAT ¦ AMS/SI/IMS ¦ DCSO ¦ toaster message is showing incorrect and publish on column not showing | 3 - Medium | TechStars | srinivasan.ks | vishnupriya.aluru | mohanraj.a.selvaraj | 4420374 | DCSO | New | Product Test